## Slide 1
CCWG on Enhancing ICANN Accountability
Charter

## Slide 2
Items covered in Charter
Problem statement, goals & objectives and Scope
Deliverables, timeframes & reporting
Membership, staffing and organization
Rules of engagement, including decision-making methodologies

## Slide 3
Goals & Objectives
Primary goal is to deliver proposals that would enhance ICANN’s accountability towards all stakeholders.
Goal is for the IANA Stewardship Transition proposal to be communicated in a timeframe which is consistent with the expiration date of the current IANA Functions Contract (30 September 2015).

## Slide 4
Scope
In scope: accountability mechanisms regarding all of the functions provided by ICANN;
Out of scope: accountability for the administration of the IANA (addressed by communities outlined in the ICG Request for Proposals);
2 tracks are "interrelated and interdependent" therefore coordination will be key.

## Slide 5
Two Work Streams
Work Stream 1: focused on mechanisms enhancing ICANN accountability that must be in place or committed to within the time frame of the IANA Stewardship Transition;
Work Stream 2: focused on addressing accountability topics for which a timeline for developing solutions and full implementation may extend beyond the IANA Stewardship Transition.

## Slide 6
Deliverables & Timeframe
Allocate issues to Work Stream 1 (WS1) and Work Stream 2 (WS2). Some issues may span both Work Streams.
WS1 deliverable of the CCWG will be provided to the ICG and CWG-Stewardship. The delivery of WS1 Proposal is expected to occur following approval of the ICANN Board.
First step is to develop work plan and timetable, and align the timelines for WS1 with the CWG-Stewardship and ICG timelines.

## Slide 7
Areas of Work - Summary
Review of the Guidelines in the Charter | Definition / description of what differentiates WS1 from WS2 | Identify what issues go in WS1 and which go into WS2 | Timeline of key dates & target dates for each work stream
Review existing accountability mechanisms | Identification of contingencies | Analysis of core issues in relation to CCWG goal and IANA Stewardship Transition | Identification of priorities
Review and analyze statements from US DoC | Review of possible solutions | Consider methodology for stress tests | Structure its work to ensure that stress tests can be designed & carried out

## Slide 8
Group Composition
Members appointed by chartering organizations
Participants – open to anyone interested
ATRT Expert (past participant)
ICANN Board liaison
ICANN Staff representative
All to participate on equal footing – only in circumstances where a formal consensus call may be required, this would be limited to members

## Slide 9
Expert Advisors
In addition to community, CCWG will have input from the Advisors selected by the Public Experts Group.
Advisors are expected to contribute to the dialogue – similar to other CCWG participants.
CCWG may identify additional advisors to contribute to its deliberations. Should additional costs be involved, prior approval must be obtained from ICANN.

## Slide 10
Decision-making Methodology
Chairs responsible for designating recommendations as having:
  Full consensus – a position where no minority disagrees ; identified by an absence of objection
  Consensus – a position where a small minority disagrees, but most agree
Minority viewpoints, if applicable, to be included in the CCWG report

## Slide 11
Further Information
Please review the full charter in detail, available from: https://community.icann.org/x/XQHxAg

## Slide 12
CCWG on Enhancing ICANN Accountability
Working Methods

## Slide 13
Principles of Operation
Rotate meetings from a timing perspective to share the burden as members and participants are located in different time zones (proposed 11:00 and 14:00 UTC)
No firm decisions are taken during any single meeting without the substance of those decisions having been articulated and open for review / consideration by those that may not have been present during the meeting

## Slide 14
Roles & Responsibilities
Members are expected to communicate the views of the communities that have selected them to the CCWG, but also communicate back the information and deliberations from the CCWG to their respective communities
Members and participants are expected to be familiar with and remain consistent with the pre-existing documents and documents developed during the course of the work of the CCWG

## Slide 15
Working Tools
Wiki space: https://community.icann.org/x/ogDxAg
Mailing list address: accountability-cross-community@icann.org
Public Archive: http://mm.icann.org/pipermail/accountability-cross-community/
Adobe Connect room: https://icann.adobeconnect.com/accountability/
Participation on calls is limited to CCWG members and participants only (to remain focused on the work), but there is an audio stream option (listen-only) for observers