ACCOUNTABILITY AND TRANSAPRENCY REVIEW TEAM

PROPOSED WORK SCHEDULE

May 27, 2010 – Approved RFP issued

June 18 and 19, 2010 – RT meetings – Brussels; presentations from RFP Management Assessment candidates to RT

July 2, 2010 – Selection of Management Assessment candidate; RT reviews inputs from ICANN Community, ACs/SOs, Board, GAC, Council; develop case study(s) for analysis and review

July 9, 2010 – Management Assessment begins

Week of August 29 – September 4, 2010 – RT reviews Management Assessor’s mid-term report; develops case study(s); feedback to Management Assessor for final assessment; review of draft case study(s) and review from Community, ACs/SOs, Board, GAC, Council feedback.

October 12-14 – RT meeting in Egypt; review data and analysis of all subcommittees; discussion and organization of initial draft recommendations

October 31, 2010 – Management Assessor’s final report to RT

December 5-10 – RT meeting in Cartegena; presentation of draft recommendations to ICANN Community and Community feedback

December 31, 2010 – Final recommendations submitted