## SSR
Questions from ATRT2 regarding implementation of recommendations of SSR
SSR Recommendations | Implementation assignments |  | A. What was the baseline? | B. What did s/he understand the recommendation to be? | C. What did s/he understand the underlying issue to be that led to the recommendation? | D. What did s/he understand the desired outcome to be from the recommendation? | E. How did s/he implement the recommendation? What options were considered and how was the actual option chosen for implementation? | F. Percentage/portion that is complete? | G. Does s/he believe ICANN fully implemented the recommendation? If not, why not? If not, what parts were not implemented, and why not? | H. Did s/he run into any new or unforeseen problems or issues while implementing the recommendation? (i.e. scope increase, costs, legal, resources, timing) | I. Did s/he identify additional opportunities for improvement by virtue of the implementation of these recommendations? | J. What has been the outcome and effect both inside ICANN and external to ICANN as a result of the implementation of the recommendation? | K. What has been the feedback both inside ICANN and external to ICANN as a result of the implementation of the recommendation? | L. How does s/he feel that ICANN has improved as a result of the implementation of the recommendation? | M. What were the dependencies as seen from each group involved in implementation? | N. In view of ATRT1 what changes in workflows and/or organization where undertaken? | Additional Information
1. ICANN should publish a single, clear and consistent statement of its SSR remit and limited technical mission. ICANN should elicit and gain public feedback in order to reach a consensus-based statement. | Security | Staff: Patrick Jones | ICANN has previously published a description of its role and remit and technical mission from the annual Security, Stability and Resiliency Framework. This document has been published annually since 2009. A draft statement of ICANN's role and remit in SSR was published in May 2012 with public comment through September 2012. This draft drew from ICANN's Bylaws, Mission and Core Values, but also from the original Green Paper and White Paper, and the Affirmation of Commitments. | ICANN understood the recommendation to be as stated in the Final Report and Recommendations of the SSR Review Team (http://www.icann.org/en/about/aoc-review/ssr/final-report-20jun12-en.pdf). | Per the Final Report of the SSR Review Team, it was noted that it would be useful for ICANN to develop a single, clear statement of SSR responsibilities from which all activities can be linked. | We understood the desired outcome to be a consensus-based, concise but clear statement of ICANN's role and remit in security, stability and resiliency of the Internet's unique identifiers and technical mission. | The Security team published a draft statement for public comment in May 2012 and conducted extensive outreach with the community to facilitate feedback. A report of the public comments received was published, and a revised draft statement was published for the ICANN meeting in Toronto (http://toronto45.icann.org/meetings/toronto2012/presentation-draft-ssr-role-remit-04oct12-en.pdf). Following an open session in Toronto and additional community engagement, a new version of the statement was incorporated into the FY 14 SSR Framework, published for public comment on 6 March 2013. This document is open for public comment through 20 May 2013 (end of the reply comment period). | We believe this recommendation will be completed following the end of public comment on the FY 14 Framework, incorporation of any revisions necessary, and acknowledgement of the Framework by the ICANN Board at the next available meeting (likely Durban). | Staff is still in the process of encouraging public comment on the text to address Recommendation 1 as part of the FY 14 SSR Framework. | Not yet. | The draft statement has already received positive feedback from the community and we think this will be useful as ICANN uses this statement and SSR terminology in engagement efforts with the community (and to encourage those not currently participating to do so). | We are still taking public comment on the text, but input received on the earlier draft statement has been very positive. Internal to ICANN this has given the new Senior Management Team language for ICANN's role and remit in SSR. Externally, the community participants who have contributed to the review of the text have noticed the improvement in language over time and have been supportive of this text. | See comment on J. | We are still taking public comment on the implementation and text. | The first dependency was to take public comment on a proposed text. This has been done, and a revised text has been published. This text has been further revised and incorporated into the annual SSR Framework. The next step will lead into SSR Recommendation 3, utilizing consistent terminology by the organization in materials, and Recommendation 4, documenting and defining the nature of SSR relationships. | No workflow changes anticipated. | The feedback on the draft statement was generally positive.
2. ICANN’s definition and implementation of its SSR remit and limited technical mission should be reviewed in order to maintain consensus and elicit feedback from the Community. The process should be repeated on a regular basis, perhaps in conjunction with the cycle of future SSR reviews. | Security | Staff: Patrick Jones | The definitions and description of ICANN's role and remit should be reviewed regularly. This is done as part of the annual SSR Framework. Overall, this recommendation will be addressed also by the next SSR Review, which will commence in 2015. | Our understanding is the recommendation is as stated in the Final Report and recommendations (see above). | The Review Team thought it important to ensure ICANN's definitions and implementation were reviewed in a repeatable, regular basis. | The desired outcome is to implement a regular process for reviewing the implementation of the SSR recommendations. | The Security team has incorporated a tracking page in the annual SSR Framework showing how the previous year's activities were implemented. The SSR RT recommendations are also included in this tracking. | Rec 2 is being addressed through the FY 14 Framework, next opportunity to review would be in publication of the FY 15 Framework in 2014, and as part of the SSR RT2 kicking off in 2015. | This recommendation is not yet implemented. | No unforeseen problems. | The discussion with the SSR Review Team over the 18+ months of its work led to a number of improvements between the FY 12 and FY 13 versions of the Framework (now reflected in the current FY 14 version). | Security is one of the few departments that publishes its own annual Framework and regularly seeks public input on its activities. | The SSR RT had positive comments for the manner in which staff made improvements to the annual Framework during the Review Team's work, from the FY 12 Framework to the FY 13 Framework. This has continued through to the FY 14 version. | The team has seen substantial improvement from the FY 12 to FY 14 Framework over the past 2 years. The SSR RT process was very helpful in refining the messages and focus of the team. |  | No workflow changes anticipated.
3. Once ICANN issues a consensus-based statement of its SSR remit and limited technical mission, ICANN should utilize consistent terminology and descriptions of this statement in all materials. | Security | Staff: Patrick Jones | ICANN first had to develop a statement of its SSR role and remit. | Our understanding is the recommendation is as stated in the Final Report and recommendations (see above). | ICANN needed to use consistent terminology across the organization when describing its SSR role and technical mission. | The desired outcome is for the entire organization and community to understand the common terminology on ICANN's SSR role and remit and be aware that ICANN has defined its technical mission, so that these are used consistently across the organization. | This recommendation has not yet been implemented, but will be addressed after the completion of the FY 14 SSR Framework comment process. The Security team will first start with an internal ICANN education process and expand that to reach out to the SO/AC, stakeholder groups and broader community. | This will be addressed after completion of the comment period on the FY 14 SSR Framework. | This recommendation is not yet ready for implementation. |  |  | We think this will help all parts of the organization have a common understanding of ICANN's SSR role and remit and use consistent terminology in its materials and discussions. |  | This should provide all parts of the organization with a common base of understanding.
4. ICANN should document and clearly define the nature of the SSR relationships it has within the ICANN Community in order to provide a single focal point for understanding the interdependencies between organizations. | Security | Staff: Patrick Jones | ICANN's SSR relationships take many forms, and other than the ICANN website sections showing its MOUs, agreements and partnerships, there is no central location at ICANN for easily seeing (internally or externally) ICANN's SSR relationships. | Our understanding is the recommendation is as stated in the Final Report and recommendations (see above). | The Review Team felt it would be helpful for ICANN to document and define the nature of the SSR relationships that exist for the organization (to parties in the community, the Supporting Organizations and Advisory Committees, but also to non-contracted parties and partners), and place this information in a location where ICANN and the community can see the description of the relationships and consider interdependencies. | The desired outcome is to have an easy to find documentation of ICANN's SSR relationships (in form and type), and also an accurate depiction of the SSR functions. | The first step has been the development of an infographic depicting the SSR functions at ICANN, showing the organizational risk management function, threat awareness, coordination function and subject matter expertise function. Within each of these areas, will be a mapping to show the relationships that fall within these areas. Version 1.0 of the infographic was included in the FY 14 SSR Framework. | The first stage of work to address implementation has been done, to develop the mapping of the SSR functions. We are now mapping the relationships to the functional areas. | This recommendation is not yet fully implemented. |  | Yes, the exercise to develop the functional graphic has helped sharpen the language on ICANN's security related technical engagement and we have made improvements to our material for the community. | This work has also produced useful material for educating those inside the organization on the role of security and the different functions of SSR. | The feedback so far has been very positive. | Recommendation not yet fully implemented.
5. ICANN should use the definition of its SSR relationships to maintain effective working arrangements and to demonstrate how these relationships are utilized to achieve each SSR goal. | Security | Staff: Patrick Jones | Currently SSR relationships are not well documented. | Our understanding is the recommendation is as stated in the Final Report and recommendations (see above). | ICANN's SSR relationships are not well documented. Changing this and making it apparent both for the organization and community to see how ICANN has extensive relationships in SSR, should enable effective working arrangements and show how these relationships support ICANN's SSR goals. | The desired outcome is an easy to find documentation of SSR functions and relationships, so that the organization and community can see the functions and relationships and have an understanding of their connection to ICANN's SSR goals. | This has not yet been implemented, and is connected to the completion of Recommendation 4. | Although the definition is not yet complete, there has been progress in documenting relationships with the establishment of the Global Stakeholder Engagement team and support of regional strategies. We are probably at 40% now. | Will be addressed with Recommendation 4. | Not an unforeseen problem, but it did highlight areas for better coordination and collaboration internally between departments so that there is a recognition of existing relationships and how these contribute to effective working arrangements. | Better coordination between departments (regular calls and interaction between GSE and Security, regular discussion between Policy and Security) | This recommendation is in process for implementation. | This recommendation is not yet implemented. |  | Identification of existing MOUs, Agreements, contracts, partnerships, informal relationships.
6. ICANN should publish a document clearly outlining the roles and responsibilities for both the SSAC and RSSAC in order to clearly delineate the activities of the two groups. ICANN should seek consensus for this across both groups, recognizing the history and circumstances of the formation of each. ICANN should consider appropriate resourcing for both groups, consistent with the demands placed upon them. | Security | Staff: Patrick Jones | The ICANN Bylaws contain provisions for SSAC and RSSAC. SSAC has published its Operating Procedures, per implementation of the SSAC Review. The ICANN Board recently approved a bylaws change for RSSAC on 11 April 2013. | Our understanding is for the publication of text describing the roles and responsibilities for SSAC and RSSAC, and that this text should have the support of each Advisory Committee. The last sentence is on ensuring both Advisory Committees have appropriate resourcing (staff and budget). | The underlying issue was to provide some clarity to the roles and responsibilities of each Advisory Committee, to avoid confusion and conflict. | A description of the roles and responsibilities for each Advisory Committee (SSAC and RSSAC) that was supported by each. Appropriate resourcing for both groups. | Staff's approach, following a presentation to SSAC in November 2012, is to divide implementation into Recommendation 6A (SSAC) and 6B (RSSAC). The roles and responsibilities for SSAC are already defined in its Operating Procedures. The roles and responsibilities for RSSAC are being examined and revised with the implementation of the Board's adoption of the bylaws change for RSSAC. | This recommendation is approximately 50% complete (6A is largely done, except for the publication of the roles and responsibilities for SSAC and confirmation from SSAC that the text is appropriate). 6B will involve staff and RSSAC collaboration to ensure the text has its endorsement. | Not yet fully implemented. Board only recently adopted bylaw changes for RSSAC in Beijing. | Not unforeseen, but there has been a delay while waiting for RSSAC bylaw changes. This is a recommendation that will involve community-staff collaboration to be implemented. |  | This recommendation is in process for implementation. | SSAC members were presented with the proposed implementation path in November 2012, and were supportive of the approach at that time |  | RSSAC and SSAC acknowledgement of the proposed roles and responsibilities text.
7. ICANN should build on its current SSR Framework by establishing a clear set of objectives and prioritizing its initiatives and activities in accordance with these objectives. This process should be informed by a pragmatic cost-benefit and risk analysis. | Security | Staff: Patrick Jones | ICANN has had a set of objectives and priorities for several years in SSR, in the Strategic and Operating Plans, along with the annual SSR Framework. | Our understanding was there should be improvement to the development of ICANN's SSR objectives, informed by a cost-benefit and risk analysis. | The Review Team felt the objectives in the ICANN Strategic Plan were not clearly mapped or prioritized, and this was reflected in the earlier versions of the SSR Framework prior to FY 13's version. | ICANN should build from improvements in the FY 13 SSR Framework to establish a clear set of objectives and priorities related to SSR. | We think we have made improvements toward the recommended clarity in the past two Frameworks, to the version out for comment now for FY 14. Further improvement will be made with the mapping of priorities to the Management delivery system and At Task. | Some of this recommendation is pending completion of the FY 14 operating plan and budget process. | This recommendation is not yet fully implemented. | Not unforeseen. Full implementation will involve internal discussions with other departments and Executive team. |  | We think this will lead to general agreement across the organization of the SSR objectives and priorities. | The ccNSO in Beijing was supportive of continued priority for technical engagement and training, and Security is one of the pillars in the regional strategies being developed for Africa, Asia-Pacific, Middle East and Latin America & Caribbean. Technical engagement is one of the priorities for the team. | We think this recommendation will help show a better connection between the published strategic objectives and the SSR initiatives. | Fy 14 operating plan completion, use of At Task, development of next Strategic Plan.
8. ICANN should continue to refine its Strategic Plan objectives, particularly the goal of maintaining and driving DNS availability. The Strategic Plan and SSR Framework should reflect consistent priorities and objectives to ensure clear alignment. | Security | Staff: Patrick Jones | ICANN has had a set of objectives and priorities for several years in SSR, in the Strategic and Operating Plans, along with the annual SSR Framework. | The Review Team felt the SSR objectives in the 2012-2015 Strategic Plan were not well refined and aligned with the SSR Framework. We understood the recommendation to be calling for improvement of the Strategic Plan objectives related to SSR. | See comment in B. | Desired outcome would be an improvement in the Strategic objectives related to SSR and an alignment between those objectives and the SSR Framework. | The Security team has been contributing to the Strategic Visioning effort for a new ICANN Strategic Plan, and encouraging the use of materials developed for the FY 14 SSR Framework which describe ICANN's SSR functions into 4 main areas (organizational risk management, technical engagement & thought leadership, coordination, threat awareness) | Completion of this recommendation is dependent on development of the next Strategic Plan. | This recommendation is not yet fully implemented. | We see no additional costs to implementation, but this will involve organizational discussions for the next Strategic Plan and then alignment of the SSR Framework to the Strategic Plan.
9. ICANN should assess certification options with commonly accepted international standards (e.g. ITIL, ISO and SAS-70) for its operational responsibilities. ICANN should publish a clear roadmap towards certification. | Security | Staff: Patrick Jones | ICANN has achieved SysTrust certification for the DNSSEC infrastructure, and is exploring SysTrust for IANA (which would include IT). | The recommendation was calling for ICANN to assess its certification options against commonly accepted international standards for its operational responsibilities, make a determination on whether to pursue certification, and if so, publish a clear roadmap for certification. | The Review Team spent some time discussing international standards and noted that ICANN should publish a roadmap toward certification for those processes and functions that it determines it should seek certification. | The desired outcome was to undertake an assessment for certification of ICANN's operational responsibilities, and if certification was pursued, to publish a clear roadmap for the community (and for ICANN) to follow. | Discussion with IT, IANA and other departments impacted by certification. IANA is pursuing SysTrust and EQFM for its processes. | Assessment is currently underway within IANA, IT. Security is providing a supporting role in this process. ICANN is working with an outside consultant to assist with completion of this assessment. | This is not yet fully implemented but the assessment is underway. | Not yet, but assessment can be costly and implementation of all controls necessary for certification (depending on the certification selected) may require additional time and budget. |  | Assessment is still underway. We think this will show that ICANN carefully considered certification and demonstrates operational excellence in its operational responsibilities. | Implementation is still in process as part of the assessment phase. | We think this will institutionalize the best practices needed to sustain certification (depending on certification or standard chosen), and will demonstrate ICANN's improvement toward operational excellence. | Assessment of capabilities and needs with IANA, IT, other key departments.
10. ICANN should continue its efforts to step up contract compliance enforcement and provide adequate resources for this function. ICANN also should develop and implement a more structured process for monitoring compliance issues and investigations. | Security (Compliance) | Staff: Patrick Jones | This recommendation was aimed at the Compliance team. When the Review Team had started its work, the Compliance Department was a much smaller group at ICANN. | The understanding was for ICANN to improve its Contractual Compliance efforts and provide adequate resources, develop and implement a more structured process for monitoring compliance. | When the Review Team had started its work, Compliance was a smaller team, and the community strongly felt that ICANN needed to step up in this area. | The desired outcome was for dedicated improvement to ICANN's contractual compliance enforcement and adequate resourcing. | We think this recommendation has been largely implemented with the improvements made by the Compliance team throughout FY 13. Compliance has grown in size and published a number of tools to enable better contract compliance enforcement. | We think this recommendation is largely complete through the work of the Compliance team in FY 13. | This recommendation is mostly (if not fully) implemented. | This is a question for the Compliance team. | ICANN has grown the Compliance team and published a number of tools to better track their progress. | This should be asked of the Compliance team.
11. ICANN should finalize and implement measures of success for new gTLDs and IDN fast track that expressly relate to its SSR-related program objectives, including measurements for the effectiveness of mechanisms to mitigate domain name abuse. | Security | Staff: Patrick Jones | The Review Team noted that the administration of the nTLD program, IDN Fast Track were significant SSR issues that should be prioritized and implemented with a more detailed set of objectives and activities. They noted that ICANN should develop and implement measures of effectiveness for these areas. | We understand the recommendation to be as written in the Final Report. | The development and implementation of specific measurements will help strengthen ICANN's focus and effectiveness, and improve the ability of the community to gauge ICANN's progress. | Measures of success for nTLDs and IDN Fast Track that relate to ICANN's SSR objectives, including measurements of effectiveness of mechanisms to mitigate domain name abuse. | This will be a community-staff collaborative recommendation, and will also depend on terms of reference for the Affirmation of Commitments Review on Competition & Consumer Choice. | This recommendation is not yet implemented. | This recommendation is not yet ripe for implementation.
12. ICANN should work with the Community to identify SSR-related best practices and support the implementation of such practices through contracts, agreements and MOUs and other mechanisms. | Security | Staff: Patrick Jones | The Registrar Accreditation Agreement and gTLD registry agreements have some SSR-related best practices. The most recent RAA and gTLD registry base agreement have additional SSR-related practices. | The recommendation was for Staff to work with the community to identify SSR-related best practices & support implementation in contracts, agreements, MOUs and other mechanisms. | The underlying issue was that there should be clearer identification of SSR-related best practices for the community and encouragement for putting those best practices into contracts, agreements, MOUs and other mechanisms as best as possible. | The desired outcome was for a staff-community dialogue on SSR-related best practices, with the incorporation of best practices into contractual mechanisms as much as practical and possible. | This recommendation has not yet been fully implemented and will involve community-staff dialogue. We do think much of the interaction with law enforcement over the past few years from the Law Enforcement recommendations on the RAA and inputs into the new gTLD registry agreement have brought us closer to implementing this recommendation. | This is partially complete with the incorporation of SSR language into the new gTLD registry agreement and 2013 RAA out for public comment now. We will need to produce a list of SSR-related best practices and where incorporated in contracts, agreements, MOUs and other for tracking purposes. | This is not yet fully implemented. See comment in F. | Not unforeseen but this recommendation will involve community-staff dialogue for full implementation. |  | We think this will make it easier to see where the SSR-related best practices exist in agreements, contracts, MOUs, etc. Keep in mind these may (and are expected to) evolve over time. |  |  | Community-staff dialogue
13. ICANN should encourage all Supporting Organizations to develop and publish SSR- related best practices for their members. | Security | Staff: Patrick Jones | Individual participants in ICANN Supporting Organizations may follow best practices, but there has not be an effort to encourage all SOs to develop and publish SSR-related best practices. This activity may occur within stakeholder groups in the GNSO, and the ccNSO does have a Tech Working Group that is looking at Security practices for ccTLDs. | We understood the recommendation was to encourage Supporting Organizations to develop and publish SSR-related best practices for their members. | The underlying issue was to encourage all Supporting Organizations (and stakeholder groups) to develop and publish SSR-related best practices. | The desired outcome is for the appropriate Supporting Organizations (and stakeholder groups) to develop and publish SSR-related best practices for their members. | This recommendation will involve community-staff dialogue for full implementation. We are participating in the ccNSO Tech Working Group, which is looking at publishing a form of guidance for TLD operators (best practices is a sensitive term for ccTLD operators), we will also reach out to the stakeholder groups within the GNSO, and check with the ASO. | We are in the early stages of this recommendation and implementation is still underway. | This recommendation is not yet fully implemented.
14. ICANN should ensure that its SSR-related outreach activities continuously evolve to remain relevant, timely and appropriate. Feedback from the Community should provide a mechanism to review and increase this relevance. | Security | Staff: Patrick Jones | SSR-related outreach has centered on technical training and participation by ICANN staff in community activities (IETF, Network Operator Group meetings, RIR meetings such as RIPE NCC, regional IGFs and at the Internet Governance Forum). | The recommendation supported the Security team's SSR-related outreach activities. | The recommendation was supportive of existing outreach activities and recommending that ICANN ensure these activities continuously evolve to remain relevant, timely and appropriate. There should also be a feedback mechanism to review and increase this relevance. | The recommendation encouraged continued focus on ICANN's SSR outreach and a reflection by ICANN to ensure these outreach activities are evolving to meet the needs of ICANN and the community. | The Security team has increased its targeted approach to receiving feedback from ccTLD community, regional operators, the Business Constituency, registries and registrars, but also to make sure other parts of the community are involved in these discussions (governments & law enforcement, non-commercial stakeholders, academia & civil society, operational security community). | We think this recommendation has been met with the annual SSR Frameworks and approach to engaging with TLD operators, law enforcement and community groups, however, the ATRT2 should keep in mind that this recommendation is very open ended. We do not think this is one that is ever "done". For our tracking purposes, this has been addressed for Fy 14 budgeting, and now we need to deliver on requested trainings and engagement. | This recommendation is not one that can be checked off after completion, it has to stay a priority for the organization. | No unforeseen problems but acknowledgement that it is one that is not completed with the deployment of a service or project. This is an open ended recommendation. | This recommendation helped refine our messaging that technical engagement is one of the central functions of ICANN Security. | See comment in L. We have received broad community support for the types of technical engagement performed by ICANN Security and we do think this outreach is evolving to meet the needs of the community. There is an increased number of requests from our Global Stakeholder Engagement team for Security support at Internet Governance events (ITU, WSIS Forum, IGF, OECD, etc). Increase with the implementation of the Speakers Bureau tool. | This has been largely positive of the SSR-related outreach and engagement. We are struggling to meet all the demands for outreach and engagement. | We think ICANN has improved its support for meeting community SSR-related outreach needs over the last 2 years. | Having the feedback loop from the community on the types of engagement is important.
15. ICANN should act as facilitator in the responsible disclosure and dissemination of DNS security threats and mitigation techniques. | Security | Staff: Patrick Jones | ICANN already participates in trusted security circles for the sharing of threat information. | The recommendation supported ICANN Security's activity as a facilitator with the community in the responsible disclosure and dissemination of DNS security threats and mitigations. | The underlying issue was to encourage ICANN to continue to act as a facilitator, and to provide a standard process for those in the community who may have information of potential DNS security threats to share them in a manner in which they can be acted upon. | See comment in C. | ICANN published responsible disclosure guidelines on 11 March 2013 and presented those guidelines at the ICANN meeting in Beijing. | We think this recommendation is complete. There will be an on-going activity for acting as a facilitator, but the tools to enable facilitation are in place. | Yes, we think this recommendation is implemented. | No unforeseen problems. | This has helped streamline our process and channels for directing information on DNS threats and mitigations. | Internally there is acknowledgement of the responsible disclosure process, and it worked in a practical way with a recent issue from SSAC on internal certificate names. | The feedback so far has been very positive. | We now have a recognized process and those in the community are making use of it.
16. ICANN should continue its outreach efforts to expand Community participation and input into the SSR Framework development process. ICANN also should establish a process for obtaining more systematic input from other ecosystem participants. | Security | Staff: Patrick Jones | ICANN conducts substantial outreach on SSR, and annually conducts engagement to encourage community comment on the SSR Framework. | The recommendation supported the Security team's outreach activities and noted that this work should continue in order to expand community participation in the SSR Framework development. | The underlying issue was to support the continued outreach with the community to encourage review and feedback on the SSR Framework, but that ICANN needed a process for obtaining input from other ecosystem participants. | The desired outcome is similar to the desired outcome for Rec 14. | Security conducts regular briefing with SSAC before the completion of the annual SSR Framework to ensure SSAC members have an opportunity to provide feedback on the draft approach. After publication, Security team conducts targeted outreach to all SO & ACs, stakeholder groups. Security also reached broadly to other groups in Civil Society/freedom of expression community; law enforcement; academic community, standards organizations and regional organizations, to encourage review and feedback. | We think this is being implemented with the FY 14 SSR Framework, however, as with our comments on Rec 14, this is an on-going responsibility for the Security team, not work that can ever be completely checked off as "done". | We think this is being met with FY 14 Framework outreach and engagement, but this is work that is never completely "done". | No unforeseen problems. | This effort has helped identify new groups to engage on outreach, and helped refine the description of ICANN's SSR functions. | Outside of ICANN, we think the explanation of ICANN's SSR functions and role has helped increase the awareness of ICANN's role and remit and involvement in the support of DNS capability building. We think this work provides ICANN (and the community) with a key service and substantial goodwill. | The feedback so far has been very positive. | We think our messaging and outreach on the SSR Framework has improved. The SSR Review Team noted this improvement from FY 12's Framework to FY 13, and the comments of far on the FY 14 also reflect this. | Outreach is more than one-way, so we need feedback from stakeholder groups that the interaction to date is in line with community expectations. While private or off the record feedback has been very positive, much of this feedback has not yet translated in significant public comments on the annual SSR Frameworks. This is somewhat reflective of community priorities on competing public comment periods, but we do know the community places a high value on security (from the regional strategies and from discussion of security in other contexts such as at WTPF, WSIS Forum, etc). | No changes, but a better description of ICANN's Security functions was published in March with the FY 14 SSR Framework. We are now using the graphics produced with XPLANE in materials and training. This information is also being used with the next Strategic Plan.
17. ICANN should establish a more structured internal process for showing how activities and initiatives relate to specific strategic goals, objectives and priorities in the SSR Framework. It also should establish metrics and milestones for implementation. | Security | Staff: Patrick Jones | ICANN has an internal process for mapping activities and initiatives for Strategic goals, objectives and priorities in the SSR Framework. | Our understanding was the process used for showing how activities relate to strategic goals and objectives was not as clear as it could be when the SSR RT began its work. | The Review Team thought it important to ensure ICANN had a process for connecting activities and initiatives to specific goals. This has been done with the Management Mapping effort, introduction of At Task system and alignment of SSR Framework | The desired outcome was for the establishment of an internal process for ensuring activities and initiatives mapped to strategic goals. | Security is contributing to the next Strategic Plan development and also will be using At Task & the Management delivery system to align strategic goals to specific initiatives and activities. | This is being addressed with the development of the next Strategic Plan, and the implementation of At Task with FY 14. | This will be implemented with FY 14, following the completion of the Strategic Plan and aligning of initiatives within At Task. | Discussions are continuing with the development of the next Strategic Plan. | We think this effort will help improve the awareness of ICANN's role and remit in Security and how the Strategic goals are aligned with ICANN's SSR functions. | This work is continuing. | See comment on J. | See comment on I. | Completion of the next Strategic Plan. | The implementation of At Task with the FY 14 operating plan and budget process, and more regular publication of reporting to the community on the SSR recommendations is addressing this.
18. ICANN should conduct an annual operational review of its progress in implementing the SSR Framework and include this assessment as a component of the following year’s SSR Framework. | Security | Staff: Patrick Jones | ICANN has published an annual SSR Framework each year since 2009. During the work of the SSR RT, the Security team developed a review of its progress on the activities set forth in the FY 12 Framework, so that the FY 13 Framework included a status report. | We understand the recommendation is for ICANN to review annually its progress in implementing the SSR Framework and add this component (which was not previously part of the annual Framework until the FY 13 version). | This recommendation was to provide more information to show how the previous year's activities had been addressed in a clear and transparent manner for the community. | The desired outcome was to include a status report for the previous year's activities as an additional section in the annual SSR Framework, in order to be able to easily see the progress in completing the activities that had been projected in the previous Fiscal Year's Framework. | In the FY 13 SSR Framework, a status report showing FY 12's activities and results was incorporated, completing this recommendation. In the FY 14 SSR Framework, the status report for FY 13 appears as Appendix B. | This recommendation is 100% complete. | We believe this recommendation was implemented with the FY 13 SSR Framework and refined with the publication of the FY 14 Framework in March 2013. | There were no unforeseen problems with implementation of this recommendation. | We think there will be opportunity to improve on the implementation as At Task continues to be used for project and program tracking with FY 14. | The outcome has been that it is easier for the community to see how ICANN has made progress on the activities and initiatives outlined in the previous year's Framework. | We received positive comments from the community on the FY 13 Framework for incorporating the status report, and the SSR Review Team noted this was also a positive development in its Final Report. | This work has provided an example for other departments on how to track and report progress on initiatives annually. |  | The Security team now includes a status report on the previous year's activities in the next SSR Framework (first done with the FY 13 version). The SSR Review Team noted this was a positive addition.
19. ICANN should establish a process that allows the Community to track the implementation of the SSR Framework. Information should be provided with enough clarity that the Community can track ICANN’s execution of its SSR responsibilities, while not harming ICANN’s ability to operate effectively. The dashboard process being used to track implementation of the ATRT recommendations serves as a good model. | Security | Staff: Patrick Jones | The Security team added a status update on FY 12 activities to the FY 13 SSR Framework, following discussion with the SSR RT during the development of their report. | We understood better explanation of progress on SSR Framework activities is needed for the community. | At the time the SSR RT report was developed, the Review Team thought the Security team could do a better job explaining how activities were being tracked from the previous Framework. | With the FY 13 to Fy 14 Framework, the team has made improvements in reporting progress on prior year activities. This will continue to improve as Security team work becomes tracked in At Task for the community to see. | We added a status update in the Fy 13 Framework and improved it for FY 14. We are also providing more information with the At Task system. | 70%, but needs to be updated to current with the FY 14 activities. | This recommendation is nearly implemented. | None. | More detail will be made available for the community through the At Task system and MyICANN. | The community can better track the Security team's activities and progress. | We do not yet have feedback on this recommendation. The SSR RT did not progress between the FY 12 and FY 13 Frameworks in their report.
20. ICANN should increase the transparency of information about organization and budget related to implementing the SSR Framework and performing SSR-related functions. Information should be provided with enough clarity that the Community can track ICANN’s execution of its SSR responsibilities, while not impeding ICANN’s ability to operate effectively. | Security | Staff: Patrick Jones | ICANN has been providing more information from its FY 12 to FY 13 (and FY 14 SSR Frameworks) related to the organization and budget for ICANN's SSR-related functions. The Review Team noted this information could be improved. | We understand the recommendation to be as written in the Final Report. | The ccNSO and other stakeholders provided comments on the FY 12 SSR Framework that ICANN needed to provide more information and increase transparency of the organization and budget for SSR. The Review Team picked up on this. | The desired outcome was to improve the amount and clarity of information on the organization and budget for implementing the SSR Framework and performing SSR-related functions. | This is being addressed with the implementation of the FY 14 budget and operating plan, and use of At Task for providing more transparency on the budget sections related to SSR. | This is well underway with the development of the FY 14 budget, pending the adoption of the budget and operating plan and updating of related projects and initiatives in At Task. | See comment in F. | Not yet.
21. ICANN should establish a more structured internal process for showing how organization and budget decisions relate to the SSR Framework, including the underlying cost-benefit analysis. | Security | Staff: Patrick Jones | Security is one of the key pillars for ICANN and it's prominently reflected in the Strategic Plan and annual Operating Plan and budget. | We understand the recommendation to be as written in the Final Report. | See comment above on Rec 20. | See comment above. | See comment above. | See comment above. | This is being done with the development of the FY 14 budget and operating plan.
22. ICANN should publish, monitor and update documentation on the organization and budget resources needed to manage SSR issues in conjunction with introduction of new gTLDs. | Security | Staff: Patrick Jones | Organization and budget for SSR issues is provided in the Security team, but also reflected in nTLD program (DNS Stability Panel, other process steps, such as EBERO) | We understand the recommendation to be as written in the Final Report. | See comment above on Rec 20. | See comment above. | This is related to the completion of the FY 14 budget and operating plan process. | See comment on Rec 20. | See comment above. | Not yet.
23. ICANN must provide appropriate resources for SSR-related Working Groups and Advisory Committees, consistent with the demands placed upon them. ICANN also must ensure decisions reached by Working Groups and Advisory Committees are reached in an objective manner that is free from external or internal pressure. | Security; Policy Support | Staff: Patrick Jones; Barbara Roseman; David Olive | Security-related activities with the Supporting Organizations and Advisory Committees are currently done in a number of working groups (for example, the cross-community DNS Security & Stability Analysis Working Group), but these are not currently tracked across all SO & ACs specifically for SSR. This work is also done through SSAC and RSSAC. | The emphasis of this recommendation from the Review Team was to ensure RSSAC (as well as SSAC, but primarily RSSAC) was sufficiently staffed and resourced to meet the demands placed upon it. In addition, the recommendation grew from an analysis of the root scaling work by SSAC and RSSAC, and SSR-related working groups should be able to do their work free from external and internal pressure. | Per the Review Team's discussions, they stated that input had been received that SSAC felt pressure to deliver an answer to a specific problem within a limited timeframe. SSAC and RSSAC should have sufficient resources to provide high-quality work in a reasonable time frame. | We understood the desired outcome to ensure SSR-related working groups are sufficiently resourced and provided with the support to reach decisions free from external or internal pressure. | Our approach has been to divide the recommendation into 23A (conducting an inventory of the existing SSR-related working groups and Advisory Committees); 23B (creating a description or documentation of the budget process for SO/AC input); 23C (describing the standard operating processes to show how SO/AC/working group decisions are reached in an objective manner). | Implementation of this recommendation is still in progress. | This recommendation is not yet fully implemented. | This is still to be implemented. | We think this will help show how the existing SSR-related activity done by Supporting Organizations, Advisory Committees and working groups is conducted and provide a solid level of transparency on the development of SO & AC budgets. | We will have more information on impacts after implementation.
24. ICANN must clearly define the charter, roles and responsibilities of the Chief Security Office Team. | Security | Staff: Patrick Jones | The Security team has maintained a webpage (https://www.icann.org/security) and published an annual Security, Stability and Resiliency Framework, since 2009. | We understood the Review Team developed this recommendation to provide greater clarity on the roles and responsibilities of the ICANN Security team vs other Security-related functions within ICANN and its Supporting Organizations. | We understood the underlying issue to be that information about the structure of the Security team could be improved, this was done during the work of the SSR Review Team and the Review Team noted this during their final report. | The desired outcome was more information for the community on the structure and roles of the Security team. | This was implemented largely with the FY 13 SSR Framework (improved in the FY 14 version), and publication of an updated section of the Security team page on the ICANN website. | We think this recommendation is complete. | We think this recommendation is implemented. | No. | We think our work to develop the FY 13, FY 14 versions of the SSR Framework and explanatory materials with XPLANE have helped refine Security's message and explain ICANN's Security functions. | The outcome so far has been a good recognition of the role and remit for ICANN in Security and a better understanding of the structure of the Security team. | The feedback so far has been very positive.
25. ICANN should put in place mechanisms for identifying both near and longer-term risks and strategic factors in its Risk Management Framework. This process should be informed by insights from research, business partnerships, ICANN Supporting Organizations and other sources. ICANN should publish information about risks, recognizing the sensitive nature of some of these factors. | Board Risk Committee | Bill Graham, Mike Silber, Suzanne Woolf, Ram Mohan
| Security; Policy Support | Staff: Patrick Jones; Barbara Roseman | ICANN has had a Board Risk Committee for several years. ICANN staff has conducted enterprise risk assessments over the past few years. | The SSR RT Final Report describes the need for a more structured process for identifying near and longer-term risks, and that ICANN should publish information about risks, with the understanding that this information may be sensitive. | The underlying issue was the need to have a comprehensive Risk Management Framework that could be used to identify near and long-term risks for the organization. | See comment in C. | ICANN retained Westlake Governance to develop a DNS Risk Management Framework. | A draft framework was presented in Beijing, will be published for comment for Durban. | See comment in F. | No. |  | This is still being implemented. | The public comments from the open sessions with the DNS RMF have been positive and in support of a stronger risk management function at ICANN. | This is still being implemented.
26. ICANN should prioritize the timely completion of a Risk-Management Framework. This work should follow high standards of participation and transparency. | Security | Staff: Patrick Jones | The Board-level DNS Risk Management Framework Working Group has had open community sessions in Costa Rica, Prague, Toronto and Beijing. A draft framework approach was presented by consultants Westlake Governance in Beijing, and is on track for a final framework report by the Durban meeting. | We understand the recommendation to be as written in the Final Report. | The SSR RT placed an emphasis on conducting a risk management framework as early as possible. | The desired outcome is for the completion of a risk management framework, developed through community participation and transparency. | This is being prioritized, by the Board-level DNS Risk Management Framework Working Group, participation has been open in public sessions at ICANN Costa Rica, Prague, Toronto, Beijing. A public comment opportunity will be available after the draft is completed. | See comment in E. | This is not yet fully implemented. See comment in F. | Not yet. |  | The feedback from the community from the public sessions on the Risk Management Framework have been positive. | See comment on J. | This is being addressed with Westlake Governance, we think the work to date has been open and inclusive, participation has been welcomed.
27. ICANN’s Risk-Management Framework should be comprehensive within the scope of its SSR remit and limited missions. | Security | Staff: Patrick Jones | Risk Management has been a component of ICANN's Security practices. The team provides staff support to the Board Risk Committee. | We understand the recommendation to be as written in the Final Report. | This is related to Rec 25. | Same comment in C for Rec 25. | A DNS Risk Management Framework will be published for community comment for ICANN Durban. | This is well underway, a draft Framework was published for community to see for the ICANN Beijing meeting. A draft will be presented for Community comment for the ICANN Durban meeting. | This work is underway and being performed by Westlake Governance. | No. |  | This is still being addressed with our consultants from Westlake Governance. | The feedback on Westlake's approach has been positive. | This is still being implemented.
28. ICANN should continue to actively engage in threat detection and mitigation, and participate in efforts to distribute threat and incident information. | Security | Staff: Patrick Jones | The Security team participates in trusted community initiatives on DNS threats, within SSAC, DNS-OARC, and other groups. | We understood the recommendation to be supportive of the existing engagement by ICANN in threat detection and mitigation efforts. | This recommendation encourages the Security team to continue to participate in threat detection and mitigation and efforts to distribute this information through appropriate channels. | The desired outcome encourages continued participation by ICANN in appropriate threat detection and mitigation efforts with the community. | This has been largely implemented. ATRT2 should keep in mind this recommendation is an on-going area of involvement, not an area that can be checked off as "done". | We think this recommendation is essentially complete. | Yes, we think this recommendation is implemented. | No. |  | ICANN participates in trusted security circles and this will continue.

## Reference Materials
Reference Materials
Document | Link
Final Report of the Security, Stability and Resiliency of the DNS Review Team | http://www.icann.org/en/about/aoc-review/ssr/final-report-20jun12-en.pdf
Revised Draft Statement of ICANN's Role and Remit in SSR | http://toronto45.icann.org/meetings/toronto2012/presentation-draft-ssr-role-remit-04oct12-en.pdf
Security Team | https://www.icann.org/security