GNSO PDP Timelines – Updated 25 June 2013

|  | IRTP Denials | IRTP Part A | Fast Flux | Domain Tasting | IRTP Part B | PEDNR | IRTP Part C | UDRP Lock | Thick Whois | Median |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Request for an Issues Report | 0 (20 Sep07) | 0 (8 May08) | 0 (6 March08) | 0 (9 May07) | 0 (16 April09) | 0 (20 Nov08) | 0 (22 Jun11) | 0 (3 Feb11) | 0 (22 Sept11) |  |
| Preliminary Issue Report |  |  |  |  |  |  | 34 (25 Jul11) | 114 (27 May11) | 61 (21 Nov11) | 61 |
| Submission of Final Issue Report | 29 (19 Oct07) | 15 (23 May08) | 19 (25 March08) | 36 (14 June07) | 29 (15 May09) | 15 (5 Dec08) | 69 (29 Aug11) | 243 (3 Oct11) | 134 (2 Feb12) | 29 |
| Initiation of PDP | 61 (20 Nov07) | 48 (25 June08) | 63 (8 May08) | 175 (31 Oct07) | 69 (24 June09) | 168 (7 May09) | 93 (22 Sept11) | 316 (15 Dec11) | 175 (14 Mar12) | 93 |
| Approval of WG Charter |  | 70 (17 July08) | 84 (29 May08) |  | 98 (23 July09) | 216 (24 June09) | 93 (22 Sept11) | 406 (14 Mar12) | 383 (8 Oct12) | 98 |
| Publication Initial Report | 179 (17 March08) | 245 (8 Jan09) | 326 (26 Jan09) | 243 (7 Jan08) | 408 (29 May10) | 557 (31 May10) | 346 (1 Jun12) | 772 (15 Mar13) | 639 (21 Jun12) | 346 |
| Publication Final Report | 202 (9 April08) | 315 (19 March09) | 518 (6 August09) | 332 (4 April08) | 775 (30 May 2011) | 937 (14 June 2011) | 476 (9 Oct 12) | 884 (5 July13) |  | 497 |
| Council Vote | 392 (16 Oct08) | 343 (16 April09) | 546 (3 Sept09) | 345 (17 April08) | 798 (22 June 2011) | 1005 (21 July 2011) | 484 (17 Oct 12) |  |  | 484 |
| Board Vote | 415 (7 Nov08) | No board vote | No board vote | 415 (26 June08) | 862 (25 Aug 2011) | 1073 (28 Oct 2011) | 548 (20 Dec 12) |  |  | 548 |
| Implementation Effective Date | 543 (15 Mar09) | N/A | N/A | 694 (1 Apr09) | 1143 1 June 2012 | 1746 (31 Aug 2013) |  |  |  | 918 |

Glossary

GNSO - Generic Names Supporting Organization

PDP - Policy Development Process

IRTP - Inter-Registrar Transfer Policy

PEDNR - Post-Expiration Domain Name Recovery

WG – Working Group

# Footnotes

Required per the revised GNSO PDP approved in December 2011

Target date

Followed by launch of drafting team on 17 April 2008, which produced its final report on 4 June 2008, whose recommendations where adopted by the GNSO Council in October 2008.

Part of the recommendations were implemented by this date