## ATRT1
ATRT1 Recommendations | Implementation Assignments |  | F. Percentage/portion that is complete? | G. Does s/he believe ICANN fully implemented the recommendation? If not, why not? If not, what parts were not implemented, and why not? | I. Did s/he identify additional opportunities for improvement by virtue of the implementation of these recommendations? | J. What has been the outcome and effect both inside ICANN and external to ICANN as a result of the implementation of the recommendation? | L. How does s/he feel that ICANN has improved as a result of the implementation of the recommendation? | N. In view of ATRT1 what changes in workflows and/or organization where undertaken? | ATRT2 Recommendation?
Governmental Advisory Committee Operations, Engagement, Interaction with Board - 9.1 (b)
9. Clarify what constitutes GAC public policy “advice” under the Bylaws. | Board/Board-GAC WG | Heather Dryden; Manal Ismail; Bill Graham | Complete. Please see 2012 Implementation Summary re: ATRT Rec. No. 9 (www.icann.org/en/news/in-focus/accountability/atrt-project-list-workplans-29jan13-en.pdf). | Yes. Please see 2012 ATRT Implementation Summary (www.icann.org/en/news/in-focus/accountability/atrt-project-list-workplans-29jan13-en.pdf) and the 2012 Annual Report on ATRT Implementation (http://www.icann.org/en/news/in-focus/accountability/atrt-implementation-report-29jan13-en.pdf) | No, not for this specific recommendation. | Significantly greater understanding among Board, staff and community as to what is and is not GAC advice, and embedded process for Board to seek clarification of the meaning of GAC advice (per Rec. 10). | As a result of implementation of recommendations 9 and 10, it seems that among the Board, GAC, Staff and community there is a greater understanding of what is and isn't GAC advice which has led to improvements in the effectiveness and quality of work of the Board, the GAC and the multistakeholder community. Additional information is available in the 2012 Annual Report on ATRT Implementation (http://www.icann.org/en/news/in-focus/accountability/atrt-implementation-report-29jan13-en.pdf) | None directly but indirectly was condition precedent for implementation of recs. 10, 11. | No
| Staff: Global Stakeholder Engagement; GAC Liaison; Board Support (Legal) | Jamie Hedlund; Jeannie Ellers; Samantha Eisner
10. Create formal, documented process for requesting, tracking GAC advice.* | Board/Board-GAC WG | Heather Dryden; Manal Ismail; Bill Graham | Complete (not including portion deferred to 12&13). Please see 2012 Implementation Summary re: ATRT Rec. No. 10 (www.icann.org/en/news/in-focus/accountability/atrt-project-list-workplans-29jan13-en.pdf). | Yes, although BGRI-WG, Board and staff recognize that further iterations of the register and improvements in online performance will be made. Please see 2012 ATRT Implementation Summary (www.icann.org/en/news/in-focus/accountability/atrt-project-list-workplans-29jan13-en.pdf) and the 2012 Annual Report on ATRT Implementation (http://www.icann.org/en/news/in-focus/accountability/atrt-implementation-report-29jan13-en.pdf) | Yes, as noted, further improvements will be made to the online register. | Greater visibility into what advice or information requests the GAC has issued to the Board and whether and to what extent ICANN has addressed these; same true with respect to Board requests of the GAC. | Greater transparency and accountability with respect to handling of GAC Advice/requests for information and Board requests. Additional information is available in the 2012 Annual Report on ATRT Implementation (http://www.icann.org/en/news/in-focus/accountability/atrt-implementation-report-29jan13-en.pdf) | Creation and ongoing operation of GAC Advice Register; enabling tool for implementation of Rec. 11; enhances efficient and effective communication between GAC and Board on progress in addressing GAC advice. | Possibly: why not extent this type of register to advice from all Advisory Committees?
| Staff: Global Stakeholder Engagement; GAC Liaison; Board Support (Legal) | Jamie Hedlund; Jeannie Ellers; Samantha Eisner
11. Ensure timely provision & consideration of GAC advice and mechanisms for Board follow-up.* | Board/Board-GAC WG | Heather Dryden; Manal Ismail; Bill Graham | Although identified tasks have been implemented, work continues as the GAC addresses ongoing improvements and evolving goals in this area. The timeline in how the Board receives advice and responds to advice is fully operationalized. The consultation process has been completely designed, though Bylaws changes are likely necessary to "hardcode" new recommended voting thresholds regarding the Board's rejection of GAC advice. However, GAC suggested that ICANN Bylaws amendment be addressed holistically with consideration of potential impact to other parts of the Bylaws and hence proposed postponing the process until after new gTLDs discussions. In the interim, the Board suggested to have all agreed changes reflected in the Board procedures manual, which does not have the same status as a formal resolution or the bylaws, but serves as a guide to the way the Board does things. Hence the consultation mechanism can/will be implemented prior to formal Bylaws modifications. Please see 2012 Implementation Summary re: ATRT Rec. No. 11 (www.icann.org/en/news/in-focus/accountability/atrt-project-list-workplans-29jan13-en.pdf). | ICANN and the GAC have addressed all portions of Recommendation 11 through the implementation work. Please see 2012 ATRT Implementation Summary (www.icann.org/en/news/in-focus/accountability/atrt-project-list-workplans-29jan13-en.pdf) and the 2012 Annual Report on ATRT Implementation (http://www.icann.org/en/news/in-focus/accountability/atrt-implementation-report-29jan13-en.pdf) | ICANN has not identified any additional material opportunities during implementation of this recommendation. | The implementation provides a clearer, more predictable path for the Board to receive and clarify the advice it receives from the GAC. This clarification may result in reduction of situations where the Board determines it is necessary to act in contravention to GAC advice. In addition, the development of the formal Consultation procedure will bring more predictability in situations where the Board determines its needs to act in contravention to GAC advice. While the new process has not yet been used, the consultation process can be expected to take a maximum duration of 6 months. While this sets a default maximum duration, it may also, in some cases, which could introduce delay into decisions that will impact third parties. | See J. Additional information is available in the 2012 Annual Report on ATRT Implementation (http://www.icann.org/en/news/in-focus/accountability/atrt-implementation-report-29jan13-en.pdf) | The procedures set out for the timing in the receipt and response to GAC advice are becoming standard operating procedures. The consultation process, upon initiation, will also become standard operating procedure. | See concerns shown in response to this question
| Staff: Global Stakeholder Engagement; GAC Liaison; Board Support (Legal) | Jamie Hedlund; Jeannie Ellers; Samantha Eisner
12. & 13. Board, acting through the JWG, should develop & implement a process to engage the GAC earlier in the policy development process; ensure GAC is fully informed of policy agenda & policy staff is aware of GAC concerns.* | Board/Board-GAC WG | Heather Dryden; Manal Ismail; Bill Graham | 70% complete (as discussion with GNSO on GAC early engagement is still ongoing). | With respect to the original ATRT Recommendations, they were all fully implemented but please also see previous entry (F). Please see 2012 ATRT Implementation Summary (www.icann.org/en/news/in-focus/accountability/atrt-project-list-workplans-29jan13-en.pdf) and the 2012 Annual Report on ATRT Implementation (http://www.icann.org/en/news/in-focus/accountability/atrt-implementation-report-29jan13-en.pdf) | Possible additional measures for future consideration: #12 - • GAC Chair designates small GAC WG • Reviews Monthly Reports for possible public policy interest • Post any comments on website • Submit comments to relevant SO • Specially-tailored Webinar prior to Public Meetings • Specifically designed for the GAC to focus on emerging or significant policy issues under development for discussion at public meetings that may raise public policy issues or concerns • Utilize Monthly Report to engage Supporting Organizations • Identify issues that may have public policy interest • Engage with relevant SOs prior to and during ICANN Public Meeting #13 - Assisting the GAC to organize/formalize regular consultation at ICANN meetings with the GNSO, ccNSO, ASO, and Advisory Committees on policy issues and matters of concern to the GAC. | Mechanisms to ensure GAC awareness of ICANN policy issues/agenda at an early stage in the policy development process, as well as ICANN Board/Staff awareness of GAC concerns are now in place. There is also a better awareness of the need for communication between the GAC and SO-AC groups on policy matters and an exchange of views. | Generally speaking, the implementation of these recommendations has established a better understanding of ICANN policy issues and policy development process by the GAC, as well as opportunities for closer collaboration and coordination between the ICANN Board, Staff and the GAC. These measures have resulted in earlier engagement by the GAC in the policy development process, and has helped to ensure that GAC concerns are taken into account in a more effective manner - i.e, while policy is still being developed (rather than after the policy has been developed and awaiting final consideration by the Board). Additional information is available in the 2012 Annual Report on ATRT Implementation (http://www.icann.org/en/news/in-focus/accountability/atrt-implementation-report-29jan13-en.pdf) | #12 - Policy Director specifically assigned to coordinate pilot project which includes distribution of monthly one-page reports on current policy development issues to GAC membership, and process to facilitate GAC's early engagement in policy development process. #13 – Face to Face Board/GAC meetings and discussion of policy issues at each ICANN meeting are now part of SOP. There is increased staff coordination support for GAC processes and involvement with ICANN. | Unknown? Defer to GAC members
| Staff: Office of the CEO; Policy; Global Stakeholder Engagement; GAC Liaison | David Olive; Jamie Hedlund; Jeannie Ellers
14. Increase support & commitment of governments to the GAC process.* | Board/Board-GAC WG | Heather Dryden; Manal Ismail; Bill Graham | Complete. Please see 2012 Implementation Summary re: ATRT Rec. No. 14 (www.icann.org/en/news/in-focus/accountability/atrt-project-list-workplans-29jan13-en.pdf). | Yes. Yet experience with the HLM needs to be studied to guide future decisions whether further such meetings should be held, how frequent and what are the lessons learnt. Please see 2012 ATRT Implementation Summary (www.icann.org/en/news/in-focus/accountability/atrt-project-list-workplans-29jan13-en.pdf) and the 2012 Annual Report on ATRT Implementation (http://www.icann.org/en/news/in-focus/accountability/atrt-implementation-report-29jan13-en.pdf) | More could be done to provide new GAC members with sufficient informational resources. MyICANN was, in part, intended to contribute to this objective and the planned Online Education Platform (working title) also is expected to help address GAC member's information needs. | GAC appears to have benefitted from increased travel, language, staff, translated documents, real-time interpretation and informational resources; successful HLM in Toronto. | ICANN gains credibility with increased governmental engagement, particularly from the developing world. Additional information is available in the 2012 Annual Report on ATRT Implementation (http://www.icann.org/en/news/in-focus/accountability/atrt-implementation-report-29jan13-en.pdf) |  | Defer to GAC members (and survey to be studied) since uch criticism of the GAC is still heard.
| Staff: Office of the CEO; Global Stakeholder Engagement; GAC Liaison | Tarek Kamel; Jamie Hedlund; Jeannie Ellers

## Reference Materials
Reference Materials
Document | Link
Accountability & Transparency Review Team 1 (ATRT1) Final Report and Recommendations, January 2010 | https://www.icann.org/en/about/aoc-review/atrt/final-recommendations-31dec10-en.pdf
ATRT Recommendations - Proposed Implementation Plans; Ocotber 2011 | http://www.icann.org/en/news/in-focus/accountability/atrt-recommendations-implementation-plans-08feb12-en.pdf
ATRT Implementation Summary Report 2012 | www.icann.org/en/news/in-focus/accountability/atrt-project-list-workplans-29jan13-en.pdf
2012 Annual Report - Implementation of the Accountability & Transparency Review Team Report; January 2013 | http://www.icann.org/en/news/in-focus/accountability/atrt-implementation-report-29jan13-en.pdf
NomCom web site | http://nomcom.icann.org/
ICANN 2012 NOMCOM FINAL REPORT | http://nomcom.icann.org/nomcom-final-report-08oct12-en.pdf
Adopted Board Resolution - Chair Remuneration, August 2013 | http://www.icann.org/en/groups/board/documents/resolutions-05aug10-en.htm#5
Community Input Advice Framework, September 2012 | www.icann.org/en/news/in-focus/accountability/input-advice-function-24sep12-en.pdf
Policy vs. Implementation Public Comment Period, January 2013 | http://www.icann.org/en/news/public-comment/policy-implementation-31jan13-en.htm
ICANN Accountability & Transparency | http://www.icann.org/en/news/in-focus/accountability
FY12 Operating Plan and Budget Fiscal Year Ending 30 June 2012, adopted 24 June 2011 | http://www.icann.org/en/financials/adopted-opplan-budget-fy12-09sep11-en.pdf
GAC High Level Meeting, Toronto - October 2013 | http://toronto45.icann.org/gac-hlm
JWG Final Report & Public Comment Forum, July 2011 | http://www.icann.org/en/news/announcements/announcement-07jul11-en.htm
Revised GAC Operating Principles | https://gacweb.icann.org/display/gacweb/Core+Principles
Publication of what constitutes GAC advice, July 2011 | http://www.icann.org/en/news/announcements/announcement-07jul11-en.htm