## Inventory
DRAFT | [6 empty] | ATRT 2 ¦ Staff/Board
# | Source of item (ATRT 1 or 2) | Prior RT Recommendation Reference | ATRT 2 Work Stream | Previous RT Recommendation/Summary of New Issue | ATRT 2 Member Assigned to complete analysis and documentation | Proposed Observation or Recommendation for Discussion | Action Items ¦ Responsibility ¦ Schedule | Additional Information
1 | ATRT 1 | 1 a-d | WS 1 (9.1 a) | Mechanisms for identifying collective Board skillset; benchmarking Board/BGC skillsets; tailoring & consulting on skills; reviewing for each NomCom; publishing outcomes & requirements with NomCom’s notice. | Avri Doria; Brian Cute | DRAFT Observation 1 (a) - Document the methodology used to identify and choose “similar corporate and other governance structures”. 1 (b) - Document benchmarks used. 1 (c) - Improve NomCom outreach/PR. 1 (d) - Expand the skills survey and benchmarking to include NomCom selections in GNSO, ccNSO, and ALAC. | (i) Discuss proposed observation/recommendation with implementers ¦ Amy Stathos, Diane Schroeder [1 (a), (b)], Joette Youkhanna [1 (c)], Amy Stathos [1 (d)] ¦ Schedule TBD (ii) Research reference to recommendations not being implemented ¦ Lise Fuhr ¦ 30 Aug; see staff response (iii) How was benchmarking done and was it published? Will it be published? ¦ Amy Stathos, Diane Schroeder ¦ Summary to be provided by Amy Stathos - done on 16 Sept
2 | ATRT 1 | 2 | WS 1 (9.1 a) | Regularly reinforce/review training & skills building. | Avri Doria; Brian Cute | DRAFT Observation 2 (a) - Metrics should be defined by which effectiveness of board training programs can be measured. 2 (b) - Board training materials should be made public. | (a) Discuss proposed observation/recommendation with implementers ¦ Avri Doria, Brian Cute, Amy Stathos/staff (Dianne or Karine) ¦ Schedule TBD (b) What is the expected action plan to get this recommendation institutionalized? ¦ Amy Stathos ¦ Summary information to be provided by Larisa Gurnick - done on 16 Sept
3 | ATRT 1 | 3 | WS 1 (9.1 a) | Increase transparency of NomCom’s deliberations & decision-making process. ASAP but starting no later than next NomCom. | Avri Doria; Brian Cute | DRAFT Recommendation Translate NomCom materials to improve international understanding of NomCom processes and outcomes. | (a) Consult with staff and NomCom chairs on potential benefits, feasibility and cost ¦ Avri Doria, Brian Cute, Joette Youkhanna, NomCom Chairs, Christina Rodriguez, Nora Abusitta ¦Schedule TBD See staff response
4 | ATRT 1 | 4 | WS 1 (9.1 a) | Continue to enhance Board performance & work practices. | Avri Doria; Brian Cute | DRAFT Recommendation Metrics should be established to measure Board performance and gauge changes in work practices. | (a) How are these improvements communicated to the community? ¦ Amy Stathos ¦ Summary information to be provided by Larisa Gurnick - done on 16 Sept | See highlights of Implementation - http://www.icann.org/en/news/in-focus/accountability
5 | ATRT 1 | 5 | WS 1 (9.1 a) | Implement compensation scheme for voting Board Directors. | Avri Doria; Brian Cute | None | None
6 | ATRT 1 | 6 | WS 1 (9.1 a) | Clarify distinction between PDP & executive function issues. | Avri Doria; Brian Cute | DRAFT Recommendation To be developed after input from staff. Clear criteria should be established distinguishing between policy and implementation. | (a) Discuss proposed observation/recommendation with implementers and get substantive input from staff ¦ ATRT 2, Amy Stathos, David Olive ¦Schedule TBD (b) Given the ongoing debate about policy vs. implementation, when will this recommendation be ultimately implementable? What is the current status of the discussion? Next steps? ¦ Amy Stathos or Sam Eisner, David Olive, Marika Konings See staff response
7 | ATRT 1 | 7.1 | WS 1 (9.1 a) | Promptly publish all appropriate Board materials related to decision-making processes. | Avri Doria; Brian Cute | TBD | (a) Discuss proposed observation/recommendation with implementers ¦ Avri Doria, Brian Cute, Sam Eisner ¦Schedule TBD
8 | ATRT 1 | 7.2 | WS 1 (9.1 a) | Publish rationale for Board decisions and for accepting or rejecting public & community input. | Avri Doria; Brian Cute | DRAFT Recommendation Decisions based on input received from SOs and ACs to the board prior to the implementation of ATRT1 recommendation 7.2 should be reviewed and in those cases where questions exist as to the status of implementation of the recommendation, rationales should be provided. | (a) Clarify proposed recommendation and discuss with implementers ¦ Avri Doria, Brian Cute, Amy Stathos (b) Complete analysis¦ Larry Strickling ¦ Done (c) discuss findings with staff for clarification/additional information ¦ Avri Doria, Brian Cute, Amy Stathos ¦ tbd | ATRT 2 Analysis - https://community.icann.org/download/attachments/41899319/ICANN+Board+Resolutions+Review.pdf?version=1&modificationDate=1377782071000. Staff would welcome guidance from ATRT 2 on how to develop criteria for what constitues useful rationale and how ICANN can make the process of providing rationale more useful to the community.
9 | ATRT 1 | 8 | WS 1 (9.1 a) | Publish redaction conditions. | Avri Doria; Brian Cute | None | (a) Provide examples of excessive redactions to Sam Eisner ¦ Brian Cute ¦ tbd
10 | ATRT 1 | 19 | WS 1 (9.1 a) | Publish translated Board material within 21 days | Avri Doria; Brian Cute ( Rec 19); Fiona Asonga (new Rec on Multilinguism) | DRAFT Observation; Link to New Recommendation on Multilinguism An assessment of whether this is the appropriate material for translations and to what extent these translations are accessed would be useful in guiding potential, future improvements.
11 | ATRT 2 | 19 | WS 4 | Multilingual quality and timeliness | Fiona Asonga; Lise Fuhr | DRAFT Observation or Recommendation ICANN needs to make every effort to improve on quality of translations in line with local language used in the specific regions. By ensuring all ICANN information is correctly translated so that it communicates the correct message to the various language users. | (a) Discuss with staff cost/benefit analysis, prioritization and implementability ¦ Fiona Asonga, Christina Rodriguez, Nora Abusitta ¦ tbd
12 | ATRT 1 | 20 | WS 1 (9.1 a) | Ensure/certify that inputs in policymaking processes are considered by the Board | Avri Doria; Brian Cute | None
13 | ATRT 1 | 23 | WS 1 (9.1 a) | Get input from committee of independent experts on restructuring review mechanisms | Avri Doria; Carlos Gutierrez | TBD | (a) Consider feedback from community (Becky Burr indicated that formal comment will be submitted to ATRT 2) ¦ Avri Doria, Carlos Gutierrez (b) Discuss proposed observation/recommendation with implementers ¦ Avri Doria, Carlos Gutierrez, Amy Stathos (c) Amy Stathos provided response on 16 Sept
14 | ATRT 1 | 25 | WS 1 (9.1 a) | Clarify standard for Reconsideration requests | Carlos Gutierrez | TBD - see linked draft template | Amy Stathos provided response on 16 Sept | https://community.icann.org/download/attachments/41899319/Template+on+Reconsideration+-+Carlos+Raul+Gutierez.pdf?version=1&modificationDate=1376418042000
15 | ATRT 1 | 24 | WS 1 (9.1 a) | Assess Ombudsman relationship and confirm framework is consistent with international standards | Avri Doria; Carlos Gutierrez | DRAFT Observation or Recommendation ICANN should review ombudsman bylaw to ensure adherence to international standards in an effort to build confidence amongst stakeholders. ICANN needs to reconsider the role of the Ombudsman office as a symbol of good governance and incorporate the office in transparency processes. ICANN should consider the use of the Ombudsman in internal mediation processes. | (a) Review transcript/recording from Durban Session with Ombudsman ¦ Avri Doria, Carlos Gutierrez (b) Discuss proposed observation/recommendation with implementers ¦ Avri Doria, Carlos Gutierrez, Amy Stathos ¦ tbd ( c) consult with Board, Ombudsman and Legal ¦ John Jeffrey, Steve Crocker and Bruce Tonkin (Executive Committee), Chris LaHatte See staff response
16 | ATRT 1 | 26 | WS 1 (9.1 a) | Adopt standard timeline & format for Reconsideration Requests | Avri Doria; Brian Cute | None | None
17 | ATRT 1 | 9 | WS 1 (9.1 b) | Clarify what constitutes GAC public policy “advice” under the Bylaws. | Larry Strickling; Jørgen Abild Andersen | see draft templates | (a) Revise recommendations ¦ Larry Strickling, Jørgen Abild Andersen ¦ 23 Aug (b) Discuss proposed recommendations with implementers ¦ Larry Strickling, Jørgen Abild Andersen, David Olive, Olof Nording, Jeannie Ellers, Sam Eisner | https://community.icann.org/display/ATRT2/Templates+for+Assessment+of+Implementation+and+for+New+Recommendations
18 | ATRT 1 | 10 | WS 1 (9.1 b) | Create formal, documented process for requesting, tracking GAC advice. | same as Rec 9 | Same as Rec 9 | Same as Rec 9
19 | ATRT 1 | 11 | WS 1 (9.1 b) | Ensure timely provision & consideration of GAC advice and mechanisms for Board follow-up | same as Rec 9 | Same as Rec 9 | Same as Rec 9
20 | ATRT 1 | 12; 13 | WS 1 (9.1 b) | Board, acting through the JWG, should develop & implement a process to engage the GAC earlier in the policy development process; ensure GAC is fully informed of policy agenda & policy staff is aware of GAC concerns. | same as Rec 9 | Same as Rec 9 | Same as Rec 9
21 | ATRT 1 | 14 | WS 1 (9.1 b) | Increase support & commitment of governments to the GAC process | same as Rec 9 | Same as Rec 9 | Same as Rec 9
22 | ATRT 1 | 15 | WS 1 (9.1 c) | Implement stratified, prioritized public Notice & Comment processes. | Brian Cute | see draft templates DRFT Recommendation Articulate overarching objectives. Recommend loosening up process and let staff explore different tools and strategies. Remind the community to use the forecast that ICANN is now preparing regularly. Make sure that blackout periods are imbedded into ICANN DNA and communicate to the community. | (a) Clarify recommendation ¦ Brian Cute ¦ tbd (b) Discuss proposed recommendation with implementers ¦ Brian Cute, Sally Costerton, David Olive, Chris Gift¦ presentation made to ATRT 2 on 10 Sept
23 | ATRT 1 | 16; 17 | WS 1 (9.1 c) | Provide “Comment” cycle & a “Reply Comment” comment cycles; review and adjust fixed timelines for Notice & Comment | Brian Cute | Same as Rec 15 | (a) Verify that blackout periods around ICANN meetings are explicitly enforced ¦David Olive - see staff response
24 | ATRT 1 | 18 | WS 1 (9.1 c) | Ensure multilingual access in PDP to maximum extent feasible | Brian Cute (Rec 18); Fiona Asonga (New Rec re: Multilingual Quality and Timeliness) | TBD | (a) Draft recommendation ¦ Fiona Asonga¦ tbd (b) Discuss proposed recommendation with implementers ¦ Fiona Asonga, Christina Rodriguez, Nora Abusitta, David Olive, Marika Konings tbd
25 | ATRT 1 | 21 | WS 1 (9.1 c) | Create annual public comment forecast | Lise Fuhr | None
26 | ATRT 1 | 22 | WS 1 (9.1 c) | Ensure senior staffing arrangements are appropriately multilingual | Lise Fuhr | TBD | (a) Provide metric of multilingual senior staff at Dec 2010 as compared to current ¦ Steve Antonoff ¦ Done - see Additional Information | • In December 2010, ICANN had 38 individuals in Senior and Executive Management roles, of which 28 were multi-lingual (73.4%). • Currently, in August 2013, there are 51 individuals in Senior and Executive Management roles, of which 39 are multi-lingual (76.5%). • Overall, ICANN staff speak approximately 45 languages.
27 | ATRT 1 | 27 | WS 1 (9.1 d) | Evaluate and report on progress on recommendations and accountability & transparency commitments in the AoC. | Brian Cute; Avri Doria | Recommendation Implement benchmarks and metrics | (a) Get information on how the Board is monitoring, how they've been briefed, and how they are preparing for the next review ¦ All information is public. See information posted on the Web page Larisa Gurnick to supply overview (b) Discuss Benchmarks/Metrics project with external consultant and provide feedback ¦ ATRT 2, Larisa Gurnick ¦ 19 Sept - Done
28 | ATRT 2 |  | WS 1 (9.1 e) | Effectiveness of the GNSO PDP | Avri Doria; Alan Greenberg | PDP - pending work of ICC - see action items Recommendation 29. (A) ICANN including the active participation of the GNSO must develop options for carrying out PDPs with the support of professional negotiators, facilitators and/or arbitrators as well as guidelines for when such options may be invoked. (B) ICANN must provide adequate funding for face-to-face meetings to augment e-mail, wiki and teleconferences for GNSO PDPs. | (a) ICC to perform its work ¦13 Oct (b) Facilitate and support ICC's work ¦ Marika Konings, Larisa Gurnick
29 | ATRT 2 |  | WS 1 (9.1 e) | Effectiveness of cross-community deliberations | Avri Doria; Alan Greenberg | Draft Recommendation Cross-Community Review - While efforts have been ongoing in the enhancement of cross-community deliberations, there are still issues that need to be improved in this area. | (a) Discuss proposed recommendation with implementers, analyze Community feedback ¦ Avri Doria, Alan Greenberg, David Olive¦ Done (b) Refine recommendation ¦ Avri Doria, Alan Greenberg Note: may relate to policy vs. implementation issue
30 | ATRT 2 |  | WS 4 | Make improvements to the Review processes: Appointment of Review Teams | Fiona Asonga | Draft Recommendation (1) It should be ensured that Review Teams are appointed in due course allowing them to run their work the 1 year process that the review is supposed to take place regardless of the time when the team is established. | (a) Discuss the notion of a 3-year cycle with Staff and Ray Plzak as part of a broader discussion on organizational reviews ¦ Brian Cute, Ray Plzak, Larisa Gurnick, Denise Michel (b) Staff Clarification: AoC does not require the reviews be completed within one year. Timely completion impacts the effectiveness of the 3-year cycle. ATRT 2 may wish to address the 3-year cycle mandate See staff response
31 | ATRT 2 |  | WS 4 | Make improvements to the Review processes: Getting the Review Team started with a complete implementation report | Fiona Asonga | DRAFT Recommendation (2) ICANN should prepare a complete implementation report to be ready by Review kick-off. This report should be submitted for public consultation. Benchmarks and metrics must be incorporated into this reporting. | (a) Staff Clarification: Staff prepares regular and frequent implementation reports to the Board and community. Additionally, annual report was provided to the Board and community. See link under "Additional Information"¦ Fiona Asonga to clarify recommendation (b) Consider providing guidance on desired reporting substance and form (i.e. report what has been done, provide supporting documentation and evaluate effectiveness of implementation) See staff response | http://www.icann.org/en/news/in-focus/accountability
32 | ATRT 2 |  | WS 4 | Make improvements to the Review processes: Review Budget Transparency and Accountability | Fiona Asonga | DRAFT Recommendation (3) ICANN should ensure that sufficient resources are allocated for the reviews to fulfill their role, including but not limited to accommodation of requests from the Review Teams to appoint independent experts/consultants if deemed necessary by the teams. ICANN should at the initial stage before a review is initiated account for and publish the budget for the review together with a rationale for the amount allocated. The budget should be established based on i.e. the experiences achieved from the work of the previous teams, including ensuring a continuous assessment and adjustment of the budget according to the needs of the reviews. | (a) Budget and actual information for previous Review Teams - in process | Conversation with Xavier Calvez during ATRT 2 call on 29 Aug
33 | ATRT 2 |  | WS 4 | Make improvements to the Review processes: Incorporation of review teams input into ICANN strategic plan and Institutionalization of progress | Fiona Asonga | DRAFT Recommendations (4) ICANN should ensure that the ongoing work of the AOC reviews, including implementation, is fed into the work of other ICANN strategic activities. (6) ICANN should ensure strict co-ordination of the various review processes so as to have all reviews done before next ATRT reviews with proper linkage of issues within the AOC and consider the function of a technical facilitator whose mandate is to co-ordinate the reviews. | (a) See staff response (b) Clarify Recommendation (6) and its objective. What is meant by "technical facilitator"? What would his/her role be? What would be his/her objective? ¦ Fiona Asonga
34 | ATRT 2 |  | WS 4 | Review actions of the Board and staff in ensuring public interest: Finance Accountability and Transparency | Fiona Asonga | TBD based on action items DRAFT Recommendations 6. In order to improve accountability and transparency and facilitate the work of the various teams ICANN’s Board should each year on a rolling basis establish a Programme of Work and Budget (PWB) reflecting the planned activities and the corresponding expenses. (The PWB may cover a two year period.) The following year a report should be drafted describing the actual implementation of the PWB including activities as well as related expenses. Budgets that are related to the timeline of the strategy – more than one year – preferred for a period of three years. 7. ICANN shall use its finances according to the published operating plan and in cases of deviation make and publish a deviation report as soon as possible. A quarterly report could be made. 8. ICANN shall report to the international internet community done in an accountable and transparent way including doing this in a timely manner in order to give time to comments and adjustments afterwards. The timing of the reporting shall be made in such a manner that it allows the internet community to have an impact on the budget. 9. Independent expert on use of finances | (a) Contact SO/AC Chairs to get specific examples of financial concerns, ¦ Brian Cute. (b) Discuss concerns with Susanna Bennett, Xavier Calvez (c) Hold a briefing with staff regarding ICANN's financial controls and reporting ¦ ATRT 2, Susanna Bennett, Xavier Calvez - done, 29 Aug (d) Follow up from 29 Aug: Org chart - Provided; availability of budget information by project/program on myICANN/AtTask (Carole Cornell) | Organization chart has been provided on Timing of publication of budget data by Program/Project on myICANN.org will be provided once Finance and PMO review the details.
35 | ATRT 2 |  | WS 4 | Review actions of the Board and staff in ensuring public interest: Publication of yearly statistical reports on transparency | Avri Doria | DRAFT Recommendations ICANN should include a yearly transparency report as part of its yearly report. ICANN Transparency report needs to include a section on Employee whistleblowing activity including metric on: i. Reports submitted ii. Reports that resulted in change to ICANN practices This report should be created under the supervision of the ICANN Ombudsman. This requires a change to By-laws on the Ombudsman scope | (a) ATRT 2 to refine recommendation and discuss with Staff. ¦ Avri Doria, Amy Stathos, Sally Costerton, Duncan Burns (b) Annual report is published, strongly tied to ATRT activities. What is being suggested, specifically? (c )Staff Clarification and request to ATRT 2: re: disposition of cases/complaints and legal impliecations/limitations in making this infomration available publically .
36 | ATRT 2 |  | WS 4 | Review actions of the Board and staff in ensuring public interest: Employee Hotline (Whistleblower Policy) | Avri Doria | DRAFT Recommendation There is a need for ICANN to develop a robust whistle blower policy. ICANN must arrange for a profession review of its current whistleblower policy to insure that the ICANN program meets the highest standards as established by tbd ○ This report to be made public ○ Processes for ICANN employee transparency and whistleblowing to be made public | (a) Provide information from external sources on best practices and how ICANN policy compares. ¦ Sam Eisner by 11 Septemer (b) Determine whether the policy can be made public.¦ Amy Stathos, Sam Eisner by 11 September See staff response
37 | ATRT 2 |  | WS 4 | Review actions of the Board and staff in ensuring public interest: Volunteer engagement | Carlos Gutierrez, Avri Doria; Alan Greenberg | DRAFT Recommendation ICANN to establish a sustainable model for relying on volunteers to do functions normally done by professionals | (a) ATRT 2 members to refine recommendation and discuss with staff ¦ Carlos Gutierrez, Avri Doria, Alan Greenberg, Sally Costerton, David Olive See staff response
38 | ATRT 2 |  | WS 2 | Board handling of SSR RT recommendations | David Conrad | Place holder - details to be completed
39 | ATRT 2 | SSR Recs 1-28 | WS 2 | Assessment of implementation of SSR RT recommendations | David Conrad | Place holder - details to be completed |  | https://community.icann.org/download/attachments/41899319/SSR+evaluation.pdf?version=1&modificationDate=1376674960000
40 | ATRT 2 |  | WS 3 | Board handling of WHOIS RT recommendations | Alan Greenberg /Michael Yakushev | Place holder - details to be completed
41 | ATRT 2 | WHOIS Recs 1-16 | WS 3 | Assessment of implementation of WHOIS RT recommendations | Alan Greenberg /Michael Yakushev | Place holder - details to be completed | Update from Staff posted 31 Aug - https://community.icann.org/download/attachments/41880363/Implementation+of+WHOIS+Review+Team+Recommendations+-+Final.doc?version=1&modificationDate=1377989528845 | https://community.icann.org/download/attachments/41899319/WHOIS+Implementation+Status.pdf?version=1&modificationDate=1376675030000
42 | ATRT 2 |  | WS 4 | Outreach | Jørgen Abild Andersen | DRAFT Recommendation (included in the revised GAC recommendations) ICANN should enhance its activities aiming at making ICANN's work relevant for stakeholders in those parts of the world where stakeholders are less active participants in the work of ICANN than stakeholders in other parts in order to ensure that ICANN's decisions are "embraced, supported and accepted by the public and the Internet community" in all parts of the world in accordance with the provisions of the AOC. Before implementing this recommendation ICANN should establish a baseline and concrete goal to be reached as well as a plan to reach the goal. | Sally Costerton, Tarek Kamel

## Assignments
ATRT 2 Member Assigned to complete analysis and documentation | Inventory Item # | Previous RT Recommendation/Summary of New Issue | Will result in a recommendation? Yes/No
Alan, Michael | 40 | Board handling of WHOIS RT recommendations
Alan, Michael | 41 | Assessment of implementation of WHOIS RT recommendations
Avri | 35 | Review actions of the Board and staff in ensuring public interest: Publication of yearly statistical reports on transparency
Avri | 36 | Review actions of the Board and staff in ensuring public interest: Employee Hotline (Whistleblower Policy)
Avri, Alan | 28 | Effectiveness of the GNSO PDP
Avri, Alan | 29 | Effectiveness of cross-community deliberations
Avri, Brian | 1 | Mechanisms for identifying collective Board skillset; benchmarking Board/BGC skillsets; tailoring & consulting on skills; reviewing for each NomCom; publishing outcomes & requirements with NomCom’s notice.
Avri, Brian | 2 | Regularly reinforce/review training & skills building.
Avri, Brian | 3 | Increase transparency of NomCom’s deliberations & decision-making process. ASAP but starting no later than next NomCom.
Avri, Brian | 4 | Continue to enhance Board performance & work practices.
Avri, Brian | 5 | Implement compensation scheme for voting Board Directors.
Avri, Brian | 6 | Clarify distinction between PDP & executive function issues.
Avri, Brian | 7 | Promptly publish all appropriate Board materials related to decision-making processes.
Avri, Brian | 8 | Publish rationale for Board decisions and for accepting or rejecting public & community input.
Avri, Brian | 9 | Publish redaction conditions.
Avri, Brian | 10 | Publish translated Board material within 21 days
Avri, Brian | 12 | Ensure/certify that inputs in policymaking processes are considered by the Board
Avri, Brian | 16 | Adopt standard timeline & format for Reconsideration Requests
Avri, Brian | 27 | Evaluate and report on progress on recommendations and accountability & transparency commitments in the AoC.
Avri, Carlos | 13 | Get input from committee of independent experts on restructuring review mechanisms
Avri, Carlos | 15 | Assess Ombudsman relationship and confirm framework is consistent with international standards
Brian | 22 | Implement stratified, prioritized public Notice & Comment processes.
Brian | 23 | Provide “Comment” cycle & a “Reply Comment” comment cycles; review and adjust fixed timelines for Notice & Comment
Brian, Fiona | 24 | Ensure multilingual access in PDP to maximum extent feasible
Carlos | 14 | Clarify standard for Reconsideration requests
Carlos, Avri, Alan | 37 | Review actions of the Board and staff in ensuring public interest: Volunteer engagement
David | 38 | Board handling of SSR RT recommendations
David | 39 | Assessment of implementation of SSR RT recommendations
Fiona | 30 | Make improvements to the Review processes: Appointment of Review Teams
Fiona | 31 | Make improvements to the Review processes: Getting the Review Team started with a complete implementation report
Fiona | 32 | Make improvements to the Review processes: Review Budget Transparency and Accountability
Fiona | 33 | Make improvements to the Review processes: Incorporation of review teams input into ICANN strategic plan and Institutionalization of progress
Fiona | 34 | Review actions of the Board and staff in ensuring public interest: Finance Accountability and Transparency
Fiona, Lise | 11 | Multilingual quality and timeliness
Jorgen | 42 | (Part of GAC Rec) Outreach
Larry | 17-21 | GAC related recommendations
Lise | 25 | Create annual public comment forecast
Lise | 26 | Ensure senior staffing arrangements are appropriately multilingual