ATRT 2 Timeline for Draft Report

|  |  |
| --- | --- |
| 29 September | Assignments due – completed assessments and draft recommendations |
| 1 October | ATRT 2 Full Team Call to review assessments and draft recommendations |
| 4 October | Draft Report circulated to ATRT 2 for review |
| 6 October | ATRT 2 comments, edits resolved and compiled |
| 7 October | Draft Report provided to staff for translation |
| 11 October | Corrections in redline mode provided to staff for translation |
| 18 October | Publication of Draft Report |