GNSO Council Restructure Implementation Timetable

The following table shows critical milestones, organized by major topic area, that are considered necessary to meet in order to seat the new GNSO Council at the 2009 annual ICANN meeting in Seoul.

The “Date” column entries below, in most instances, reflects a suggested “no later than” completion target.  As with other Staff suggestions intended to jump-start discussions, the target dates reflect Staff’s best estimates of the latest possible completion time for various milestones.  They are not intended to indicate that a particular activity may not be completed earlier.

| Activity | Responsible | Date(s) |
| --- | --- | --- |
| Bylaws Amendments: |  |  |
| Public Comment Period Closed (Bylaws Amendments v2) | Staff | 24 Aug |
| Board Action/Approval | Board | 27 Aug |
| Restructure/Transition Implementation Plan Approved | GNSO Council | 24 Sep |
| (3) NCSG Board Appointments to GNSO Council: |  |  |
| Announcement Posted | Staff | 5 Aug |
| Candidates Statement of Interest (SOI) Deadline | Board/SIC | 31 Aug |
| Board Action on Appointments | Board | 30 Sep |
| Stakeholder Groups: |  |  |
| Executive Committees Formed (*) | SGs | 31 Aug |
| GNSO Councilors Elected/Appointed | SGs/Constituencies | 30 Sep |
| Constituency Reconfirmations: |  |  |
| Staff Suggested Revisions Published | Staff | 14 Aug |
| Revised Charters Submitted to Board | Constituencies | 16 Sep |
| Constituency Charters Reconfirmed | Board | 30 Sep |
| Nominating Committee Appointees to GNSO Council: |  |  |
| GNSO Secretariat Notified of Appointments | NomComm | 30 Sep |
| GNSO Council Operating Procedures: (**) |  |  |
| Operating Procedures (Draft) Recommendations | OSC | 17 Sep |
| GNSO Council Discussion & Review of Recommendations | GNSO Council | 24 Sep |
| 21-Day Public Comment Forum Period after Council Mtg | Staff | 16 Oct |
| New GNSO Council Adopts Procedures | GNSO Council | 28 Oct |
| Board Review | Board | 30 Oct |
| GNSO Council Officer Elections: |  |  |
| Call for Council Chair Nominations | GNSO Secretariat | 07 Oct |
| Nominations (Chair) Closed | GNSO Secretariat | 21 Oct |
| Candidates Interviewed | SGs/Constituencies | Seoul |
| Vice-Chair Elections Held | Voting Houses*** | TBD |
| Chair Election Held (#) | GNSO Council | Seoul |

(*) Exception: NCSG waits until (3) Board appointments are announced.

(**) The GNSO Operations Work Team is currently developing recommendations for these procedures.  As with all the other actions and milestone dates in this table, the Council Operating Procedure approval process set forth here is merely an educated suggestion and subject to further Council or Restructure Drafting Team deliberations.

(***) Procedures for these elections will likely need to be addressed by the members of each voting house.

(#) A procedure is still needed to address potential eventuality that Council Chair is not elected on first ballot.