**Final Report Work Plan – new gTLD Auction Proceeds CCWG – 18 March 2019**

| **Meeting / Target Date** | **Proposed Topics** | **Whom** | **Status / Notes** |
| --- | --- | --- | --- |
| CCWG Conference Call – 27 March 2019 | * Continue review of comments received in relation to charter question #4
* Review comments received in relation to charter question #5
* Review comments received in relation to charter question #6
* Review comments received in relation to charter question #7
 | CCWG |  |
| CCWG Conference Call – 10 April 2019 | * Continue review comments received in relation to charter question #7
* Review comments received in relation to charter question #8
* Review comments received in relation to charter question #9
 | CCWG |  |
| CCWG Conference Call – 24 April 2019 | * Review comments received in relation to charter question #10
* Review comments received in relation to charter question #11
* Review comments received in relation to Initial Report Sections 1-4
 | CCWG |  |
| CCWG Conference Call – 8 May 2019 | * Review comments received in relation to Annex C
* Review comments received in relation to Annex D
* Review general comments received
* Review comments received in relation to proposals for funding allocation
 | CCWG |  |
| CCWG Conference Call – 22 May 2019 | * Review CCWG Agreements and confirm changes to recommendations and report
 | CCWG |  |
| CCWG Conference Call – 5 June 2019 | * Review CCWG Agreements and confirm changes to recommendations and report
 |  |  |
| CCWG Conference Call – 19 June 2019 | * Review updated recommendations and proposed Final Report
 |  |  |
| ICANN65 Marrakesh – 24-27 June 2019 | * Finalize review of updated recommendations and proposed Final Report
 |  |  |