# GNSO Operating Plan

15 March, 2007

Current Policy PDPs

| GNSO PDP | Start date | Last action | Next action | End date |
| --- | --- | --- | --- | --- |
| New gTLDs Project No. 2005 / 01 http://gnso.icann.org/issues/new-gtlds/ Staff lead: Liz Williams | December, 2005 | 23 February, 2007 GNSO Council met 22-23/2/07 to work on draft final report & implementation plan | 16 March, 2007 Posting of draft final report 3/07; Council work & consultations at Lisbon ICANN meeting 28 April, 2007 GNSO Council vote on final report at Puerto Rico ICANN meeting | 28 June, 2007 (Estimated) Council vote on final report at Puerto Rico ICANN meeting |
| GNSO Working Groups | Start date | Last action | Next action | End date |
| GNSO WORKING GROUPS GNSO Working Group on Internationalized Domain Names (IDNs) Project No. 2005 / 03 http://gnso.icann.org/issues/idn-tlds/ Staff lead: Olof Nordling GNSO Working Group on Reserved Names Working Group on Protecting the Rights of Others: | December, 2005 February 2007 March 2007 | 6 March, 2007 IDN Working Group call discussed techno-policy details. 14 March release of draft Reserved Names Report 11 March conference call to confirm progress on work items | 21 March, 2007 Working Group Outcomes Report will be submitted to the GNSO Council. Lisbon meeting F2F planned Lisbon meeting F2F planned | 30 March, 2007: Working Group Outcomes Report to be submitted to the GNSO Council. Work ongoing to 31 March, 2007 (30 day extension likely) Work ongoing through May, 2007 |
| GNSO PDP | Start date | Last action | Next action | End date |
| February 2006 PDP on contractual conditions in gTLDs Project No. 2006 /01 http://gnso.icann.org/issues/gtld-policies/ Staff lead: Liz Williams | December, 2005 | 8-28 March, 2007 Public comments period 24 February, 2007 Completion of Task Force report at LA meetings | 28 March, 2007 Presentation of Final Task Force Report to GNSO Council meeting in Lisbon. Post-Lisbon: Preparation of Board Report, review by Council, submission to ICANN Board | Task Force completion anticipated by 15 April, 2007 (approx.) |
| GNSO PDP | Start date | Last action | Next action | End date |
| PDP on Whois Services Project No. 2005/06 http://gnso.icann.org/issues/whois-privacy/ Staff lead: Maria Farrell | June, 2005 | 13 March, 2007 Submission of ICANN Staff Notes to GNSO Council 9 March, 2007 Presentation of Final Task Force Report to GNSO Council | 28 March, 2007 Discussion of Final Task Force Report by GNSO Council in Lisbon | Task Force end date: 9 March, 2007: Final Task Force Report submitted to the GNSO Council. GNSO Council end date: TBA. |

## Current GNSO Issues

| GNSO Issue | Start date | Last action | Next action | End date |
| --- | --- | --- | --- | --- |
| GNSO Board election Board seat #13 Staff lead: Glen de Saint Gery | 19 February, 2007 Nominations opened | 12 March, 2007 Nominations close | 13 – 30 March, 2007 Interview candidate(s) 2 April, 2007 Email voting starts | 8 May, 2007 Announce GNSO Board seat #13 election results to ICANN Secretary |