PDP Timelines – Updated 2 February 2010

|  | IRTP Denials | IRTP Part A | Fast Flux | Domain Tasting | Average | IRTP Part B | PEDNR |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Request for an Issues Report | 0 (20 Sep 2007) | 0 (8 May 2008) | 0 (6 March 2008) | 0 (9 May 2007) |  | 0 (16 April 2009) | 0 (20 Nov 2008) |
| Submission of Issues Report | 29 (19 Oct2007) | 15 (23 May 2008) | 19 (25 March 2008) | 36 (14 June 2007) | 24,75 23,8 | 29 (15 May 2009) | 15 (5 Dec 2008) |
| Initiation of PDP | 61 (20 Nov 2007) | 48 (25 June 2008) | 63 (8 May 2008) | 175 (31 Oct 2007) | 86,75 103 | 69 (24 June 2009) | 168 (7 May 2009) |
| Approval of WG Charter |  | 70 (17 July 2008) | 84 (29 May 2008) |  | 77 117 | 98 (23 July 2009) | 216 (24 June 2009) |
| Publication Initial Report | 179 (17 March 2008) | 245 (8 Jan 2009) | 326 (26 Jan 2009) | 243 (7 Jan 2008) | 248,28 |  |  |
| Publication Final Report | 202 (9 April 2008) | 315 (19 March 2009) | 518 (6 August 2009) | 332 (4 April 2008) | 342 |  |  |
| Council Vote | 392 (16 Oct 2008) | 343 (16 April 2009) | 546 (3 Sept 2009) | 345 (17 April 2008) | 406 |  |  |

# Footnotes

Including IRTP Part B and PEDNR

Including PEDNR

Including IRTP Part B and PEDNR

Followed by launch of drafting team on 17 April 2008, which produced its final report on 4 June 2008, whose recommendations where adopted by the council in October 2008.