| Phase | Title | Links |
| --- | --- | --- |
| 1 - Issue Identification | GNSO Council Action Items [refer to list on wiki] | LINK |
| 2 - Issue Scoping | Purpose of WHOIS Issue Report [DEFERRED PENDING OUTCOME OF EWG FINAL REPORT] (WHOIS-PDP) | LINK |
| 2 - Issue Scoping | Uniform Dispute Resolution Policy [ON HOLD] (UDRP) | LINK |
| 3 - Initiation | Drafting Team for a Cross Community Working Group for an IANA Stewardship Transfer Proposal | LINK |
| 4 - Working Group | Discussion Group – New gTLD Subsequent Rounds (ngTLDs-DG) | LINK |
| 4 - Working Group | Curative Rights Protections for IGO/INGOs (IGO-INGO-CRP) | LINK |
| 4 - Working Group | GNSO Standing Committee on Improvements Implementation (SCI) | LINK |
| 4 - Working Group | IRTP Part D PDP Working Group (IRTP-D) | LINK |
| 4 - Working Group | Policy & Implementation Working Group (POLIMP) | LINK |
| 4 - Working Group | GNSO Data & Metrics for Policy Making Working Group (DMPM) | LINK |
| 4 - Working Group | RAA Privacy & Proxy Services Accreditation Issues Working Group (PPSAI) | LINK |
| 4 - Working Group | Translation/Transliteration of Internationalized Registration Data Working Group (T&T) | LINK |
| 4 - Working Group | GNSO PDP Improvements Discussion Group (PDP-IMPR) | LINK |
| 4 - Working Group | GNSO Review Committee (REVIEW) | LINK |
| 4 - Working Group | Geo Regions Review Community-wide Working Group (GEO) | LINK |
| 4 - Working Group | GAC-GNSO Consultation Group on Early Engagement (GAC-GNSO-CG) | LINK |
| 4 - Working Group | Cross-Community Working Group to develop a Framework of Principles for Future CWGs (CWG-Principles) | LINK |
| 4 - Working Group | Cross-Community Working Group to develop a framework for the use of Country and Territory names as TLDs (CWG-UCTN) | LINK |
| 5 - Council Deliberations | -none- | -none- |
| 6 – Board Vote | Protection of International Organization Names in All gTLDs PDP (IGO-INGO) | LINK |
| 7 - Implementation | Inter-Registrar Transfer Policy Part B PDP (IRTP-B) | LINK |
| 7 - Implementation | Inter-Registrar Transfer Policy Part C PDP (IRTP-C) | LINK |
| 7 - Implementation | Locking of a Domain Name subject to UDRP Proceedings PDP (UDRP-LOCK) | LINK |
| 7 - Implementation | ‘Thick’ WHOIS PDP (THICK-WHOIS) | LINK |
| Other | -none- | -none |

Last updated: 25 August 2014

This list includes GNSO Council projects. It does not reflect the full granularity of each task, just current status and next scheduled action(s).

| 1 - Issue Identification |
| --- |
| Description | Initiated | Target Date | Who holds Token | Pending action/status |
| -none- |  |  |  |  |

| 2 - Issue Scoping |
| --- |
| Description | Initiated | Target Date | Who holds Token | Pending action/status |
| Issue Report on the purpose of collecting and maintaining gTLD registration data and on solutions to improve accuracy and access to gTLD registration data. Staff: TBD | 2012-Nov-8 |  | Staff | The Board resolution on the Whois RT Recommendations (see http://www.icann.org/en/groups/board/documents/resolutions-08nov12-en.htm) directed preparation of an Issue Report on the purpose of collecting and maintaining gTLD registration data, and on solutions to improve accuracy and access to gTLD registration data, as part of a Board-initiated GNSO policy development process. The Preliminary Issue Report was published for public comment on 15 March 2013. The comment forum closed on 13 May. A Final Issue Report will be published following the finalization of the EWG recommendations (EWG Final Report was published on 6 June 2014) and subsequent Board consideration. |
| Uniform Dispute Resolution Policy Issue Report Staff: TBD | 2011-Feb-03 | Completed for now (with further Issue Report due in March 2015) | Staff | The GNSO Council deferred commencement of a PDP on reviewing the UDRP, except with regard to the lock issue. Instead, an Issue Report reviewing all rights protection mechanisms (current and developed for the New gTLD Program) including the UDRP and URS was requested by the GNSO Council, to be delivered eighteen months after the first delegation of new gTLDS (which occurred in October 2013). |

| 3 - Initiation |
| --- |
| Description | Initiated | Target Date | Who holds Token | Pending action/status |
| Drafting Team to develop a charter for a Cross Community Working Group to Develop an IANA Stewardship Transfer Proposal Chairs: Jonathan Robinson, Byron Holland Staff: M. Konings, B. Boswinkel This cross-community drafting team was formed to develop a proposed charter for a cross-community working group to develop an IANA Stewardship Transfer Proposal. | 2014-Jul-14 | Ongoing | Council | The drafting team with representatives from the GNSO, ccNSO, ALAC and SSAC met for the first time on 14 July to commence their deliberations on the development of a proposed charter for a cross-community working group to develop an IANA Stewardship Transfer Proposal. The DT completed its work on the charter, which has now been submitted to the different SO/ACs for review and approval well ahead of the ICANN meeting of LA. The GNSO Council is expected to consider the charter for approval at its meeting on 4 September. |

| 4 – Working Group |
| --- |
| Description | Initiated | Target Date | Who holds Token | Pending action/status |
| Discussion Group – New gTLD Subsequent Rounds Interim Chair: Bret Fausset Staff: S. Chan, M. Konings The Discussion Group was created to discuss the experiences gained by the first round of new gTLD applications and identify subjects for future issue reports, if any, that might lead to changes or adjustments for subsequent application procedures. | 2014-Jun-25 | Ongoing | WG | The GNSO resolution creating the new Discussion Group was approved on 25 June 2014. The DG held its introductory meeting on 11 August 2014 and is expected to hold two sessions prior to meeting for a face to face in Los Angeles. DG members are being encouraged to provide their list of issues from the first round of the New gTLD Program, after which staff will prepare a first draft of the categorized issues. In addition, the GNSO Council resolution requested a status report from ICANN Staff on the current progress of (a) the New gTLD program generally; (b) ICANN's anticipated timeline and work plan for the review specified in Section 9.3 of the Affirmation of Commitments; (c) ICANN's work to date on any evaluation of the first round; (d) the work to date on the post-launch independent review of the Trademark Clearinghouse; and (e) ICANN's current projection for a timetable for subsequent rounds, which is expected to be delivered shortly. |
| Curative Rights Protections for IGO/INGOs Chair: TBD Council Liaison: Petter Rindforth Staff: M. Wong, S. Chan The PDP WG is tasked to explore possible amendments to the Uniform Dispute Resolution Policy (UDRP) and the Uniform Rapid Suspension procedure (URS) so as to enable International Governmental Organizations (IGOs) and International Non-Governmental Organizations (INGOs) to access and use curative rights protection mechanisms | 2014-Jun-05 | Ongoing | WG | Based on the recommendation of the IGO-INGO PDP Working Group, the GNSO Council resolved to initiate a PDP on 5 June 2014. The GNSO Council approved the WG’s charter for the PDP WG at the London GNSO Council Public Meeting. The WG held its introductory meeting on 11 August 2014 and will resume sessions in September. Staff is preparing research documentation. |
| GNSO Standing Committee on Improvements Implementation (SCI) Chair: Ron Andruff Vice-Chair: Cintra Sooknanan Council Liaison: Avri Doria Staff: J. Hedlund, M. Wong, M. Konings The GNSO Standing Committee on Improvements Implementation (SCI) reviews and assesses the effective functioning of recommendations related to GNSO Improvements that have been approved by the Council. It was recently confirmed as a standing committee by the GNSO Council. | 2011-Apr-07 | Ongoing | SCI | The SCI has been working on the following topics: Voting outside a GNSO Council meeting; Waiver of the 10-day motion deadline under the GNSO Operating Procedures; Consensus scale definitions in the current WG Guidelines. A formal consensus call has concluded for #3, and one is in progress for #1 and #2. Once all formal consensus calls are completed, the SCI’s proposed changes to the GNSO Operating Procedures will be published for public comment and sent to the GNSO Council for review and adoption. |
| IRTP Part D PDP WG Chair: James Bladel Council Liaison: Volker Greimann Staff: L. Hoffmann, M. Konings PDP on the remaining IRTP issues which include: Reporting requirements for registries and dispute providers in relation to the TDRP; How to handle disputes when multiple transfers have occurred in the TDRP; Should dispute options for registrants be developed; Should there be requirements or best practices for registrars to make information on transfer dispute resolution options available; Are existing penalties for policy violations sufficient; Have EPP AuthInfo codes eliminated the need for FOAs. | 2012-Oct-17 | Ongoing | WG | A second complete draft of the final report has been circulated to the WG and members will now start to determine consensus levels. The WG envisages submitting the Final Report to the GNSO Council in time for consideration at the ICANN 51 meeting in Los Angeles. |
| Policy & Implementation WG Co-Chairs: Chuck Gomes, J. Scott Evans Council Liaison: Amr Elsadr and Brian Winterfeldt Staff: M. Konings, M. Wong The WG is tasked to provide the GNSO Council with a set of recommendations on: A set of principles that would underpin any GNSO policy and implementation related discussions A process for developing gTLD policy, perhaps in the form of “Policy Guidance”, including criteria for when it would be appropriate to use such a process (for developing policy other than “Consensus Policy”) instead of a GNSO Policy Development Process; A framework for implementation related discussions associated with GNSO Policy Recommendations; Criteria to be used to determine when an action should be addressed by a policy process and when it should be considered implementation, and; Further guidance on how GNSO Implementation Review Teams are expected to function and operate. | 2013-May-09 | Ongoing | WG | The WG has approved its Working Definitions document and developed a draft set of Working Principles. The WG has begun to consider each of its other Deliverables under its Work Plan serially rather than use sub-groups for each. As a result, an updated work plan was published (see https://community.icann.org/x/rC_fAg). The WG Is meeting weekly to continue its work on its various Deliverables. It has completed its review of input obtained from a number of SO/AC/SG/Cs on its Charter, and plans to solicit feedback on new proposed policy guidance and input processes by mid-September, with a view toward producing a more detailed framework for community discussion at the LA meeting. |
| GNSO Data & Metrics for Policy Making WG (DMPM) Chair: Jonathan Zuck Council Liaison: Klaus Stoll Staff: S. Chan, L. Hoffmann The WG is tasked to provide the GNSO Council with a set of recommendations on: A set of principles that may compliment any GNSO policy efforts related to metric/data requirements to better inform the policy development process; A process for requesting metrics and reports both internal to ICANN or external, including GNSO contracted parties; A framework for distributing metrics and reports to Working Groups, the GNSO Council and the GNSO as a whole; Changes, if any, to existing Working Group Guidelines and work product templates | 2012-Oct-17 | On-going | WG | The WG has established a bi-weekly meeting schedule and has completed the due-diligence phase of its work which included the review of several previous PDP and non-PDP efforts to analyse where and how metrics were used to facilitate the policy process and to also identify gaps where they were not used. The WG is now reviewing the primary work products of WGs to draft possible methods for data collection and metrics before they review how metrics can be obtained from contracted parties and other external sources. The WG is targeting the LA Meeting to expand this issue discussion with the broader community. |
| Privacy & Proxy Services Accreditation Issues PDP WG Chair: Don Blumenthal Council Liaison: Maria Farrell Staff: M. Wong, M. Konings The Registrar Accreditation Agreement (RAA), the contract governing the relationship between ICANN and accredited registrars, has been in place since 2001. The Board initiated negotiations for a new RAA in October 2011, and requested an Issue Report from the GNSO at the same time. The final version of the new RAA was approved by the Board in June 2013, thereby signifying that the RAA negotiations were concluded. Per the Board’s 2011 request, the remaining issues, which have been identified as those relating to privacy & proxy services and their accreditation, will be examined in this PDP. | 2009-May-21 | Ongoing | WG | The WG is continuing to meet weekly, to discuss each of its Charter questions using a template to record deliberations and preliminary conclusions. It presented its preliminary conclusions to the community for feedback in London, and aims to publish its Initial Report in early 2015 (see work plan at https://community.icann.org/x/wx3Rag). The WG has been selected by the GNSO Council to be the first group to participate in the facilitated face-to-face meetings pilot project for FY15; this will take place just before the LA meeting, on Friday 10 October 2014. |
| Translation/Transliteration of Internationalized Registration Data PDP WG Co-Chairs: Chris Dillon, Rudi Vansnick Council Liaison: Ching Chiao Staff: J. Hedlund/L. Hoffmann The Council approved the initiation of a PDP on translation and transliteration of contact information on 13 June 2013. | 2012-Oct-17 | Ongoing | WG | The WG is meeting weekly and has reviewed all Community input received. It is aiming to publish its Initial Report by the ICANN meeting in LA (see work plan at https://community.icann.org/x/xR3Rag). To that end, the WG Chairs submitted a strawman document to the WG, which the WG is currently discussing. |
| GNSO PDP Improvements Implementation Discussion Group Volunteers: Gabriela Szlak, Dan Reed, Klaus Stoll Staff: M. Konings The GNSO Council agreed to form a small committee of interested Council members to work with staff on the implementation of the GNSO PDP Improvements (see http://gnso.icann.org/en/drafts/pdp-improvements-table-16jan14-en.pdf), particularly items 3 (Increase pool of PDP volunteers) and 5 (Improved online tools & training) . | 2014-Jan-30 | Ongoing | Council | The group held a first informal meeting in Singapore to discuss how to approach the next steps identified for items 3 and 5, namely: Review existing outreach efforts and determine whether there are any actions the GNSO Council should be taking to increase the pool of PDP volunteers (item 3) Review existing online tools & training efforts and determine whether there are any additional actions should be taken by the GNSO Council and/or provide input on how existing activities may be further improved / modified in order to contribute to the success of the PDP (item 5) A memo providing some further background information on these tasks as well as proposed next steps were circulated for review to the Discussion Group. Staff published a proposal for PDP WG member onboarding which was further discussed by the GNSO Council in London. Staff will move forward with the implementation of the identified GNSO PDP improvements, incorporating the suggestions made in London. |
| GNSO Review Committee Lead: Jennifer Wolfe Staff: M. Konings, M. Wong Following discussions in Singapore, the GNSO Council agreed to form a small committee to liaise with the SIC on the GNSO Review and discuss a potential self-review of the GNSO Council. | 2014-Apr-07 | Ongoing | Working Party | The Working Party finalized a questionnaire/survey for which community responses will form the basis of the third party review (360 assessment) recommended by the Board’s Structural Improvements Committee. The survey has been published, and the Working Party will continue to work with the independent examiner selected by the SIC to prepare for the next phase of the review. |
| Geo Regions Review Community-wide Working Group Chair: Dave Archbold (ccNSO)(retired) GNSO Council Reps: Ching Chiao Staff: R. Hoggarth This Board-chartered cross community WG has consulted with ICANN stakeholders regarding the definition and applications of ICANN’s Geographic Regions. Changes could have broad impact, so this WG has representatives from most SOs and ACs. | 2008-Aug-07 | Nov 2014 | WG | The Working Group published its Final Report recommendations (see - http://www.icann.org/en/news/announcements/announcement-22jun13-en.htm) and circulated the Final Report to ICANN SOs and ACs (including the Council) for review and comment. The Council provided feedback to the WG Chair on 13 December 2013 (see http://gnso.icann.org/en/correspondence/robinson-to-archbold-13dec13-en.pdf). After all written SO-AC responses are submitted and reviewed by the WG, the Final Report of the WG will be shared with the Board for review. This is likely to take place after the ICANN Public Meeting in London. With the retirement of the WG Chair, a new chair is being appointed to help marshal this effort toward review by the Board. |
| GAC-GNSO Consultation Group on GAC Early Engagement in GNSO PDP Chairs: Jonathan Robinson (GNSO) and Manal Ismail (GAC) Staff: M. Konings, O. Nordling The Governmental Advisory Committee (GAC) and the Generic Names Supporting Organization (GNSO) have jointly established a consultation group to explore ways for the GAC to engage early in the GNSO Policy Development Process (PDP) and to improve overall cooperation between the two bodies (for example, by exploring the option of a liaison). | 2014-Jan-07 | Ongoing | CG | The launch of this GAC-GNSO Consultation Group on Early Engagement is the result of discussions between the two entities at the ICANN meeting in Buenos Aires as well as previous ICANN meetings, reflecting a joint desire to explore and enhance ways of early engagement in relation to GNSO policy development activities. The issue was also specifically called-out by both Accountability and Transparency Review Teams (ATRT). The CG is meeting every two weeks with the team leads for the two tracks (day-to-day co-ordination and PDP) meeting every other week. The CG presented its preliminary recommendations to the GNSO and GAC for review and consideration on a number of items at the ICANN meeting in London. The CG has now recommenced its meetings and is preparing its activities for between now and the ICANN meeting in LA. |
| Cross-Community Working Group- on a Framework of CWG Principles GNSO Council Co-Chair: John Berard ccNSO Council Co-Chair: Becky Burr Staff: M. Wong, B. Boswinkel, S. Chan The CWG was chartered by the ccNSO and GNSO Councils to further refine the principles initially drafted by the GNSO and commented on by the ccNSO for the formation, operation and termination of future cross-community working groups. | 2011-May-19 | Ongoing | CWG | This Cross-Community Working Group was chartered by both the ccNSO and GNSO Councils at their respective meetings in March in Singapore. A call for volunteers was sent to all SO/ACs. The CWG has held four meetings and has reviewed the processes and outcomes of selected prior CWGs, including mapping their charters to the typical WG life cycle. The WG has begun looking in detail at each of these stages of the typical WG life cycle (Initiation of CWG, Formation, Operation, Closure, Post-Closure). The work schedule has been developed and shared with the WG. The next meeting is expected to be held in early September. |
| Cross-Community Working Group to develop a framework for the use of Country and Territory names as TLDs (CWG-UCTN) GNSO Council Co-Chairs: Heather Forrest, Ching Chiao ccNSO Council Co-Chairs: Paul Szyndler, Lise Fuhr Council liaison: Gabriela Szlak Staff: M. Konings, B. Boswinkel The objective of the CWG is to: Further review the current status of representations of country and territory names, as they exist under current ICANN policies, guidelines and procedures; Provide advice regarding the feasibility of developing a consistent and uniform definitional framework that could be applicable across the respective SO’s and AC’s; and Should such a framework be deemed feasible, provide detailed advice as to the content of the framework. | 2014-Mar-26 | Ongoing | CWG | Following the adoption of the Final Report of the ccNSO Study group on the use of Names for Country and Territory, the ccNSO invited the GNSO to join a CWG on the use of coutry and territory names as TLDs. Both the ccNSO and GNSO Council adopted the charter during its respective meetings in Singapore. The GNSO Council has requested that Heather Forrest and Ching Chiao serve as GNSO co-chairs to this WG. A first meeting of the CWG was held on 10 June, followed by a F2F meeting in London. The WG has started working on its work plan and schedule for upcoming meetings. |

| 5 – Council Deliberation |
| --- |
| Description | Initiated | Target Date | Who holds Token | Pending action/status |
| - None - |  |  |  |  |

| 6 – Board Vote |
| --- |
| Description | Initiated | Target Date | Who holds Token | Pending action/status |
| Protection of Intergovernmental Organization Names in New gTLDs Staff: M. Wong Chair: Thomas Rickert Council Liaison: | 2012-Apr-12 | 2014-Dec-11 | Board/ Council | The GNSO Council unanimously approved the motion on the IGO-INGO WG’s recommendations at its 20 Nov 2013 meeting. As requested by the Board, the NGPC developed a proposal for further discussion in March 2014. In April 2014 the Board voted to adopt those of the GNSO’s recommendations that are not inconsistent with GAC advice received on the topic, and requested additional time to consider the remaining recommendations, for which it will also facilitate dialogue between the GAC and the GNSO. Staff has started to organize an Implementation Review Team (in line with the GNSO’s recommendation), to be led by Han Chuan Lee, to implement those recommendations recently adopted by the Board. On 18 June the NGPC sent a letter to the GNSO Council requesting that the GNSO contemplate initiating a process to consider possible modifications to its recommendations, per the PDP Manual. The GNSO Council will now determine next steps, including whether to reconvene the IGO-INGO WG, at its September GNSO Council meeting. |

| 7 – Implementation |
| --- |
| Description | Initiated | Target Date | Who holds Token | Pending action/status |
| IRTP Part B PDP Adopted Recommendations 5. Promotion by ALAC and other ICANN structures of the measures outlined in a recent SSAC report: A Registrant's Guide to Protecting Domain Name Registration Accounts (SAC 044). (See http://gnso.icann.org/resolutions/#201106 for text of resolution) IRTP Part B Recommendation #9 – part 2 The GNSO Council resolved in Singapore that prior to consideration of the recommendation which states: "denial reason #7 should be replaced by adding a new provision in a different section of the IRTP on when and how domains may be locked or unlocked", the GNSO Council requests ICANN Staff to provide a proposal for such a new provision, taking into account the IRTP Part B WG deliberations in relation to this issue (see IRTP Part B Final Report - (Recommendation #9 - part 2). Upon review of the proposal, the Council will consider the recommendation. IRTP Part B Recommendation #8 The GNSO Council resolved in Singapore that prior to considering a recommendation to standardize and clarify WHOIS status messages regarding Registrar Lock status, the GNSO Council asked staff to provide a proposal to ensure that it is technically feasible to implement this recommendation. Staff should take into account the IRTP Part B WG deliberations in relation to this issue (see IRTP Part B Final Report). (IRTP Part B Recommendation #8). The goal of these changes is to clarify why the Lock has been applied and how it can be changed. Upon review of the proposed plan, the Council will consider whether to approve the recommendation. | 2011-Jun-22 2011-Jun-22 2011-Jun-22 | 31 Jan 2015 31 Jan 2015 | SOs/ACs Completed Completed | Chair of the GNSO Council has sent messages to the Chairs of ALAC, SSAC, ccNSO, GAC, ASO (see http://gnso.icann.org/mailing-lists/archives/council/msg11736.html) to inform them about the recommendation and open discussions. The ICANN Board adopted the recommendation and staff proposal at its meeting in Costa Rica. ICANN Staff has completed the implementation and the GDD team announced the update to the IRTP. ICANN is amending the Inter-Registrar Transfer Policy (IRTP) to implement the GNSO's recommendations related to locking and unlocking of domain names as a result of the IRTP Part B Policy Development Process (PDP). These changes came after significant collaboration and deliberation by the GNSO and other members of the ICANN community, and were approved by the ICANN Board of Directors on 16 March 2012. The modifications are the following: Registrars will be obligated to inform their registrants in the registration agreement under which circumstances a domain name will be locked and how a domain name can be unlocked. Registrars will be obligated to unlock a domain name within five (5) calendar days of receiving a request to unlock a domain name from the registrant if the registrar does not provide facilities for the registrant to unlock the domain name. The new policy will take effect 31 Jan 2015. The ICANN Board adopted the recommendation at its meeting on 6 May (see http://www.icann.org/en/groups/board/documents/resolutions-06may12-en.htm#1.5). ICANN Staff published the proposed implementation plan for public comment on 10 May 2013 (see http://www.icann.org/en/news/public-comment/wisp-10may13-en.htm). The Reply period for public comment closed on 24 June 2013. The GDD team has announced the Additional Whois Information Policy (AWIP) on 7 July 2014. The AWIP was developed with the goals of providing a better understanding of the existing domain name statuses (also known as EPP status codes) for Whois service users, and to create more uniformity among the multiple Whois outputs provided by ICANN-accredited registrars and gTLD registry operators. The AWIP requires each ICANN-accredited registrar and gTLD registry operator that displays Whois status codes to include in its Whois output a link to an ICANN web page where the existing domain names statuses are listed along with their respective meanings. Additionally, registries must identify the Globally Unique Registrar ID (GURID, also commonly known as an IANA ID) of the registrar that sponsors each registration in its Whois output. The new policy will take effect 31 Jan 2015. |
| IRTP Part C Recommendations The GNSO Council unanimously adopted the recommendations of the IRTP Part C PDP at its meeting on 17 October 2012 (see http://gnso.icann.org/en/resolutions#20121017-4). | 17 Oct 2012 | 1 May 2015 | Staff | The ICANN Board adopted the IRTP Part C recommendations at its meeting in December (see https://www.icann.org/en/groups/board/documents/resolutions-20dec12-en.htm#2.a). As instructed by the GNSO Council, an Implementation Review Team was formed. Meetings of the IRT have recently recommenced and details of the proposed implementation plan have been shared with the IRT. A white board session on Rec #1 (Chg of Rt) was conducted at the London meeting. Based on great feedback by the community, GDD will create the next version of process flow on the Chg of Rt and collaborate further with the IRT prior to drafting final policy language. The target policy effective date is 1 May 2015. |
| Locking of a Domain Name Subject to UDRP Proceedings Recommendations The GNSO Council unanimously adopted the recommendations of the Locking of a Domain Name subect to UDRP Proceedings at its meeting of 1 August 2013. | 2013-Aug-01 | 30 Dec 2015 | Staff | The ICANN Board adopted the Locking of a Domain Name subject to UDRP Proceedings at its meeting on 28 September (see http://www.icann.org/en/groups/board/documents/resolutions-28sep13-en.htm#1.c). As instructed by the GNSO Council, an Implementation Review Team was formed. Staff has met several times with the IRT and published the proposed policy language for public comment on 19 May 2014 (see https://www.icann.org/public-comments/udrp-rules-proposed-2014-05-19-en). The IRT reviewed the public comments and staff is now finalizing the proposed policy language and collaborating with the IRT to determine a Policy Effective Date. |
| Thick WHOIS PDP Recommendations The GNSO Council adopted the recommendation to require Thick Whois for all gTLD registries at its meeting on 31 October 2013. | 2012-Mar-14 | On-Going | Staff | The ICANN Board approved the GNSO recommendations on Thick WHOIS at its meeting on 7 February 2014. (http://www.icann.org/en/groups/board/documents/resolutions-07feb14-en.htm). An Implementation Review Team has been formed and a draft implementation plan has been created and shared with the IRT. A further review of the plan, issues, and risks are being discussed in subsequent IRT sessions. ICANN’s General Counsel’s Office is also working on the legal review per the GNSO Council’s recommendation. |