

| **Phase** | **Title** | **Links** |
| --- | --- | --- |
| **1 - Issue Identification** | **GNSO Council Action Items** [refer to list on wiki] | [LINK](https://community.icann.org/display/gnsocouncilmeetings/Action%2BItems) |
| **2 - Issue Scoping** | **- none -** |  |
| **3 - Initiation** | **- none -** |  |
| **4 - Working Group** | **New gTLD Auction Proceeds** (CWG-Auction) | [LINK](#AUCTION) |
| **4 - Working Group** | **Cross Community Working Group on Enhancing ICANN Accountability** (WS2) | [LINK](#WS2) |
| **4 - Working Group** | **Review of All Rights Protection Mechanisms in All gTLDs PDP** (RPM) | [LINK](#UDRP) |
| **4 - Working Group** | **New gTLD Subsequent Procedures PDP** (Sub-Pro) | [LINK](#subrnd_gTLD) |
| **4 - Working Group** | **Next-Generation gTLD Registration Directory Services (RDS) to replace WHOIS** (RDS) | [LINK](#WHOIS_PDP) |
| **4 - Working Group** | **Curative Rights Protections for IGO/INGOs PDP** (IGO-INGO-CRP) | [LINK](#IGO_INGO_RPM) |
| **4 - Working Group** | **Cross-Community Working Group to develop a framework for the use of Country and Territory names as TLDs** (CWG-UCTN) | [LINK](#CWG_UTCN) |
| **4 - Working Group** | **Cross-Community Working Group on Internet Governance** (CWG-IG) | [LINK](#IG) |
| **5 – Council Deliberations** | **- none -** |  |
| **6 – Board Vote** | **GNSO Review Working Group** (GRWG) | [LINK](#GRWG) |
| **6 – Board Vote** | **Protection of International Organization Names in All gTLDs PDP** (IGO-INGO) | [LINK](#IGO_INGO) |
| **6 – Board Vote** | **Geo Regions Review** (GEO) | [LINK](#GEO) |
| **7 – Implementation** | **GNSO Rights & Obligations under Revised ICANN Bylaws Drafting Team** (RODT) | [LINK](#RODT) |
| **7 – Implementation** | **GAC-GNSO Consultation Group on Early Engagement** (GAC-GNSO-CG) | [LINK](#GAC_GNSO_CG) |
| **7 – Implementation** | **Privacy & Proxy Services Accreditation Issues PDP** (PPSAI) | [LINK](#PPSAI) |
| **7 – Implementation** | **Translation/Transliteration of gTLD Registration Data PDP** (T&T) | [LINK](#TandT) |
| **7 – Implementation** | **Inter-Registrar Transfer Policy Part C PDP** (IRTP-C) | [LINK](#IRTP_C) |
| **7 – Implementation** | **‘Thick’ WHOIS PDP** (THICK-WHOIS) | [LINK](#THICK_WHOIS) |
| **7 – Implementation** | **Protection of International Organization Names in All gTLDs PDP** (IGO-INGO) | [LINK](#IGO_INGO2) |
| **Other** | **Consumer Choice Competition and Trust Review Team** (CCT-RT) | [LINK](#CCT_RT) |
| **Other** | **Cross-Community Working Group for a Framework of Principles for Future CWGs (CWG-Principles)** | [LINK](#CWG_CWG)  |

Last updated: 16 January 2017

This list includes GNSO Council projects. It does not reflect the full granularity of each task, just current status and next scheduled action(s).

| **1 - Issue Identification** |
| --- |
| **Description** | **Initiated** | **Target Date**  | **Who holdsToken** | **Pending action/status** |
| GNSO Council Action Items - [LINK](https://community.icann.org/display/gnsocouncilmeetings/Action%2BItems) | NA | NA | NA | Refer to most recent action item list for latest status |

| **2 - Issue Scoping** |
| --- |
| **Description** | **Initiated** | **Target Date**  | **Who holdsToken** | **Pending action/status** |
| **- None -**  |  |  |  |  |

| **3 – Initiation** |
| --- |
| **Description** | **Initiated** | **Target Date**  | **Who holdsToken** | **Pending action/status** |
| - none -  |  |  |  |  |

| **4 – Working Group** |
| --- |
| **Description** | **Initiated** | **Target Date**  | **Who holdsToken** | **Pending action/status** |
| **[New gTLD Auction Proceeds Cross-Community Working Group](https://community.icann.org/display/NGAPDT/New%2BgTLD%2BAuction%2BProceeds%2BDrafting%2BTeam%2BHome) (CCWG)**Co-Chairs: Ching Chiao (ccNSO); Jonathan Robinson (GNSO) Staff: M. KoningsThis CCWG is tasked with developing a proposal(s) for consideration by its Chartering Organizations on the mechanism that should be developed in order to allocate the new gTLD Auction Proceeds. As part of this proposal, the CCWG is also expected to consider the scope of fund allocation, due diligence requirements that preserve ICANN’s tax status as well as how to deal with directly related matters such as potential or actual conflicts of interest. The CCWG will not make any recommendations or determinations with regards to specific funding decisions (i.e. which specific organizations or projects are to be funded or not). | 2016-Mar-10 | Ongoing | SO/ACs/ CCWG | The new gTLD Program established ICANN auctions of last resort as a mechanism to resolve string contention. Most string contentions (approximately 90% of sets scheduled for ICANN auction) have been resolved through other means before reaching an auction conducted by ICANN's authorized auction service provider, Power Auctions LLC. However, it was recognized from the outset that significant funds could accrue as a result of several auctions. As such, these auction proceeds have been reserved and earmarked until the Board authorizes a plan for the appropriate use of the funds. Board, staff, and community are expected to be working together in designing and participating in the next steps addressing the use of new gTLD auction proceeds. A Drafting Team (DT) was created to develop a proposed charter for a CCWG. The DT submitted the proposed charter for consideration by the different ICANN Supporting Organizations and Advisory Committees (SO/ACs) prior to ICANN57. The GNSO, ccNSO and ALAC adopted the Charter ([https://community.icann.org/x/DJjDAw)](https://community.icann.org/x/DJjDAw%29) at ICANN57 in Hyderabad 3-9 November, with the ASO and SSAC confirming adoption shortly thereafter. A call for participants to take part in the newly established CCWG was issued on 13 December 2016, and the group will hold its first meeting on 26 January 2017. |
| **[Cross Community Working Group on Enhancing ICANN Accountability](https://community.icann.org/display/WEIA/WS2%2B-%2BEnhancing%2BICANN%2BAccountability%2BHome)**Co-Chairs: Mathieu Weill (ccNSO), Thomas Rickert (GNSO), Leon Sanchez (ALAC)Staff: B. TurcotteThis CCWG is expected to deliver proposals that would enhance ICANN’s accountability towards all stakeholders. In Work Stream 1, it identified those mechanisms that must be in place or committed to before the IANA Stewardship Transition occurs. Currently, in Work Stream 2 it is considering those mechanisms for which a timeline for implementation extends beyond the IANA Stewardship Transition. | 2016-Jun-26 | June 2017 | CCWG | The CCWG-WS2 commenced work on Work Stream 2 (WS2) at ICANN56 in June 2016. It will address the remaining nine issues that were deferred from WS1 (i.e. Diversity, Guidelines for Good Faith Conduct, Human Rights, Jurisdiction, Ombudsman, Reviewing the Cooperative Engagement Process (CEP), SO/AC Accountability, Staff Accountability, and Transparency).  |
| **[Rights Protection Mechanisms (RPMs) in All gTLDs PDP](https://community.icann.org/display/RARPMRIAGPWG/Review%2Bof%2Ball%2BRights%2BProtection%2BMechanisms%2B%28RPMs%29%2Bin%2Ball%2BgTLDs%2BPDP%2BWorking%2BGroup%2BHome)** Co-Chair(s)**:** Philip Corwin, J. Scott Evans, Kathy KleimanCouncil Liaison**:** Heather ForrestCommunity Liaisons (to/from the New gTLD Subsequent Procedures PDP WG): Robin Gross, Susan PayneStaff: M. WongThis WG is tasked to review all the RPMs that have been developed by ICANN in a two-phased PDP. By the end of its work, the WG will be expected to also have considered the overarching issue as to whether or not the RPMs collectively fulfil their purposes or whether additional policy recommendations will be necessary, including to clarify and unify the policy goals.  | 2011-Feb-03 | Ongoing | WG | On 28 February 2016, the GNSO Council voted to [initiate](http://gnso.icann.org/en/council/resolutions#20160218-3) this Policy Development Process (PDP) and adopted the Working Group Charter (updated from its draft form following work by several Council volunteers) in March ([https://community.icann.org/x/2CWAAw)](https://community.icann.org/x/2CWAAw%29). The PDP is being conducted in two phases, beginning with the RPMs developed for the 2012 New gTLD Program, with the 1999 Uniform Domain Name Dispute Resolution Policy to follow. The first WG meeting was held on 21 April 2016. The WG began its work with a review of the Trademark Post-Delegation Dispute Resolution Procedure (TM-PDDRP). Sub Teams were formed concurrently to perform data gathering and to clarify the Charter questions for the WG’s review of the Trademark Clearing House (TMCH). The WG wrapped up its initial review of the TM-PDDRP at ICANN57 and finalized the scope of its review of the TMCH in December 2016. The WG expects to be working on Phase 1 through late/end 2017. |
| **[New gTLD Subsequent Procedures PDP](https://community.icann.org/display/NGSPP/New%2BgTLD%2BSubsequent%2BProcedures%2BPDP%2BHome)**Co-Chair(s): Avri Doria and Jeff NeumanCouncil Liaison: Paul McGradyCommunity Liasons (to/from the RPM Review PDP WG): Robin Gross, Susan PayneCommunity Liaison (to/from CCT-RT): Carlos Raúl GutiérrezStaff: S. Chan, J. Hedlund, E. BarabasThis WG is tasked with calling upon the community’s collective experiences from the 2012 New gTLD Program round to determine what, if any changes may need to be made to the existing 2007 Introduction of New Generic Top-Level Domains policy recommendations. Those policy recommendations will remain in place for subsequent rounds unless modified via a PDP. The work of this WG follows the efforts of the New gTLD Subsequent Procedures Discussion Group (DG), which identified a set of issues for a future PDP-WG to consider in their deliberations.  | 2014-Jun-25 | 2015-Dec | WG | The WG was chartered by the GNSO Council in January 2016 ([https://community.icann.org/x/KAp1Aw)](https://community.icann.org/x/KAp1Aw%29). It has completed preliminary deliberations on a set of overarching topics, which formed the basis for a formal request for input that was sent to all SO/ACs and GNSO Stakeholder Groups and Constituencies (SG/Cs) ahead of ICANN56 in Helsinki in June. The WG has considered input received from the community on the overarching issues and is now working to determine what the WG’s outputs will be for these topics. In addition, the WG’s four Work Track (WT) Sub Teams continue to work to address the other 30+ topics identified in the WG’s charter. The WG and WTs are working to develop a second Community Comment related to the WTs topics, with a target of mid-February for distribution.On 25 October 2016, the GNSO Council sent a Council response ([https://gnso.icann.org/en/correspondence/gnso-council-to-icann-board-25oct16-en.pdf)](https://gnso.icann.org/en/correspondence/gnso-council-to-icann-board-25oct16-en.pdf%29) to an August 2016 letter from the ICANN Board concerning the question whether some of the WG’s work could be prioritized (e.g., in work streams) or otherwise organized to facilitate the launch of a new application mechanism ([https://gnso.icann.org/en/correspondence/crocker-to-bladel-05aug16-en.pdf)](https://gnso.icann.org/en/correspondence/crocker-to-bladel-05aug16-en.pdf%29). The WG will keep this topic under consideration as it progresses its work. |
| **[PDP on the next generation gTLD Registration Directory Service to replace WHOIS](https://community.icann.org/display/gTLDRDS/Next-Generation%2BgTLD%2BRegistration%2BDirectory%2BServices%2Bto%2BReplace%2BWhois)**Chair: Chuck GomesVice-Chairs: David Cake, Michele Neylon, Susan KawaguchiCouncil liaison: Stephanie Perrin Staff: M. KoningsThe WG is tasked to provide the GNSO Council with recommendations on the following two questions as part of phase 1: What are the fundamental requirements for gTLD registration data and is a new policy framework and next-generation RDS needed to address these requirements? | 2012-Nov-8 | Ongoing | WG | The PDP Working Group was chartered in November 2015 ([https://community.icann.org/x/E4xlAw)](https://community.icann.org/x/E4xlAw%29) and first convened at the end of January 2016. The WG continues to refine its Work Plan (see <https://community.icann.org/x/oIxlAw>). Most recently, the Working Group has compiled a list of possible requirements for gTLD registration directory services, providing a foundation upon which to recommend answers to these two questions: What are the fundamental requirements for gTLD registration data and directory services, and is a new policy framework and next-generation RDS needed to address these requirements? Triage on the list of possible requirements was completed and deliberations on [the list of possible requirements](https://community.icann.org/download/attachments/41890478/RDS%20PDP%20List%20of%20Possible%20Requirements%20D5%20-%20TriageInProgress%20-%2028%20October.pdf?version=1&modificationDate=1477707482753&api=v2) commenced at ICANN57. However, the WG decided to first focus on a number of [key concepts](https://community.icann.org/download/attachments/63153291/KeyConceptsDeliberation-WorkingDraft-12Dec-1800.pdf?version=1&modificationDate=1481814064000&api=v2) which are intended to facilitate the deliberations on the list of possible requirements. At the same time, the WG has compiled a [RDS statement of purpose](https://community.icann.org/x/tiW4Aw), which it may need to review at a later point in time depending on the outcome of the deliberations.  |
| **[Curative Rights Protections for IGO/INGOs](http://community.icann.org/display/gnsoicrpmpdp/) PDP**Co-Chair(s): Philip Corwin, Petter Rindforth Council Liaison: Susan KawaguchiStaff: M. Wong, S. ChanThis WG is tasked with providing the GNSO Council with recommendations as to whether to amend the UDRP and URS to allow access to and use of these mechanisms by IGOs and INGOs and, if so in what respects or whether a separate, narrowly-tailored dispute resolution procedure that takes into account the particular needs and specific circumstances of IGOs and INGOs should be developed. | 2014-Jun-05 | Ongoing | WG | Based on the recommendation of the IGO-INGO PDP Working Group in 2013, the GNSO Council resolved to initiate a PDP and chartered the WG in June 2014 ([https://community.icann.org/x/77rhAg)](https://community.icann.org/x/77rhAg%29). The PDP WG is tasked to explore possible amendments to the Uniform Domain Name Dispute Resolution Policy (UDRP) and the Uniform Rapid Suspension procedure (URS) so as to enable International Governmental Organizations (IGOs) and International Non-Governmental Organizations (INGOs) to access and use curative rights protection mechanisms. The WG is focusing on IGOs, as it has preliminarily determined that INGOs do not appear to require additional protections. At the WG’s request, an external legal expert, Professor Edward Swaine from George Washington University, was engaged to provide a legal opinion on the state of international law on the topic of IGO jurisdictional immunity. Professor Swaine’s final legal opinion has been reviewed and incorporated into its preliminary recommendations by the WG. The WG has also reviewed the IGO Small Group Proposal (see [https://gnso.icann.org/en/correspondence/crocker-icann-board-to-council-chairs-04oct16-en.pdf)](https://gnso.icann.org/en/correspondence/crocker-icann-board-to-council-chairs-04oct16-en.pdf%29), which was sent to the GNSO and the GAC on 6 October 2016. The WG is currently finalizing its preliminary recommendations and its Initial Report, which it plans to publish for public comment by end-January 2017.  |
| **[Cross-Community Working Group to develop a framework for the use of Country and Territory names as TLDs (CWG-UCTN)](https://community.icann.org/x/X7XhAg)**GNSO Council Co-Chairs: Heather Forrest, Carlos Gutierrez ccNSO Council Co-Chairs: Paul Szyndler, Annabeth LangeCouncil liaison: Heather ForrestStaff: B. Boswinkel, J. Braeken, S. Chan, E. BarabasThe objective of the CCWG is to: * Further review the current status of representations of country and territory names, as they exist under current ICANN policies, guidelines and procedures;
* Provide advice regarding the feasibility of developing a consistent and uniform definitional framework that could be applicable across the respective SO’s and AC’s; and
* Should such a framework be deemed feasible, provide detailed advice as to the content of the framework.
 | 2014-Mar-26 | Ongoing | CCWG | The CWG-UCTN used an Options Paper to drive its discussion and concluded its work on two-letter codes ([https://community.icann.org/x/4xXxAg)](https://community.icann.org/x/4xXxAg%29). Following a request for input to all SO/ACs and SG/Cs on 3-character codes, a straw person proposal on 3-character codes was presented and discussed during ICANN55 in Marrakech in March 2016 ([https://community.icann.org/x/4xXxAg)](https://community.icann.org/x/4xXxAg%29). At ICANN56 in Helsinki in June 2016, the CWG-UCTN provided a brief update and conducted a cross community session. A draft status report and initial draft of the CWG-UCTN’s Interim Paper were made available prior to ICANN57 ([https://community.icann.org/x/4xXxAg)](https://community.icann.org/x/4xXxAg%29). Discussions at ICANN57 in Hyderabad in November 2016 focused on these two documents, with a view towards winding up the CWG’s work in favour of another effort with a broader charter and scope to rationalize the various current community efforts relating to geographic names.. The draft Interim Paper is being further revised based on feedback received in Hyderabad and will be published for public comment once completed. Communication channels with the GAC remain open regarding potentially overlapping work efforts. |
| **[Cross-Community Working Group on Internet Governance (CCWG-IG)](https://community.icann.org/pages/viewpage.action?pageId=43984275)**Co-Chairs: Rafik Dammak (GNSO), Jordan Carter (ccNSO), Olivier Crepin-Leblond (ALAC)GNSO Council Liaison: Carlos GutierrezStaff: A-R Inne, N. Hickson, R. DewulfThis CCWG was established by the participating SO/ACs to coordinate, facilitate, and increase the participation of the ICANN community in discussions and processes pertaining to Internet Governance.  | 2014-Oct-15 | Ongoing | CCWG | The GNSO Council adopted the charter ([https://community.icann.org/x/lQInAw)](https://community.icann.org/x/lQInAw%29) for this CCWG during ICANN51 in October 2014. The CCWG subsequently requested confirmation from its Chartering Organizations regarding a question of interpretation of its charter, which the GNSO Council agreed to at its May 2015 meeting ([https://gnso.icann.org/en/meetings/minutes-council-21may15-en.htm)](https://gnso.icann.org/en/meetings/minutes-council-21may15-en.htm%29). The CCWG co-chairs provided an update to the ccNSO and GNSO Councils at ICANN55 and ICANN56. At ICANN57 in Hyderabad in November 2016, a motion to withdraw GNSO support from the Charter was submitted for GNSO Council consideration. The Council decided to request that the CCWG propose refinements to its Charter before ICANN58 in March 2018, including consideration of alternative mechanisms to a CCWG for continuing its work. |

| **5 – Council Deliberation** |
| --- |
| **Description** | **Initiated** | **Target Date**  | **Who holdsToken** | **Pending action/status** |
| - none - |  |  |  |  |
|  |  |  |  |  |

| **6 – Board Vote** |
| --- |
| **Description** | **Initiated** | **Target Date**  | **Who holdsToken** | **Pending action/status** |
| **GNSO Review Working Group**Chair: Jennifer WolfeVice-Chair: Wolf-Ulrich KnobenCouncil Liaison: Rafik DammakStaff: J. Hedlund, M. KoningsThis WG was tasked to develop an implementation plan for the GNSO Review recommendations ([http://gnso.icann.org/en/drafts/review-feasibility-prioritization-25feb16-en.pdf)](http://gnso.icann.org/en/drafts/review-feasibility-prioritization-25feb16-en.pdf%29) which have been [adopted](https://www.icann.org/resources/board-material/resolutions-2016-06-25-en%22%20%5Cl%20%222.e) by the ICANN Board. | 2016-Jul-21 | ICANN57 | Council | The GNSO Council adopted the WG Charter ([http://gnso.icann.org/en/drafts/gnso-review-charter-11jul16-en.pdf)](http://gnso.icann.org/en/drafts/gnso-review-charter-11jul16-en.pdf%29) during its meeting on 21 July 2016. The Working Group delivered its proposed implementation plan for the Board-adopted GNSO Review recommendations to the GNSO Council on 21 November ([https://gnso.icann.org/en/drafts/review-implementation-recommendations-plan-21nov16-en.pdf)](https://gnso.icann.org/en/drafts/review-implementation-recommendations-plan-21nov16-en.pdf%29) The GNSO Council deferred voting on the issue to its meeting on 15 December to allow more time for deliberation, and a webinar on the topic was held on 08 December. On 15 December the GNSO Council unanimously approved the proposed plan. The Board’s Organizational Effectiveness Committee is reviewing the plan, which is expected to be on the agenda for consideration at the Board’s February 2017 meeting. |
| **[Protection of International Organization Names in All gTLDs](http://gnso.icann.org/en/group-activities/active/igo-ingo) PDP**Chair**:** Thomas RickertCouncil liaison: Keith DrazekStaff**:** M. Wong, S. Chan, B. CobbThis WG was tasked to to provide the GNSO Council with policy recommendations as to whether there is a need for special protections at the top and second level in all gTLDs for the names and acronyms of International Governmental Organizations (IGOs) and international non-governmental organizations (INGOs) receiving protections under treaties and statutes under multiple jurisdictions, specifically including the Red Cross/Red Crescent Movement (RCRC) and the International Olympic Committee (IOC).  | 2012-Apr-12 | 2014-Dec-11 | Board/Council/IRT | In April 2014 the Board voted to adopt those of the GNSO’s recommendations, approved unanimously by the GNSO Council in November 2013, that are not inconsistent with GAC advice received on the topic (<http://www.icann.org/en/groups/board/documents/resolutions-30apr14-en.htm#2.a)>. An Implementation Review Team (IRT) has been formed, led by Dennis Chang of GDD, to implement those recommendations adopted by the Board (See below in the “7 – Implementation” section for more details). The IRT is currently meeting regularly to finalize proposed text for a Consensus Policy on these adopted recommendations.As requested by the Board, in March 2014 the Board’s New gTLD Program Committee (NGPC) developed a proposal for dealing with the remaining recommendations, taking into account the GNSO’s recommendations and GAC advice. On 16 June 2014 the NGPC sent a letter to the GNSO Council requesting that the GNSO contemplate initiating a process to consider possible modifications to its remaining recommendations, per the PDP Manual ([https://gnso.icann.org/en/correspondence/chalaby-to-robinson-16jun14-en.pdf)](https://gnso.icann.org/en/correspondence/chalaby-to-robinson-16jun14-en.pdf%29). Following a discussion with Chris Disspain, the Council sent a letter (<http://gnso.icann.org/en/correspondence/robinson-to-chalaby-disspain-07oct14-en.pdf>) on 7 Oct 2014 to the NGPC seeking confirmation and input about the most appropriate forms of protection for IGO acronyms and Red Cross names. Through various resolutions passed in 2013 (see e.g. <https://www.icann.org/resources/board-material/resolutions-new-gtld-2013-07-17-en#1.a)>, the Board resolved to temporarily reserve the Red Cross National Society names at issue as well as the names and acronyms of the IGOs that appear on the list provided by the GAC to ICANN in March 2013 until the differences between the GNSO recommendations and the GAC advice have been reconciled. GDD Staff has been working on implementing this resolution. The NGPC responded to the Council on 15 January 2015 noting that discussions are ongoing ([https://gnso.icann.org/en/correspondence/chalaby-to-robinson-15jan15-en.pdf)](https://gnso.icann.org/en/correspondence/chalaby-to-robinson-15jan15-en.pdf%29). A small group of IGO, GAC and NGPC representatives was formed in late 2014 to develop a final proposal concerning IGO acronyms for the GAC’s and GNSO’s consideration. The IGO Small Group Proposal was forwarded by the Board to the Council on 6 October 2016 (see [https://gnso.icann.org/en/correspondence/crocker-icann-board-to-council-chairs-04oct16-en.pdf)](https://gnso.icann.org/en/correspondence/crocker-icann-board-to-council-chairs-04oct16-en.pdf%29) with a request that the GNSO Council consider the proposal.Representatives from the Red Cross provided a briefing to the Council during the Council’s April 2016 meeting. On 31 May, the Council sent a further letter to the Board requesting updated Board input on the remaining Red Cross names and IGO acronyms (see [https://gnso.icann.org/en/correspondence/council-chairs-to-crocker-icann-board-06jun16-en.pdf)](https://gnso.icann.org/en/correspondence/council-chairs-to-crocker-icann-board-06jun16-en.pdf%29). It also discussed the matter of Red Cross and IGO acronyms protection with Board members during ICANN56 in Helsinki in June. On 27 October 2016 a call (see [http://tinyurl.com/hubz9qo)](http://tinyurl.com/hubz9qo%29) was held among Board, GAC and GNSO representatives on this topic, to discuss next steps. Further discussions took place at Hyderabad in November. Following a further call held on 20 December 2016 among Board, GAC and GNSO leadership, the Council will now consider a Board suggestion for a facilitated dialogue between the GAC and the GNSO to resolve the outstanding issues. |
| **[Geo Regions Review Community-wide Working Group](https://community.icann.org/display/georegionwg/Home%2BPage%2Bof%2BGeographic%2BRegions%2BReview%2BWorking%2BGroup)**Chair: Cheryl Langdon-Orr (ccNSO/APRALO)GNSO Council Reps: Staff: R. HoggarthThis Board-chartered cross community WG has consulted with ICANN stakeholders regarding the definition and applications of ICANN’s Geographic Regions.  | 2008-Aug-07 | TBC | Board | A community Public Comment opportunity has been established for this matter (see <https://www.icann.org/public-comments/geo-regions-2015-12-23-en>. The comment period closed on 24 April 2016 and 7 submissions were received. The staff report of public comments was published ([https://www.icann.org/en/system/files/files/report-comments-geo-regions-13may16-en.pdf)](https://www.icann.org/en/system/files/files/report-comments-geo-regions-13may16-en.pdf%29) and the Board will now review the comments received and consider next steps. |

| **7 – Implementation** |
| --- |
| **Description** | **Initiated** | **Target Date**  | **Who holdsToken** | **Pending action/status** |
| **[GNSO Rights & Obligations under Revised ICANN Bylaws Drafting Team](https://community.icann.org/x/yhCsAw) (DT) Recommendations**Chair: Steve DelBiancoVice-Chair: Amr ElsadrStaff: M. Wong, J. Hedlund, M. KoningsThis DT was created to work with ICANN staff to identify the GNSO’s new rights and obligations under the revised ICANN Bylaws, and to prepare an implementation plan for the GNSO Council’s consideration. | 2016-Jun-30 | Late 2016 | Staff/DT/Council | On 27 May 2016 the ICANN Board adopted a set of new ICANN Bylaws that reflect changes needed to implement the IANA Stewardship Transition Proposal. The revised Bylaws include new and additional rights and obligations for the GNSO. As changes to the GNSO’s Operating Procedures and applicable Bylaws may be needed to accommodate these new roles, including the participation of the GNSO in the newly created Empowered Community, the GNSO Council created this DT on 30 June 2016 to identify the GNSO’s new rights and obligations, and work with ICANN staff to prepare an implementation plan to address any needed changes by 30 September (<http://gnso.icann.org/en/council/resolutions#201606)>. Following GNSO Council approval for an extension of time, the DT delivered its final report on 12 October 2016 (see <https://gnso.icann.org/en/drafts/bylaws-drafting-team-final-report-12oct16-en.pdf>, with minority statements available at [https://gnso.icann.org/en/drafts/bylaws-drafting-team-minority-report-10oct16-en.pdf)](https://gnso.icann.org/en/drafts/bylaws-drafting-team-minority-report-10oct16-en.pdf%29). On 13 October, the GNSO Council agreed to defer consideration of the motion to approve the DT’s report to its meeting at ICANN57 in Hyderabad in November, where it agreed to further defer consideration to its meeting on 1 December 2016. At its 1 December meeting the GNSO Council voted unanimously to approve a motion to accept the report and directed staff to begin implementation. Staff is currently working on developing a proposal for implementation. |
| **Recommendations from the [GAC-GNSO Consultation Group (CG) on GAC Early Engagement in GNSO PDP](https://community.icann.org/x/phPRAg)s**Co-Chairs: Jonathan Robinson (GNSO) and Manal Ismail (GAC)Staff: M. Konings, O. NordlingThe Governmental Advisory Committee (GAC) and the GNSO jointly established a consultation group to explore ways for the GAC to engage early in the GNSO Policy Development Process and to improve overall cooperation between the two bodies (for example, by exploring the option of a liaison). | 2014-Jan-07 | ICANN58 | Staff | The launch of this GAC-GNSO Consultation Group on Early Engagement was the result of discussions between the two entities at several ICANN meetings, including in Buenos Aires in November 2013, reflecting a joint desire to explore and enhance ways of early engagement by the GAC in GNSO policy development activities. The issue was also specifically called-out by both Accountability and Transparency Review Teams (ATRT). The GNSO Council recently confirmed that the position of GNSO Liaison to the GAC, created as a result of the work of the CG on a pilot basis, should be made a permanent role. At ICANN56 in Helsinki in June, the CG shared the results of the survey which was held to obtain further input from the GNSO as well as GAC on the review of the Quick Look Mechanism as well as other opportunities for early engagement of the GAC in the GNSO PDP. The CG submitted its final status report and recommendations to the GNSO and GAC for their consideration at ICANN57 in Hyderabad in November. With the adoption of the recommendations, the CG considers its work complete. Staff is working in conjunction with the GAC and GNSO leadership teams on the implementation of the recommendations.  |
| **[Privacy & Proxy Services Accreditation Issues PDP Recommendations](https://community.icann.org/pages/viewpage.action?pageId=43983094)** Council Liaison: Darcy SouthwellIRT Support Staff: Amy Bivins The *Registrar Accreditation Agreement* (RAA), the contract governing the relationship between ICANN and accredited registrars, has been in place since 2001. The Board initiated negotiations for a new RAA in October 2011, and requested an Issue Report from the GNSO at the same time. The final version of the new RAA was approved by the Board in June 2013, thereby signifying that the RAA negotiations were concluded. Per the Board’s 2011 request, the remaining issues, which were identified as those relating to privacy & proxy services and their accreditation, were examined in a PDP. This IRT was formed to implement the PDP recommendations approved by the ICANN Board. | 2009-May-21 | Ongoing | Staff/IRT | The WG’s Final Report was sent to the GNSO Council on 8 December 2015 and in January 2016, the GNSO Council voted unanimously to approve all the WG’s final recommendations (<https://gnso.icann.org/en/council/resolutions#201601)>. At its May 2016 meeting, at which the Board acknowledged receipt of the PDP recommendations and requested additional time to consider, to allow for possible timely GAC input. The GAC issued advice via its Helsinki Communique requesting that its concerns be addressed during implementation to the extent feasible. On 9 August 2016, the Board adopted the PDP recommendations (<https://www.icann.org/resources/board-material/resolutions-2016-08-09-en#2.e)>. An IRT was formed and is being led by Amy Bivins of GDD.The IRT will begin reviewing draft policy language when it reconvenes in January 2017. In addition, a subgroup has been formed to review a proposed framework to be developed by the GAC's Public Safety Working Group (PSWG) in relation to privacy and proxy services' handling of law enforcement requests (the goal is to have a document ready to review before ICANN58 in March). The IRT has requested that staff deliver a proposal to compress the project timeline to align with the new 1 January 2018 expiration date of the 2013 RAA specification on privacy and proxy registrations. This was submitted to the IRT on 3 January 2017 for its review. |
| **[Translation/Transliteration of Internationalized Registration Data PDP](https://community.icann.org/display/tatcipdp/Translation%2Band%2BTransliteration%2Bof%2BContact%2BInformation%2BPDP%2BHome) Recommendations**Council Liaison: Amr ElsadrIRT Support Staff: Brian Aitchison The PDP addressed two primary issues: 1. Whether it is desirable to translate contact information to a single common language or transliterate contact information to a single common script; and
2. Who should bear the burden translating contact information to a single common language or transliterating contact information to a single common script?

This IRT was formed to implement the final PDP recommendations as approved by the ICANN Board. | 2012-Oct-17 | Ongoing | Staff/IRT | On 28 September 2015 the ICANN Board approved the adoption of all seven recommendations contained in the Final Report from the PDP Working Group ([https://www.icann.org/resources/board-material/resolutions-2015-09-28-en)](https://www.icann.org/resources/board-material/resolutions-2015-09-28-en%29). An Implementation Review Team (IRT) was formed and a draft implementation plan shared with the IRT, which met for its first meeting on 19 July 2016. As of November 2016, the IRT is engaged in discussions around language and script tags, which appear to be a minimum requirement to meet the standards set by the PDP recommendations.The timeline for the implementation of the PDP recommendations has been extended into 2018 as a result of emerging complexities relating to the implementation. A tentative implementation announcement is currently scheduled for August 2017—with a tentative policy effective date of 1 February 2018—pending further discussion with the IRT. However, this timeline is dependent on the roll-out of the new Registration Data Access Protocol (RDAP). |
| **Inter-Registrar Transfer Policy (IRTP) Part C Recommendations** Council Liaison: Rubens KuhlIRT Support Staff: Caitlin TubergenThe Inter‐Registrar Transfer Policy (IRTP) is a consensus policy adopted in 2004 to provide a straightforward procedure for domain name holders to transfer domain names between registrars. An overall review of this policy identified areas that require clarification or improvement. Because the initial review identified a wide range of issues related to transferring domain names, the issues were categorized into subsets. This project relates to implementation of the “Part C” issues. | 17 Oct 2012 | 1 Sept 2015 | Board / Staff | The ICANN Board adopted the IRTP Part C recommendations at its meeting in December 2012 (<https://www.icann.org/en/groups/board/documents/resolutions-20dec12-en.htm#2.a>). An IRT was formed and consulted on the Change of Registrant draft policy language. The draft policy was posted for public comment on 30 March 2015. Following IRT review of the comments received, the updated Transfer Policy was announced on 24 September 2015 (<https://www.icann.org/news/announcement-2-2015-09-24-en>). Following community feedback, an updated version of the Transfer Policy was announced on 1 June 2016 ([https://www.icann.org/news/announcement-2016-06-01-en)](https://www.icann.org/news/announcement-2016-06-01-en%29). The updated version of the Transfer Policy was effective 1 December 2016.At the request of the Registrars’ Stakeholder Group, which raised a substantive concern regarding the application of IRTP-C to privacy and proxy services, the GNSO Council wrote to the ICANN Board to recommend that the matter be referred to the PPSAI IRT for consideration before the Policy effective date ([https://gnso.icann.org/en/correspondence/bladel-to-crocker-01dec16-en.pdf)](https://gnso.icann.org/en/correspondence/bladel-to-crocker-01dec16-en.pdf%29). The Board responded on 21 December 2016 to note that it is reviewing the Council’s request and in the interim directing that ICANN Compliance defer enforcement of the issue ([https://gnso.icann.org/en/correspondence/crocker-to-bladel-21dec16-en.pdf)](https://gnso.icann.org/en/correspondence/crocker-to-bladel-21dec16-en.pdf%29).  |
| **Thick WHOIS PDP Recommendations**Council Liaison: Amr ElsadrIRT Support Staff: Dennis ChangThis IRT was formed to work with ICANN staff on the implementation of the GNSO’s policy recommendation to require Thick Whois for all gTLD registries, as approved by the ICANN Board.  | 2012-Mar-14 | Ongoing | IRT / Staff / Council | The ICANN Board approved the GNSO recommendations on Thick Whois at its meeting on 7 February 2014 (<http://www.icann.org/en/groups/board/documents/resolutions-07feb14-en.htm>). An IRT was formed and various impact assessments and implementation proposals have been discussed with the IRT in the two decoupled work streams, corresponding to the two expected outcomes in the PDP Recommendations: transition from thin to thick for .COM, .NET and .JOBS; and the consistent labeling and display of Whois output for all gTLDs as per Specification 3 of the 2013 RAA. Following IRT review and formal public comment, the first outcome was published as a Consensus Policy for Registry Registration Data Directory Services Consistent Labelling and Display Policy on 26 July 2016 with a required implementation date of 1 February 2017. However, due to a Request for Reconsideration related to the inclusion of a requirement in the Consensus Policy to implement the new RDAP, the policy was rescinded, modified to remove the RDAP requirement, then re-published for public comment. The policy effective date is expected to be established in the first quarter of 2017.For the Thin to Thick transition, the implementation plan has been developed as a separate work track and also published for public comment. The policy effective date for this policy is also expected to be established in the first quarter of 2017.Regarding the transition from thin to thick for .COM, .NET and .JOBS, in June 2015, ICANN’s General Counsel’s Office, released to the IRT a Legal Review Memorandum per the GNSO Council’s recommendation. ICANN staff is currently engaging with experts from affected parties to identify an implementation path. Additionally, the IRT recently raised concerns regarding privacy issues that were not anticipated by the PDP Working Group. On 15 December 2016, the IRT notified the GNSO Council of these issues so that appropriate action can be taken ([https://gnso.icann.org/en/correspondence/irt-to-gnso-council-15dec16-en.pdf)](https://gnso.icann.org/en/correspondence/irt-to-gnso-council-15dec16-en.pdf%29). The Council will discuss these issues at its next meeting on 19 January 2017.  |
| **Protection of International Organization Names in All gTLDs** Council Liaison: Keith DrazekIRT Support Staff: Dennis ChangThis IRT was formed to work with ICANN staff to adopt those of the GNSO’s recommendations to protect certain identifiers of IGO & INGO Organizations in all gTLD registries that were approved by the ICANN Board in April 2014. | 2012-Apr-12 | Ongoing | Staff/IRT  | In April 2014 the Board voted to adopt those of the GNSO’s PDP recommendations that are not inconsistent with GAC advice received on the topic (<http://www.icann.org/en/groups/board/documents/resolutions-30apr14-en.htm#2.a)>. An IRT was formed to implement those recommendations adopted by the Board.To date, ICANN staff has been working on building comprehensive and actionable lists of all the identifiers to be protected as well as draft procedures for eventual implementation of relevant protections, i.e. reservations at the top and second levels and related exception procedures. Staff, in collaboration with the IRT, is progressively building a Draft Consensus Policy document. This document serves to support the continuing development of the implementation plan. The IRT is continuing to discuss finalizing the draft Consensus Policy language. |

| **Other** |
| --- |
| **Description** | **Initiated** | **Target Date**  | **Who holdsToken** | **Pending action/status** |
| **[Consumer Choice Competition and Trust Review Team](https://community.icann.org/display/CCT/Competition%2C%2BConsumer%2BTrust%2Band%2BConsumer%2BChoice)**Chair**:** Jonathan ZuckStaff**:** Eleeza Agopian, Margie Milam, Brian AitchisonThis Review Team was formed to examine the extent to which the introduction or expansion of gTLDs has promoted competition, consumer trust and consumer choice. It will also assess the effectiveness of the application and evaluation processes, as well as the safeguards put in place by ICANN to mitigate issues involved in the introduction or expansion of new gTLDs. | 2015-Feb-12 | 2017-Mar-31 | Review Team | Under the [Affirmation of Commitments (AoC),](https://www.icann.org/resources/pages/affirmation-of-commitments-2009-09-30-en) ICANN is committed to ensuring that, as it contemplates expanding the top-level domain space, the various issues that are involved will be adequately addressed prior to implementation. These include issues such as competition, consumer protection, security, stability and resiliency, malicious abuse issues, sovereignty concerns, and rights protection. The AoC also requires ICANN to convene a community-driven review team to examine the extent to which the introduction or expansion of gTLDs has promoted competition, consumer trust and consumer choice, as well as the effectiveness of:* The application and evaluation process
* Safeguards put in place to mitigate issues involved in the introduction or expansion

The Competition, Consumer Trust and Consumer Choice (CCT-RT) was formed in November 2015. The CCT-RT hosted several sessions and group updates at ICANN57 in Hyderabad in November 2016. An update on its work can be found [here](https://www.icann.org/news/blog/new-gtlds-competition-consumer-trust-consumer-choice-review-interim-findings-next-steps).  |
| **[Cross-Community Working Group- on a Framework of CWG Principles](https://community.icann.org/x/rQbPAQ)**GNSO Council Co-Chair: John BerardccNSO Council Co-Chair: Becky BurrStaff: M. Wong, B. Boswinkel, S. ChanThis CCWG was chartered by the ccNSO and GNSO Councils to develop a set of uniform guidelines (based on earlier work by the GNSO, feedback from the ccNSO and community experience from past CCWGs) for the formation, operation and termination of future CCWGs. Its Final Framework, as approved by the ccNSO and GNSO Councils, is intended to serve as a guide to the community for all future CCWGs that are proposed. | 2011-May-19 | Completed | Staff | This CCWG was chartered by both the ccNSO and GNSO Councils in March 2014. It reviewed the processes and outcomes of selected prior CWGs, including mapping their charters to the typical WG life cycle (Initiation, Formation, Operation, Closure, Post-Closure), and published a draft framework for public comment on 22 February 2016. A final proposed framework based on public comments received was drafted and presented for community deliberation at ICANN56 in Helsinki in June 2016. Following review of the public and community comments received, the CCWG completed its Final Framework and sent it to both the Chartering Organizations for their review and action ([https://community.icann.org/x/4CiOAw)](https://community.icann.org/x/4CiOAw%29). The GNSO Council approved the Final Framework on 13 October 2016 and the ccNSO Council also approved it during its meeting at ICANN57 in November 2016. The Framework will now be sent to all other ICANN SO/ACs, with the recommendation that it be used to guide the community’s discussions for all future CCWGs. |