CWG Draft Timeline

16 September 2014

| Target Date – Week of | What | Deliverable / Topic for Discussion | Who |
| --- | --- | --- | --- |
| 29 September | First CWG Meeting | Introductions Review Charter Identify / confirm required reading materials Discuss next steps in relation to development of work plan Plan for F2F meeting in LA | CWG |
| 6 October | CWG Meeting | Discuss work plan and required elements Consider assigning each required element of work plan to individual / subteam to develop proposal for CWG review Finalize agenda for F2F meeting in LA | CWG |
| 13 October | CWG F2F Meeting | Finalize work plan Commence deliberations | CWG |
| 20 October | CWG Meeting | Continue deliberations | CWG |
| 27 October | CWG Meeting | Continue deliberations | CWG |
| 3 November | CWG Meeting | Continue deliberations | CWG |
| 10 November | Publish Draft Transition Proposal for public comment (21 + 21 days) | Publish Draft Transition Proposal for public comment and submit to chartering organizations for consideration | CWG |
| 17 November | CWG Meeting | Start review of comments received |  |
| 22 December | CWG Meeting | Continue review of comments received | CWG |
| 29 December | CWG Meeting | Update Draft Transition Proposal as deemed appropriate | CWG |
| 5 January | CWG | Finalize Transition Proposal and submit to Chartering Organizations | CWG |
| 15 January | CWG | Submission of Final Transition Proposal to CWG | CWG |