CWG Draft Timeline

Updated 7 October 2014

| Target Date – Week of | What | Deliverable / Topic for Discussion | Who |
| --- | --- | --- | --- |
| 6 October | CWG Meeting | Introductions Review Charter Identify / confirm required reading materials Discuss next steps in relation to development of work plan Plan for F2F meeting in LA Finalize agenda for F2F meeting in LA | CWG |
| 13 October | CWG F2F Meeting | Discuss work plan and required elements Consider assigning each required element of work plan to individual / subteam to develop proposal for CWG review | CWG |
| 20 October | CWG Meeting(s) | Continue deliberations | CWG |
| 27 October | CWG Meeting(s) | Continue deliberations | CWG |
| 3 November | CWG Meeting(s) | Continue deliberations | CWG |
| 10 November | CWG Meeting(s) | Continue deliberations | CWG |
| 17 November | CWG Meeting(s) | Continue deliberations | CWG |
| 24 November | CWG Meeting(s) | Continue deliberations | CWG |
| 1 December | Publish Draft Transition Proposal for public comment (21) | Publish Draft Transition Proposal for public comment and submit to chartering organizations for consideration | CWG |
| 1 December | CWG Meeting(s) Webinars | Webinars to inform ICANN Community about Draft Transition Proposal and solicit / encourage input | CWG |
| 8 December | CWG Meeting(s) | Review input received during webinars and possible public comments submitted |  |
| 15 December | CWG Meeting(s) | Continue review of input received and public comments received | CWG |
| 22 December | Close of public comment forum | Summary report of public comments received | Staff / CWG |
| 29 December | CWG Meeting(s) | Continue review of input received and public comments received | CWG |
| 5 January | CWG Meeting(s) | Update Draft Transition Proposal as deemed appropriate | CWG |
| 12 January | CWG Meeting(s) | Review updated draft transition proposal |  |
| 19 January | CWG Meeting | Finalize Transition Proposal and submit to Chartering Organizations | CWG |
| 20-30 January | Consideration of Final Transition Proposal by Chartering Organizations | Adoption by chartering organizations of final transition proposal | GNSO Council, ccNSO Council, SSAC, ALAC, GAC |
| 31 January | Submission of Final Transition Proposal to ICG | Submission of Final Transition Proposal to ICG |  |