**Draft Timeline – new gTLD Auction Proceeds Drafting Team**

|  |  |  |  |
| --- | --- | --- | --- |
| **Option 1 - Date** | **Action** | **Option 2 – Date** | **Action** |
| Week of 11 July | DT Meeting | Week of 11 July | DT Meeting |
| Week of 25 July | DT Meeting | Week of 25 July | DT Meeting |
| Week of 8 August | DT Meeting | Week of 8 August | DT Meeting |
| Week of 15 August | Distribute Charter to ICANN SO/ACs to identify whether there are any pertinent issues that would prevent adoption of the charter | Week of 15 August | Distribute Charter to ICANN SO/ACs to identify whether there are any pertinent issues that would prevent adoption of the charter |
| Week of 12 September | Deadline for feedback on proposed charter | Week of 12 September | Deadline for feedback on proposed charter |
| 19 September | DT confirmation that no pertinent issues have been identified by ICANN SO/ACs | 19 September | DT confirmation that pertinent issues have been identified by ICANN SO/ACs |
| 19 – 30 September | Consideration of charter for approval by Chartering Organizations | 19 Sept – 15 October  (pertinent issues identified) | DT review of feedback received and rework of charter |
| 1 – 15 October | Call for volunteers for CCWG | 15 October | Submission of final charter to chartering organizations |
| ICANN57 | First meeting of CCWG | ICANN57 | Approval of charter by Chartering Organizations |