**Proposed Timeline for GAC-GNSO Consultation Group on Early Engagement**

| **When** | **What** | **Proposed Topics to be covered**  **Day-to-Day Work Stream** | **Proposed Topics to be covered**  **PDP Work Stream** | **Who** |
| --- | --- | --- | --- | --- |
| 29 April 2014 & on the mailing list | CG Meeting | * Review / confirm expectations of day-to-day co-operation as currently outlined in Mechanism for day to day cooperation (dated 18 Feb) * Review options to be considered. Are there any missing? * Provide input on whether any information is missing / requiring updating on pages 2-8 * Brainstorm on pros/cons, if time allows | * Confirm how to proceed – work through questions identified in table or use PPT presentation developed by Mikey * If former, start walking through each step of the PDP, review current method of seeking input – brainstorm possible improvements and/or additional steps desirable. | All |
| Week of 5 May | Team Leads meet | Incorporate feedback received during previous meeting in document. Prepare items for discussion during next meeting. | Incorporate feedback received during previous meeting in document. Prepare items for discussion during next meeting. | Team leads & staff support |
| 13 May 2014 & on the mailing list | CG Meeting | * Review / confirm updates made to document based on discussion of previous meeting * Continue brainstorm on pros/cons | * Review / confirm updates made to document based on discussion of previous meeting * Continue walk through of PDP, review current method of seeking input - brainstorm possible improvements and/or additional steps desirable. | All |
| Week of 19 May | Team Leads meet | Incorporate feedback received during previous meeting in document. Prepare items for discussion during next meeting. | Incorporate feedback received during previous meeting in document. Prepare items for discussion during next meeting. | Team leads & staff support |
| 27 May 2014 & on the mailing list | CG Meeting | * Review / confirm updates made to document based on discussion of previous meeting * Continue brainstorm on pros/cons | * Review / confirm updates made to document based on discussion of previous meeting * Continue walk through of PDP, review current method of seeking input - brainstorm possible improvements and/or additional steps desirable. | All |
| Week of 2 June | Team Leads meet | Incorporate feedback received during previous meeting in document. Prepare items for discussion during next meeting.  Develop draft recommendations | Incorporate feedback received during previous meeting in document. Prepare items for discussion during next meeting.  Develop draft recommendations | Team leads & staff support |
| 10 June 2014 & on the mailing list | CG Meeting | * Review / confirm updates made to document based on discussion of previous meeting * Continue brainstorm on pros/cons * Review draft recommendations | * Review / confirm updates made to document based on discussion of previous meeting * Continue walk through of PDP, review current method of seeking input - brainstorm possible improvements and/or additional steps desirable. * Review draft recommendations | All |
| Between 11 – 16 June | Team Leads meet | Incorporate feedback received during previous meeting in document.  Update draft recommendations  Develop proposed presentation for ICANN meeting in London | Incorporate feedback received during previous meeting in document.  Update draft recommendations  Develop proposed presentation for ICANN meeting in London | Team leads & staff support |
| 17 June 2014 & on the mailing list | CG Meeting | Review proposed recommendations  Review proposed presentation for ICANN meeting in London | Review proposed recommendations  Review proposed presentation for ICANN meeting in London | All |
| 22 June 2014 | GAC-GNSO Joint Meeting | Present status update, including proposed recommendations under consideration | Present status update, including proposed recommendations under consideration | All |
| 22 June 2014 | Informal GAC-GNSO CG Gathering | Review feedback received during GAC-GNSO Joint Meeting & determine next steps | | All |