## Slide 1: GAC-GNSO Consultation Group On GAC Early Engagement in GNSO PDP
Los Angeles Progress Report
12 October 2014

## Slide 2: Overview
Background
Work Track 1 – Regular Interaction Includes GNSO Liaison to the GAC
Work Track 2 – Engagement with GNSO PDP
Early Awareness & Notifications Includes output from Survey of GAC
Look Ahead
Questions & Discussion

## Slide 3: Background
GAC-GNSO Consultation Group (CG)
To address GAC early engagement in GNSO Policy Development Process (PDP)
Early engagement identified by both Accountability and Transparency Review Teams (ATRT1 Rec. 12, ATRT2 Rec. 10.2)
Group commenced work Q1 2014
Two work tracks - Day-to-day co-ordination - PDP engagement

## Slide 4: Work Track I (Team 1)
Mechanisms for day-to-day ongoing cooperation
First recommendation implemented as pilot project for FY2015: GNSO Liaison to the GAC
Focus is now on:
  GAC / GNSO Chairs regular interaction
  Rethinking recurring joint meetings
  Early awareness & notification

## Slide 5: GNSO Liaison to the GAC
Mason Cole appointed as GNSO liaison to the GAC
Pilot implemented for one year starting ICANN 51 LA meeting
Coordination mechanism evaluated after one year
Notes: <number>

## Slide 6: Place Holder for
A couple of slides by Mason

## Slide 7: GNSO Liaison to the GAC
Action 1 for ICANN51
Ensure mutual understanding of role of GNSO liaison to the GAC
Seek to obtain GAC and GNSO feedback on:
  Opportunities provided by having a GNSO liaison to the GAC
  …

## Slide 8: A. GAC/GNSO Chairs Regular Interaction
Proposed approach: Regular calls between GAC and GNSO Chairs, as well as GNSO liaison as appropriate
As deemed necessary, regular calls may include:
  GAC vice chairs
  GAC topic leads
  GNSO issue/PDP leads

## Slide 9: A. GAC/GNSO Chairs Regular Interaction
Action 2 for ICANN51 Seek to obtain GAC and GNSO feedback on:
  The suggested approach
  Suggested frequency of calls?
  …

## Slide 10: B. Rethinking Recurring Joint Meetings
Identify ahead of time topics of mutual interest
Provide updates on status of PDP WGs ahead of time (e.g. webinar?)
Focus meetings on identified questions / concerns
Share identified questions / concerns with GNSO liaison in advance to facilitate f2f meeting discussion
Invite GNSO topic leads as necessary
Provide new members with short overviews (for example one-pager)

## Slide 11: B. Rethinking Recurring Joint Meetings
Action 3 for ICANN51 Seek to obtain GAC and GNSO feedback on:
  The suggested approach
  …

## Slide 12: C. Early Awareness/Notifications
Results of on-line survey for GAC members => 29 responses
Mechanisms evaluated, in terms of awareness, usefulness and suggestions for improvement:
  Policy Update – monthly
  GAC Early Engagement Policy Documents – monthly
  Policy Update Webinar (takes place prior to every ICANN meeting) – 3 times/year
  Requests for input from GNSO PDP Working Groups – ongoing basis
  Participation in GNSO Working Groups – ongoing basis
  Announcements from GNSO Secretariat – ongoing basis
  GNSO Background Briefings (e.g.) – issued just prior to each ICANN meeting

## Slide 13: C. Early Awareness/Notifications
Challenges mentioned in the survey include:
  Volume of activities
  Number of simultaneous PDPs
  Timeline
  Lack of both understanding and/or ability to participate in GNSO working groups
  Frequency of GNSO working group meetings (some twice a week for months, others every two weeks) makes it difficult for bureaucrats to participate

## Slide 14: C. Early Awareness/Notifications
Suggestions mentioned in the survey include:
  Highlight Public Policy aspect of a given issue
  Indicate relationship between a policy initiative and existing GAC advice
  More frequent policy updates
  Direct engagement with and follow-up with the GAC, GAC Executive and Secretariat
  Make clear what stage the GNSO work is in, which relates to the issue of knowing when/how to contribute
  Regular feedback on outcome of PDP process, including a summary of previous processes
  More inter-committee relationships

## Slide 15: C. Early Awareness/Notifications
Suggestions mentioned in the survey include:
  A home page quick link directly to "Main Policy Activities“
  Highlighting policy activities which require liaison with and significant inputs from the GAC and expected potential degree of interest - e.g. GAC should be aware / discussion with GAC expected / requires GAC public policy input
  GAC website mirror this description of cross-community policy interest and provide links to the GNSO summaries

## Slide 16: C. Early Awareness/Notifications
Action 4 for ICANN51 Seek to obtain GAC and GNSO feedback on / approval for:
  …

## Slide 17: Work Track II (Team 2)
GAC early engagement in GNSO PDP
Look at 6 phases of the current GNSO PDP
  Issue Scoping
  Initiation
  Working Group
  Council Deliberations
  Board Vote
  Implementation
Initial focus on early phases i.e. 1 & 2

## Slide 18: Issue Scoping – Existing & Possible new Engagement Opportunities

## Slide 19: Ideas being explored
Streamlining and prioritizing early awareness & notification
GAC ‘Quick look’ mechanism; establish whether issue has potential public policy implications, flag as such at early stage
Additional support to allow GAC to provide timely input
Ensure that any GAC positions / advice are included in the Preliminary Issue Report
GAC could consider creation of Triage committee

## Slide 20: Looking ahead
Consultation Group to review input received in Los Angeles (Open F2F meeting from 18h30 – 19h30 in Constellation)
Continue implementation of pilot project for the GNSO Liaison to the GAC
Further develop recommendations for other items aiming to present for GAC / GNSO review / approval at ICANN 52

## Slide 21: Questions & Discussion