Updated Timeline and deadlines

| **Date** | **What** | **Topic** |
| --- | --- | --- |
| 5 December 2019 | EPDP- Phase 2 call #33 | Authorization Provider |
| 8 December 2019 | Deadline for comments and suggestions | Initial Report language on:* Terms of use
* Automation
 |
| 10 December 2019  | EPDP- Phase 2 call #34 | Address comments / suggestions received by deadline on:* Terms of use
* Automation
 |
| 10 December 2019 | Deadline for comments and suggestions | Updated language for:* Response requirements

Initial Report language on:* User groups
 |
| 12 December 2019  | EPDP- Phase 2 call #35 | Address comments / suggestions received by deadline on:* Response requirements
* User groups
 |
| 17 December 2019 | Legal Committee call #11 | * Continued review of Priority 2 issues
 |
| 17 December 2019 | Deadline for comments and suggestions | Initial Report language on:* Purposes
* Acceptable Use Policy
 |
| 19 December 2019  | EPDP- Phase 2 call #36 | Address comments / suggestions received by deadline on:* Purposes
* Acceptable Use Policy
 |
| 7 January 2020 | Legal Committee Call #12 | * Continued review of Priority 2 issues
 |
| 7 January 2020 | Deadline for comments and suggestions | Initial Report (apart from preliminary recommendations already addressed)Initial Report language on:* Financial sustainability
* Audits
 |
| 9 January 2020  | EPDP- Phase 2 call #37 | Address comments / suggestions received by deadline on:* Financial sustainability
* Audits
 |
| 14 January 2020  | EPDP- Phase 2 call #38 | Initial Report issues identified |
| 16 January 2020  | EPDP- Phase 2 call #39 | Initial Report issues identified |
| 23 January 2020  | EPDP- Phase 2 call #40 | Initial Report issues identified |
| 27-29 January 2020  | Phase 2 F2F | Finalize Initial Report and preliminary recommendationsConsider priority 2 items |
| 7 February 2020  | LAUNCH PCP - Initial Report |  |