**Proposed work plan – priority 2 items and phase 1 remaining issues**

*4 March 2020*

| **Date** | **What** | **Topic** |
| --- | --- | --- |
| ~~18 February 2020~~ | ~~Legal Committee Meeting~~ | * ~~Consider EPDP Team input & finalize priority 2 questions for submission to legal counsel~~

[**~~Feasibility of unique contacts to have a uniform anonymized email address~~**](https://docs.google.com/document/d/1meyuNRsq4sMOI6pefJk4jZevaKUsTkVf8_XyW1tRaiA/edit)~~(priority 2)~~* ~~EPDP Legal Committee to review legal guidance and make recommendation for next steps to EPDP Team.~~
 |
| ~~20 February 2020~~ | ~~EPDP Team Meeting~~ | [**~~Display of information of affiliated vs. accredited privacy / proxy providers~~**](https://docs.google.com/document/d/1izpX2C-RrfAdRgRDwBO9tQuJIBA9Xt38p1MTJgQNDGI/edit)~~(priority 2)~~* ~~EPDP Team to review ICANN Org feedback and consider Support Staff proposed recommendation~~
 |
| ~~25 February 2020~~ | ~~Automation Use Cases Small Team~~  | * ~~Small team to further review and consider possible automation use cases (priority 1 – SSAD)~~
 |
| ~~27 February 2020~~ | ~~EPDP Team Meeting~~ | [**~~Data retention~~**](https://docs.google.com/document/d/1xlw1N7omlgPKjag_FnOy03NRvByol8IaJma5zNPkWaY/edit?usp=sharing)~~(priority 2)~~* ~~EPDP to review ICANN Org feedback and consider whether updates are needed to phase 1 data retention recommendation.~~
* ~~At a minimum, the EPDP Team would need to reconfirm its original recommendation, which was adopted on an interim basis, that registration data must be retained for a period of fifteen months following the life of the registration plus three months to implement the deletion, i.e., 18 months.~~
 |
| ~~3 March 2020~~ | ~~Legal Committee Meeting~~ | [**~~City field redaction~~**](https://docs.google.com/document/d/1rdtRLaNm5DiWR_EPei4Oi64FaDauIXEQhnF2Lm_NxbI/edit)~~(priority 2)~~* ~~Legal committee to review and analyze legal advice received on this topic and recommend next steps to the EPDP Team, which could include modification of the phase 1 recommendation, maintaining phase 1 recommendation as is, and/or additional legal guidance to help inform a determination on whether or not the recommendation should be modified.~~
 |
| 5 March 2020 | EPDP Team Meeting | [**Feasibility of unique contacts to have a uniform anonymized email address**](https://docs.google.com/document/d/1meyuNRsq4sMOI6pefJk4jZevaKUsTkVf8_XyW1tRaiA/edit)(priority 2)* Consider legal committee recommendation

[**City field redaction**](https://docs.google.com/document/d/1rdtRLaNm5DiWR_EPei4Oi64FaDauIXEQhnF2Lm_NxbI/edit)(priority 2)* Consider legal committee recommendation

[**Potential OCTO Purpose**](https://docs.google.com/document/d/174PSGgWB-UTTcqIA-NndIVDkP6WR701tzwjDsozVRXM/edit) (priority 2)* Consider org input
 |
| 10 March 2020 | Virtual ICANN67 CancunEPDP Team meeting (tentative 9:00 – 11:00 local time (14:00 – 16:00 UTC) | Second / final reading:* Display of information of affiliated vs. accredited proxy / privacy providers
* Data retention

Automation Use Cases* Review remaining use cases (not yet reviewed by small team)

Purpose 2* Review EPDP Team feedback & updated language from Volker / Brian
 |
| 12 March 2020 | Virtual ICANN67 CancunEPDP Team meeting (tentative 10:45 – 12:45 local time local time (15:45 – 17:45 UTC) | Second / final reading:* Feasibility of unique contacts to have a uniform anonymized email address
* City field redaction

[**Accuracy and WHOIS Accuracy Reporting System**](https://docs.google.com/document/d/1pS9Pibanj-Hp6LztZpeERtxdoLsnp4y_-do0vU5VJuw/edit) (consider ICANN Org / GNSO Council correspondence) |
| 17 March 21020  | EPDP Team meeting | Second / final reading:* Purpose 2
* Potential OCTO Purpose
* Automation Use Cases (note, prior to the meeting groups will be asked to indicate their support or lack thereof of including use cases in Final Report – focus will be on those where there is sufficient support or indication of ability to find support)
 |
| 18 March 2020 | Legal Committee Meeting | * Territorial Scope
* Review of B&B feedback on Legal vs. Natural follow-up and Initial Report follow-up (if applicable)
 |
| 19 March 2020 | EPDP Team meeting | * Final reading of remaining priority 2 items
 |
| 20 March 2020 | Publication for review by EPDP Team of proposed Initial Report addendum on priority 2 items | * Review Initial Report addendum on priority 2 items which is to be published for public comment
 |
| 23 March 2020 | Closing date of public comment forum on SSAD Initial Report |  |
| 24 March 2020Note: last possible day to hold 40-day PCP on priority 2 items and incorporate into Final Report | EPDP Team Meeting | * Close out any remaining priority 2 items and confirm next steps, including publication for public comment of Initial Report addendum on priority 2 items
* Overview of comments submitted on SSAD Initial Report and discuss approach for reviewing input
 |
| 26 March 2020 | EPDP Team Meeting | * Commence review of public comments
 |
| April 2020(frequency of meetings dependent on # of comments received – possible F2F/high intensity meetings 29 April – 3 May) | EPDP Team Meetings | * Continue review of public comments
 |
| 3 May 2020 | Closing date of public comment forum on Initial Report addendum on priority 2 items |  |
| May 2020(frequency of meetings dependent on # of comments received – possible F2F/ high intensity meetings 13-17 May) | EPDP Team Meetings | * Conclude to final agreements, prepare Final Report, consensus call
 |
| 11 June 2020 |  | * Submit Final Report to GNSO Council (14 June = GNSO Council Motions and Docs Deadline)
 |