**Draft Work Plan for IRTP Part D PDP Working Group to submit Final Report for ICANN 50 in London**

|  |  |  |  |
| --- | --- | --- | --- |
| **Target Date** | **What** | **Deliverable/Topic for Discussion** | **Who** |
| 07 April | WG Meeting | Finalise Use Cases | All |
| 14 April | WG Meeting | Finalise Use Cases | All |
| 21 April | WG Meeting | Finalise Use Cases / Start reviewing Comments | All |
| 25 April  | Reply Period Closes | Close Reply Period | Staff |
| 28 April | WG Meeting | Review comments/replies | All |
| 5 May | WG Meeting | Review comments/replies | All |
| 12 May | WG Meeting | Review comments/replies | All |
| 19 May | WG Meeting | Review comments/replies | All |
| 26 May | WG Meeting | Discuss Definitions  | All |
| 02 June | WG Meeting | Discuss Definitions  | All |
| 09 June  | WG Meeting | Discuss Definitions  | All |
| 16 June | WG Meeting | Discuss Definitions  | All |
| 23 June | F2F Meeting in London | Status Update, community discussion | All |
| 7 July  | WG Meeting | Finalise Recommendations | All |
| 14 July  | WG Meeting | Finalise Report | All |
| 21 July | WG Meeting | Finalise Report | All |
| 28 July | WG Meeting | Finalise Report | All |
| 4 August  | WG Meeting | Finalise Report  | All |
| 11 August  | WG Meeting | Finalise Report  | All |
| 18 August | WG Meeting | Finalise Report  | All |
| 25 August | WG Meeting | Finalise Report  | All |
| 1 September  | WG Meeting  | Consensus Call | All |
| 8 September  | WG Meeting (if needed) | Finalise Report and consensus call | All |
| 15 September | Motion Deadline for GNSO Council Meeting on 25 September | Submit Motion to pass the Final Report to the GNSO Council | Staff/Co-Chairs |