PPSAI – Updated Work Plan (DRAFT)

5 January 2015

| DATE | EVENT | TOPIC/ACTION | WHO |
| --- | --- | --- | --- |
| 7 Oct 2014 | WG Meeting | Continue deliberations on Category A Main Issues | WG |
| 10 Oct 2014 | WG F2F Facilitated Session | Discuss selected high-priority topics (Transfer, Relay, Reveal) | WG |
| 15 Oct 2014 | WG F2F Meeting – ICANN51 in LA | Provide status update to ICANN community | WG |
| 28 Oct 2014 | WG Meeting | Review outcome of 10 Oct Facilitated Session; complete discussion on Relay; continue deliberations on Reveal | WG |
| 4 Nov 2014 | WG Meeting | Agree on preliminary conclusions for Category F Reveal; commence deliberations on Category G Termination | WG |
| 11 Nov 2014 | WG Meeting | Discussion with LEA/DPA; continue deliberations on Category G Termination | WG |
| 18 Nov 2014 | WG Meeting | Discussion with LEA/DPA; agree on preliminary conclusions for Category G Termination | WG |
| 25 Nov 2014 | WG Meeting | Review all preliminary conclusions A-G | WG |
| 2 Dec 2014 | WG Meeting | Review all preliminary conclusions A-G | WG |
| 9 Dec 2014 | WG Meeting | Review all preliminary conclusions A-G | WG |
| 16 Dec 2014 | WG Meeting (if needed) |  | WG |
| 19 Dec 2014 |  | Circulate draft Initial Report | Staff |
| 6 Jan 2015 | WG Meeting | Review draft Initial Report (other than Category F) | WG |
| 13 Jan 2015 | WG Meeting | Complete review draft Initial Report (other than Category F) | WG |
| 19 Jan 2015 | Document Deadline for ICANN 52 |  |  |
| 20 Jan 2015 | WG Meeting | Continue to discuss Category F | WG |
| 27 Jan 2015 | WG Meeting | Continue to discuss Category F | WG |
| 3 Feb 2015 | WG Meeting | Finalize Category F and any remaining issues | WG |
| 11 Feb 2015 | WG F2F Meeting – ICANN52 in Singapore | Presentation of initial recommendations to community | WG |
| 27 Feb 2015 |  | Circulate revised draft Initial Report | Staff |
| 3 Mar 2015 | WG Meeting | Finalize Initial Report | WG |
| 6 Mar 015 |  | Publish Initial Report for public comment | Staff |
| 15 Apr 2015 |  | Public comment period closes |  |
| 30 Apr 2015 |  | Publish summary of public comments | Staff |
| 7 Apr 2015 | WG Meeting | Commence review of public comments received (note that WG meetings may resume before this date if the Chairs determine that sufficient comments have been received to allow for WG discussion) | WG |
| 14 Apr 2015 | WG Meeting | Continue review of public comments received | WG |
| 21 Apr 2015 | WG Meeting | Conclude review of public comments received |  |
| 30 Apr 2015 |  | Circulate draft Final Report (taking into account relevant public comments received and WG input) | Staff |
| 5 May 2015 | WG Meeting | Review draft Final Report | WG |
| 12 May 2015 | WG Meeting | Review draft Final Report | WG |
| 19 May 2015 | WG Meeting | Conclude review of and finalize Consensus Call for Final Report | WG/Chairs |
| 29 May 2015 |  | Submit Final Report to GNSO Council | Chairs/Staff/Council Liaison |
| 1 June 2015 |  | Publication deadline for ICANN53 |  |
| 21-25 June 2015 | ICANN53 in Buenos Aires |  |  |