PPSAI – Updated Work Plan

23 February 2015

| DATE | EVENT | TOPIC/ACTION | WHO |
| --- | --- | --- | --- |
| 19 Dec 2014 |  | Circulate draft Initial Report | Staff |
| 6 Jan 2015 | WG Meeting | Commence review draft Initial Report | WG |
| 13 Jan 2015 | WG Meeting | Continue review of draft Initial Report | WG |
| 19 Jan 2015 | Document Deadline for ICANN 52 |  |  |
| 20 Jan 2015 | WG Meeting | Continue review of draft Initial Report | WG |
| 27 Jan 2015 | WG Meeting | Continue review of draft Initial Report | WG |
| 11 Feb 2015 | WG F2F Meeting – ICANN52 in Singapore | Discussion of outstanding issues with community | WG |
| 27 Feb 2015 | WG Meeting | Discuss outstanding issues in draft Initial Report | WG |
| 3 Mar 2015 | WG Meeting | Continue to discuss outstanding issues in draft Initial Report | WG |
| 10 Mar 2015 | WG Meeting | Continue to discuss outstanding issues in draft Initial Report | WG |
| 17 Mar 2015 | WG Meeting | Continue to discuss outstanding issues in draft Initial Report | WG |
| 24 Mar 2015 | WG Meeting | Continue to discuss outstanding issues in draft Initial Report | WG |
| 31 Mar 2015 | WG Meeting | Finalize Initial Report | WG |
| 7 Apr 2015 | WG Meeting (if needed) | Finalize Initial Report | WG |
| 15 Apr 015 |  | Publish Initial Report for public comment | Staff |
| 26 May 2015 |  | Public comment period closes |  |
| 1 June 2015 |  | Publication deadline for ICANN53 |  |
| 2 June 2015 | WG Meeting | Commence review of public comments received | WG |
| 9 June 2015 | WG Meeting | Continue review of public comments received | WG |
| 9 June 2015 |  | Publish summary of public comments | Staff |
| 16 June 2015 | WG Meeting | Continue review of public comments received |  |
| 24 June 2015 | WG Community Session – ICANN53 in Buenos Aires | Opportunity for discussion with community | WG |
| 26 June 2015 | WG F2F Meeting in Buenos Aires | Discuss WG consensus positions on outstanding issues following public comment analysis and community feedback | WG |
| 10 July 2015 |  | Circulate draft Final Report | Staff |
| 17 July 2015 | WG Meeting | Commence discussion of draft Final Report | WG |
| 24 July 2015 | WG Meeting | Continue discussion of draft Final Report | WG |
| 31 July 2015 | WG Meeting | Conclude discussion of draft Final Report; issue formal Consensus Call | WG/WG Chairs/Staff |
| 14 Aug 2015 |  | Close of formal Consensus Call period | WG Chairs/Staff |
| 21 Aug 2015 |  | Circulate Final Report | Staff |
| 25 Aug 2015 | WG Meeting (if needed) | Discuss Final Report | WG |
| 4 Sept 2015 |  | Submit Final Report to GNSO Council | WG Chairs/Staff/Council Liaison |
| 14 Sept 2015 |  | Deadline for documents/motions for GNSO Council meeting on 24 Sept |  |
| 24 Sept 2015 |  | GNSO Council teleconference meeting |  |
| 11 Sept 2015 |  | Deadline for documents/motions for GNSO Council meeting on 21 Oct |  |
| 18-22 Oct 2015 | ICANN54 in Dublin | GNSO Council in-person meeting (21 Oct) |  |

# Footnotes

This indicates the new 40-day period for public comment; the period may be extended.

WG meetings may resume before this date if the Chairs determine that sufficient comments have been received to allow for WG discussion.

Given the nature and complexity of this issue, it is anticipated that the GNSO Council may elect to consider adoption of the WG’s Final Report at its in-person meeting in Dublin in October; the September meeting may therefore be used for a briefing by the Council liaison/WG chairs.