PPSAI – Updated Work Plan

13 April 2015

| DATE | EVENT | TOPIC/ACTION | WHO |
| --- | --- | --- | --- |
| 14 Apr 2015 | WG Meeting | Conclude discussions on Disclosure Framework for Category F | WG |
| 16 Apr 2015 |  | Circulate proposed final version of Disclosure Framework for inclusion in Initial Report | Staff |
| 21 Apr 2015 | WG Meeting | Flag agreed compromises/corrections on Category F; complete discussions on remaining open items in draft Initial Report | WG |
| 24 Apr 2015 |  | Circulate proposed final version of Initial Report | Staff |
| 28 Apr 2015 | WG Meeting | Finalize Initial Report | WG/Staff |
| 30 Apr 2015 |  | Deadline for submission of additional statements (including minority positions), if any | WG |
| 4 May 2015 |  | Publish Initial Report for public comment | Staff |
| 1 June 2015 |  | Publication deadline for ICANN53 |  |
| 13 June 2015 |  | Public comment period closes |  |
| 16 June 2015 | WG Meeting | Commence review of public comments received | WG |
| 24 June 2015 | WG Working Session in Buenos Aires | Discuss possible WG consensus positions on outstanding issues following public comment review, with opportunity for community to observe and offer feedback | WG |
| 6 July 2015 |  | Publish report of public comments | Staff |
| 7 July 2015 | WG Meeting | Continue discussion of “open issues” from Buenos Aires | WG |
| 14 July 2015 | WG Meeting | Continue discussion of remaining issues | WG |
| 21 July 2015 | WG Meeting | Conclude discussion of remaining issues | WG |
| 24 July 2015 |  | Circulate draft Final Report | Staff |
| 28 July 2015 | WG Meeting | Commence discussion of draft Final Report | WG |
| 4 August 2015 | WG Meeting | Continue discussion of draft Final Report | WG |
| 11 August 2015 | WG Meeting | Conclude discussion of draft Final Report; issue formal Consensus Call | WG/WG Chairs/Staff |
| 25 Aug 2015 |  | Close of formal Consensus Call period | WG Chairs/Staff |
| 4 Sept 2015 |  | Circulate Final Report | Staff |
| 8 Sept 2015 | WG Meeting (if needed) | Discuss Final Report | WG |
| 11 Sept 2015 |  | Submit Final Report to GNSO Council | WG Chairs/Staff/Council Liaison |
| 14 Sept 2015 |  | Deadline for documents/motions for GNSO Council meeting on 24 Sept |  |
| 24 Sept 2015 |  | GNSO Council teleconference meeting |  |
| 11 Sept 2015 |  | Deadline for documents/motions for GNSO Council meeting on 21 Oct |  |
| 18-22 Oct 2015 | ICANN54 in Dublin | GNSO Council in-person meeting (21 Oct) |  |

# Footnotes

This indicates the new 40-day period for public comment; the period may be extended.

WG meetings may resume before this date if the Chairs determine that sufficient comments have been received to allow for WG discussion.

Given the nature and complexity of this issue, it is anticipated that the GNSO Council may elect to consider adoption of the WG’s Final Report at its in-person meeting in Dublin in October; the September meeting may therefore be used for a briefing by the Council liaison/WG chairs.