PPSAI – Updated Work Plan

10 November 2015

| DATE | EVENT | TOPIC/ACTION | WHO |
| --- | --- | --- | --- |
| 5 May 2015 |  | Initial Report published for public comment | Staff |
| 1 June 2015 |  | Publication deadline for ICANN53 |  |
| 7 July 2015 |  | Public comment period closes |  |
| 16 June 2015 | WG Meeting | Commence review of public comments received | WG |
| 24 June 2015 | WG Working Session in Buenos Aires | Discuss open questions and outstanding issues with community | WG |
| 14 July 2015 | WG Meeting | Begin review of public comments received | WG |
| 21 July 2015 | WG Meeting | Agree on approach to review of public comments received | WG |
| 28 July 2015 | WG Meeting | Continue review of public comments received (initial report from Sub Team 1 – Section 1.3.2) | WG/Sub Team 1 |
| 4 August 2015 | WG Meeting | Continue review of public comments received (initial report from Sub Team 2 – Section 1.3.3) | WG/Sub Team 2 |
| 11 August 2015 | WG Meeting | Continue review of public comments received (initial report from Sub Team 3 - Annex E) | WG/Sub Team 3 |
| 18 August 2015 | WG Meeting | Continue review of public comments received (initial report from Sub Team 4 – Additional Questions/Topics) | WG/Sub Team 4 |
| 25 August 2015 | WG Meeting | Continue review of public comments received (updated report from Sub Team 1 – Section 1.3.2) | WG/Sub Team 1 |
| 1 Sept 2015 | WG Meeting | Continue review of public comments received (updated report from Sub Team 2 – Section 1.3.3) | WG/Sub Team 2 |
| 8 Sept 2015 | WG Meeting | Continue review of public comments received (updated report from Sub Team 3 - Annex E) | WG/Sub Team 3 |
| 15 Sept 2015 | WG Meeting | Continue review of public comments received (discussion of possible revised Annex E) | WG |
| 22 Sept 2015 | WG Meeting | Continue review of public comments received (updated report from Sub Team 4 – Additional Topics/Questions) | WG/Sub Team 4 |
| 29 Sept 2015 | WG Meeting | Review any additional issues arising from Parts 1 – 3 of the WG Public Comment Review Tool | WG |
| 6 Oct 2015 | WG Meeting | Continue WG review of Sub Team reports | WG |
| 9 Oct 2015 |  | Circulate draft Final Report | WG Chairs/Staff |
| 16 Oct 2015 | WG F2F Meeting | Discuss remaining Sub Team topics and proposed final recommendations for Final Report | WG |
| 18-22 Oct 2015 | ICANN54 in Dublin | Community session | WG |
| 3 Nov 2015 | WG Meeting | Review feedback from ICANN54; continue discussion of recommendations for inclusion in Final Report | WG |
| 10 Nov 2015 | WG Meeting | Continue discussion of draft Final Report | WG |
| 17 Nov 2015 | WG Meeting | Finalize outstanding items for draft Final Report | WG |
| 20 Nov 2015 |  | Circulate updated Final Report / open formal Consensus Call | WG Chairs/Staff |
| 24 Nov 2015 | WG Meeting | Discuss any questions arising from SG/C consultations by WG members for formal Consensus Call |  |
| 1 Dec 2015 | WG Meeting (if needed) |  |  |
| 7 Dec 2015 |  | Close of formal Consensus Call | WG Chairs/Staff |
| 8 Dec 2015 |  | Deadline for submission of documents to GNSO Council (for December 2015) |  |
| 14 Dec 2015 | WG Meeting (if needed) |  |  |
| 17 Dec 2015 |  | GNSO Council meeting |  |
| ?? Jan 2016 |  | Deadline for submission of documents to GNSO Council (for January 2016) | WG Chairs/Staff/Council Liaison |
| ?? Jan 2016 |  | First GNSO Council meeting for 2016 |  |

NOTE: Following the Council’s approval and adoption of any recommendations, a Recommendations Report will be prepared and sent to the ICANN Board. Per the ICANN Bylaws, any potential policy recommendations being considered by the Board “that substantially affect the operation of the Internet or third parties” will need to be published for public comment, prior to Board action. As such, the above timeline does not represent the final date of adoption of any recommendations to be made by this WG.

# Footnotes

The WG agreed to request an extended public comment period, extending beyond the normal 40-day period due to the number of other activities in the ICANN community and the agreed need for detailed community input on a number of the WG’s recommendations and open questions.

WG meetings may resume before this date if the Chairs determine that sufficient comments have been received to allow for WG discussion.

From this date on, unless otherwise noted, WG meetings are expected to be of at least a 90-minute duration.