|  |  |
| --- | --- |
| Recommendation 14: Feasibility for Breaking PDPs into Discrete Stages  Recommendation 15: Timeliness of the Policy Development Process | |
| Strategic Alignment | |
| Part One – Which ICANN Objective does this meet | |
| Promote role clarity and establish mechanisms to increase trust within the ecosystem rooted in the public interest. . See Strategic Plan, page 23 at: https://www.icann.org/en/system/files/files/strategic-plan-2016-2020-10oct14-en.pdf | |
| Alignment with Strategic Objectives | |
| **Goal** | Shared understanding by Board, staff and stakeholders of the allocation of responsibilities for design, development and implementation of policy and operational processes.  - Shared understanding of the roles, responsibilities and accountability of the Board, staff and stakeholders.  - Board, staff, and stakeholders use |
| **Project/Recommendation** | 14. That the GNSO further explores PDP ‘chunking’ and examines each potential PDP as to its feasibility for breaking into discrete stages.  15. That the GNSO continues current PDP Improvements Project initiatives to address timeliness of the PDP. |

|  |
| --- |
| Scope Description |
| Scope Statement |
| 1. Staff to confirm whether the approach of determining the feasibility for breaking PDPs into discrete stages is already being used by PDP Working Groups and whether there are any provisions in the PDP Manual which would prevent and/or encourage “chunking”. 2. Staff to confirm whether the expedited PDP procedures have been adopted. 3. The GNSO Review Working Group to determine whether this recommendation has been implemented. |
| **Out of Scope** |
| The above scope is sufficiently clear. |
| **Assumptions** |
| That the PDP Manual does not preclude the approach of determining the feasibility for breaking PDPs into discrete stages. |
| **Deliverables** |
| Examples of current PDPs that are following this approach. Possible revisions to the WG Assessment. |

|  |
| --- |
| Option Analysis |
| None were considered or were necessary to be considered. |
| Solution |
| 1. In its analysis staff notes that ongoing broad-subject PDPs are often chunked and divided into phases and/or subgroups. In case of the PDP on Review of all RPMs in all gTLDs the phasing has even been added to the PDP Charter. In the case of the PDP Working Group on New gTLD Subsequent Procedures the work has been divided among four work tracks each managed by a sub team. See the RPM Charter: <http://gnso.icann.org/en/drafts/rpm-charter-15mar16-en.pdf>. See the PDP Working Group on New gTLD Subsequent Procedures wiki at: <https://community.icann.org/display/NGSPP/New+gTLD+Subsequent+Procedures+PDP+Home>. 2. Staff reviewed the PDP Manual and the Working Group Guidelines and determined that nothing in those document prevents or discourages the phasing or dividing of a PDP into subgroups. However, the Working Group Guidelines address the potential risk (noted below) of subgroups lacking community representation, but notes that this may not be a barrier to the formation of subgroups. In particular, section 2.2.1 Chair states, “The Chair should make it clear that participation on sub-teams is open to all and he/she should encourage representational balance to the degree possible. However, it should be understood that there will not always be volunteers from every interest group and that it is often acceptable to have a small sub-team that is not totally representational perform an initial role that will later be reviewed by a broader more representational group.” 3. Staff notes that the current Working Group Guidelines do not specifically encourage a phased approach and ask the Working Group whether specific language should be added in this regard, noting that a phased approach may not be appropriate for all PDPs. 4. Staff reviewed the Final Report of the Policy & Implementation Working Group that was adopted by the GNSO Council. See the Final Report at: <https://gnso.icann.org/en/issues/policy-implementation/pi-wg-final-recommendations-01jun15-en.pdf>. In particular, recommendation #2 recommended the creation of three additional GNSO Processes, namely a GNSO Input Process, a GNSO Guidance Process and a GNSO Expedited Policy Development Process following the model as outlined in Annex C (GNSO Input Process), Annex D and E (GNSO Guidance Process) and Annex F and G (GNSO Expedited Policy Development Process).  In addition, staff noted that on 24 June 2015 the GNSO Council recommended that the ICANN Board of Directors adopt the new GNSO Processes as reflected in the Annexes D and E for the GNSO Guidance Process and Annexes F and G for the GNSO Expedited Policy Development Process as outlined in the Policy & Implementation Final Recommendations Report and the motion at <https://community.icann.org/display/gnsocouncilmeetings/Motions+24+June+2015>. In addition, the GNSO Council recommended that the GNSO Guidance Process and GNSO Expedited Policy Development Process shall be available for use by the GNSO Council following adoption of any necessary changes to the ICANN Bylaws by the ICANN Board. The revised ICANN Bylaws were completed and posted on 16 February 2016 and the revised GNSO Operating Procedures were posted on 17 February 2016 at version v3.2 5. Staff notes that the Working Group could consider whether a more formal process should be undertaken for speeding up PDPs.  Perhaps, periodically in PDPs to share ideas how it could be speeded up. If so, staff could draft language for inclusion in the WG Assessment questionnaire (which would not require a change to the GNSO Operating Procedures. 6. Staff hereby presents the results of the review to the Working Group. 7. The Working Group will determine whether the revisions constitute the implementation of the recommendation. |

|  |
| --- |
| Key Dependencies |
| Feasibility of phasing of PDPs. |

|  |
| --- |
| Risk Identification |
| Risk of volunteer overload if breaking the PDP into subgroups results in a large number of subgroups that lack adequate volunteer participation or community representation. |
|  |

|  |
| --- |
| Key Performance Indicators |
| ~~As the manager of the PDP GNSO Council is expected to ensure that the PDP process is as efficient as possible.~~ If the recommendation is to encourage phasing of PDPs, a KPI could be the measurement of the completion time of phased PDPs versus non-phased PDPs. However, it is not clear that a KPI applies in this instance. |

|  |
| --- |
| Necessary to proceed |
| Next Phase Activities/Resources |
| None. |

|  |  |  |
| --- | --- | --- |
| **Reviewers** | | |
| **Name** | **Title** | **Date Sent** |
| GNSO Review Working Group |  |  |

|  |  |  |  |
| --- | --- | --- | --- |
| **Approvers** | | | |
| **Name** | **Title** | **Approval Status** | **Date** |
| GNSO Review Working Group |  |  |  |
| GNSO Council |  |  |  |

|  |  |  |  |
| --- | --- | --- | --- |
| **Revision History** | | | |
| **Date** | **Version** | **Description** | **Author** |
| 12 April 2017 | V1 | Original Draft | Julie Hedlund, Policy Director |

**Attachments, as applicable:**

* None