**UPDATED WORK PLAN – updated 2 MAY 2017**

(Note: \*\* denotes the 4th rotational meeting time of 0300 UTC)

|  |  |  |  |
| --- | --- | --- | --- |
| **DATE/MEETING TIME** | **SUBJECT** | **DISCUSSION TOPICS** | **ACTION BY:** |
| 1 March 2017 | TMCH review | * Review TMCH Charter questions (Category 3) against STI recommendations, AGB and other Program Documentation * Review proposed meeting agendas for ICANN58 | All |
| 8 March 2017 | Pre-ICANN Meeting Week | * No meeting | Chairs & staff to confirm presentation materials for ICANN58 |
| 11-16 March 2017 | **ICANN58** | For intensive 3-hour F2F session:   * 1-hour discussion with Deloitte * Continue review of TMCH Charter questions (Categories 1-2 and possibly Categories 3-6) against STi recommendations, AGB, Program Documentation? * Discuss which, if any, TMCH Charter questions can be considered closed for the time being, and which require additional work and/or discussion? * Form Sub Teams to begin process of refining Sunrise & Claims Charter questions?   For Open Community Session:   * Brief presentation of status of TMCH review for community feedback * Invite community feedback on how to refine Sunrise & Claims Charter questions | All |
| 22 March 2017 | Post-ICANN Meeting Week | * No meeting |  |
| 29 March 2017 (90 minutes) | TMCH review  Sunrise & Claims Charter questions review (Sub Team) | * Review community feedback from ICANN58 * Complete discussions from F2F session at ICANN58 | All  Form Sunrise/Claims Charter Sub Teams |
| 5 April 2017 (90 minutes) | TMCH review  Sunrise & Claims Charter questions review (Sub Team) | * Review Analysis Group’s Final Report | All (staff to invite Greg Rafert from Analysis Group to join the call)  Sunrise/Claims Charter Sub Team meeting |
| 12 April 2017 (90 minutes) | TMCH review  Sunrise & Claims Charter questions review (Sub Team) | * Review any remaining open questions from TMCH review | All  Sunrise/Claims/Private Protections Sub Team meeting |
| 19 April 2017 (90 minutes?) | Sunrise/Claims scoping | NO WORKING GROUP MEETING (deadline for submitting proposals on open TMCH questions) | Sunrise/Claims Sub Team meeting |
| \*\* 26 April 2017 (90 minutes) | TMCH open questions discussion  Sunrise & Claims scoping | * Sub Teams to present progress report to full WG * WG to discuss any proposals received on remaining open TMCH questions | All  Sunrise/Claims |
| 3 May 2017 (90 minutes) | Sunrise & Claims scoping | * Sub Teams to present progress report to full WG * Complete discussion of TMCH open questions | All  Sub Teams |
| 17 May 2017 (90 minutes) | Sunrise, Claims & Private Protections scoping | * Sunrise & Claims Sub Teams to present proposed finalized Charter questions and proposed mini Work Plans | All  Sub Teams |
| 31 May 2017 (90 minutes) | Sunrise review  Private Protections scoping | * Commence Sunrise review | All |
| \*\* 7 June 2017 (90 minutes) | Sunrise review  Private Protections scoping | * Private Protections Sub Team to present progress report to full WG * Continue Sunrise review |  |
| 14 June 2017 (120 minutes) | Prep for ICANN59 | * Continue Sunrise review * Agree on community discussion points for ICANN59 and (if planned) F2F intensive session | All |
| 21 June 2017 | Pre-ICANN59 Meeting Week | * No meeting | Chairs & staff to confirm presentation materials for ICANN59 |
| 26-29 June 2017 | **ICANN59** | * F2Fmeeting (complete initial Sunrise review and commence Claims review; discuss proposed questions from Private Protections Sub Team) | All |
| 5 July 2017 | Post-ICANN Meeting Week | * No meeting |  |
| 12 July 2017 | Claims review  Form Sub Team to refine Charter questions for URS | * Review feedback from ICANN59 * Continue Claims review | All |
| 19 July 2017 | Claims review | * Continue Claims review | All  URS Charter Sub Team meeting |
| 26 July 2017 | Claims review/Private Protections discussion | * Continue Claims review * Discuss Private Protections | All  URS Charter Sub Team meeting |
| \*\* 2 August 2017 | Claims review/Private Protections discussion | * Conclude initial Claims review * Continue discussion of Private Protections | All  URS Charter Sub Team meeting |
| 9 August 2017 | Stock taking: TMCH and associated RPMs | * Evaluate overall progress and conclusions from TMCH, Sunrise and Claims review | All  URS Charter Sub Team meeting |
| 16 August 2017 | **URS Overview** | * Overview presentation of URS and introduction of Charter questions | All  URS Charter Sub Team meeting |
| 23 August 2017 | URS review scoping | * Discuss Sub Team proposal for refined URS Charter questions | All |
| \*\* 30 August 2017 | URS review scoping | * Discuss and agree on refined URS Charter questions | All |
| 6 September 2017 | URS review | * Finalize approach to URS review | All |
| 13 September 2017 | URS review | * Commence URS review | All |
| 20 September 2017 | URS review | * Continue URS review | All |
| \*\* 27 September 2017 | URS review | * Continue URS review | All |
| 4 October 2017 | URS review | * Continue URS review |  |
| 11 October 2017 | URS review | * Continue URS review | All |
| 18 October 2017 | URS review | * Agree on points to be raised to community at ICANN60 and (if planned) agenda for ICANN60 F2F intensive session | All |
| 25 October 2017 | Pre-ICANN60 Meeting Week | * No meeting | Chairs & staff to confirm presentation materials for ICANN60 |
| 28 Oct – 3 Nov 2017 | **ICANN60** | * (possible) intensive F2F meeting (conclude initial URS review?) * Open community discussion on URS | All |
| 8 November 2017 | Post-ICANN Meeting Week | * No meeting |  |
| 15 November 2017 | URS review/General | * Review community feedback from ICANN60 * Review preliminary conclusions on URS | All |
| 22 November 2017 | Day before Thanksgiving (US holiday) | * No meeting |  |
| 29 November 2017 | Finalize Phase 1 | * Agree on Phase 1 recommendations | All |
| 6 December 2017 | Finalize Phase 1 | * Agree on Phase 1 recommendations |  |
| 13 December 2017 | Finalize Phase 1   * Staff to circulate draft Initial Report containing agreed recommendations | * Commence discussion of draft Initial Report | All; staff |
| 20 December 2017 | Finalize Phase 1 | * Continue discussion of draft Initial Report | All |
| Week of 27 December 2017 | ICANN offices closed | * No meeting |  |
| 3 January 2018 | Finalize Phase 1 | * Finalize discussion of draft Initial Report | All |
| 15 January 2018 | Finalize Phase 1 and open public comment forum   * Staff to circulate proposed finalized Initial Report | * **Public comment forum opens** | Staff |
| **24 February 2018** | **Close of public comment period** | * NOTE: WG may hold meetings to review public comments received before this date * Staff to circulate (and update, as needed) Public Comment Review Tool |  |
| 28 February 2018 | Review Phase 1 Report | * Discuss public comments received on Phase 1 Report | All |
| 7 March 2018 | Pre-ICANN Meeting Week | * No meeting | Chairs & staff to confirm presentation materials for ICANN61 |
| 10-15 March 2018 | **F2F at ICANN61** | * Discuss public comments received and proposed WG responses with community | All |
| 21 March 2018 | Post-ICANN Meeting Week | * No meeting |  |
| 28 March 2018 | Review Phase 1 Report | * Continue discussion of public comments received | All |
| 4 April 2018 | Review Phase 1 Report | * Continue discussion of public comments received | All |
| 11 April 2018 | Review Phase 1 Report   * Staff to circulate updated report before this meeting | * Review updated recommendations based on public comments accepted by the WG | All; staff |
| 18 April 2018 | Review Phase 1 Report | * Finalize updated Phase 1 Report | All |
| 25 April 2018 | Review Phase 1 Report | * Finalize Phase 1 Report * **Submit Phase 1 Report to GNSO Council** | All; chairs & staff |
| **CONCLUSION OF PHASE ONE – COMMENCE PHASE TWO** | | | |
| 2 May 2018 | UDRP overview | * Overview presentation of UDRP and Charter questions | All |
| 9 May 2018 | UDRP outreach | * Discuss outreach letter/questions to ICANN SO/AC/SG/Cs | All (Sub Team may be formed to develop initial draft letter) |
| 16 May 2018 | UDRP outreach | * Agree on outreach letter/questions | All |
| 23 May 2018 | UDRP review scoping | * Commence discussion of Charter questions | All |
| 30 May 2018 | UDRP review scoping | * Continue discussion of Charter questions | All |
| 6 June 2018 | UDRP review scoping | * Agree on discussion items with community for ICANN62 | All |
| 13 June 2018 | Pre-ICANN Meeting Week | * No meeting | Chairs & staff to confirm presentation materials for ICANN62 |
| 18-21 June 2018 | **F2F at ICANN62** | * Seek community input on Charter questions to be reviewed for the UDRP | All |
| 27 June 2018 | Post-ICANN Meeting Week | * No meeting |  |
| 4 July 2018 | US holiday (4th of July) | * No meeting |  |
| 11 July 2018 | UDRP review scoping | * Review community input from ICANN62 | All |
| 18 July 2018 | UDRP review scoping | * Agree on questions to be reviewed | All |
| 25 July 2018 | UDRP review | * Commence review of UDRP | All |
| 1 August 2018 | UDRP review |  |  |
| 8 August 2018 | UDRP review |  |  |
| 15 August 2018 | UDRP review |  |  |
| 22 August 2018 | UDRP review |  |  |
| 29 August 2018 | UDRP review |  |  |
| 5 September 2018 | UDRP review |  |  |
| 12 September 2018 | UDRP review |  |  |
| 19 September 2018 | UDRP review |  |  |
| 26 September 2018 | UDRP review |  |  |
| 3 October 2018 | UDRP review |  |  |
| 10 October 2018 | Status Summary | * Agree on discussion items with community at ICANN63 | All |
| 17 October 2018 | Pre-ICANN Meeting Week | * No meeting | Chairs & staff to confirm presentation materials for ICANN63 |
| 20-26 October 2018 | **F2F at ICANN63** |  |  |
| 31 October 2018 | Post-ICANN Meeting Week | * No meeting |  |
| 7 November 2018 | UDRP review | * Review feedback from ICANN63 | All |
| 14 November 2018 | UDRP review | * Conclude initial review of UDRP | All |
| 21 November 2018 | US holiday (day before Thanksgiving) | * No meeting |  |
| 28 November 2018 | UDRP conclusions | * Begin discussion of preliminary recommendations for UDRP review | All |
| 5 December 2018 | UDRP conclusions | * Continue discussions of UDRP preliminary recommendations | All |
| 12 December 2018 | UDRP conclusions | * Continue discussions of UDRP preliminary recommendations | All |
| 19 December 2018 | UDRP conclusions | * Continue discussions of UDRP preliminary recommendations | All |
| Week of 26 December 2018 | ICANN offices closed | * No meeting |  |
| 2 January 2019 | UDRP conclusions | * Continue discussions of UDRP preliminary recommendations | All |
| 9 January 2019 | Finalize UDRP conclusions | * Agree on UDRP preliminary recommendations | All |
| 16 January 2019 | Phase Two initial report   * Staff to circulate partial draft Phase Two report (on the UDRP) | * Discuss draft report on the UDRP | All; staff |
| 23 January 2019 | Phase Two initial report | * Discuss draft report on the UDRP | All |
| 30 January 2019 | Phase Two initial report | * Finalize draft report on the UDRP | All |
| Week of 6 February 2019 | **Open public comment forum for Phase Two (UDRP review)** | * [No meeting?] | Staff |
| 13 February 2019 | Review of remaining topics | * Consider overarching and remaining general Charter questions | All |
| 20 February 2019 | Review of remaining topics | * Consider overarching and remaining general questions | All |
| 27 February 2019 | Status Summary | * Agree on discussion items for community at ICANN64 | All |
| 6 March 2019 | Pre-ICANN Meeting Week | * No meeting | Chairs & staff to confirm presentation materials for ICANN64 |
| 9-14 March 2019 | **F2F at ICANN64** |  |  |
| Week of 20 March 2019 | **Close of public comment forum**  Post-ICANN Meeting Week | * No meeting |  |
| 27 March 2019 | Review of public comments | * Discuss public comments received on UDRP report | All |
| 3 April 2019 | Review of public comments | * Discuss public comments received on UDRP report | All |
| 10 April 2019 | Review of public comments | * Discuss public comments received on UDRP report | All |
| 17 April 2019 | Finalise Phase 2 - UDRP report | * Agree on updates to UDRP recommendations | All |
| 24 April 2019 | Finalize Phase 2 - UDRP report   * Staff to update UDRP report | * Agree on updates to UDRP recommendations | All/staff |
| **CONCLUSION OF PHASE TWO – CONSOLIDATION PHASE BEGINS** | | | |
| 1 May 2019 | Overall review of all recommendations from Phase 1 & Phase 2 |  |  |
| 8 May 2019 |  |  |  |
| 15 May 2019 |  |  |  |
| 22 May 2019 |  |  |  |
| 29 May 2019 |  |  |  |
| 5 June 2019 |  |  |  |
| 12 June 2019 |  | * Agree on overall recommendations for Phases 1 & 2 | All |
| 19 June 2019 | Pre-ICANN Meeting Week | * No meeting | Chairs & staff to confirm presentation materials for ICANN65 |
| 24-27 June 2019 | **F2F at ICANN65** | * Present overall recommendations to community | All |
| 3 July 2019 | Post-ICANN Meeting Week | * No meeting |  |
| 10 July 2019 | Review all proposed Phase 1 & 2 recommendations | * Review feedback from ICANN65 | All |
| 17 July 2019 | Prepare Final Report | * Review all recommendations | All |
| 24 July 2019 |  |  |  |
| 31 July 2019 |  |  |  |
| 7 August 2019 |  |  |  |
| 14 August 2019 |  |  |  |
| 21 August 2019 |  |  |  |
| 28 August 2019 |  |  |  |
| 4 September 2019 |  |  |  |
| 11 September 2019 |  |  |  |
| 18 September 2019 |  |  |  |
| 25 September 2019 |  |  |  |
| 2 October 2019 |  |  |  |
| 9 October 2019 |  |  |  |
| 16 October 2019 |  |  |  |
| 23 October 2019 |  |  |  |
| 30 October 2019 | Pre-ICANN Meeting Week | * No meeting |  |
| 2-8 November 2019 | **ICANN66** |  |  |