| IANA Stewardship Transition Coordination Group: Process flow and Timeline, Status: 10 September 2014 (MN) |
| --- |
|  |  | Protocol Parameters IETF | PROPOSAL |  |  |  | Protocol Parameters IETF |  |  |  | Protocol Parameters IETF |  |  |  |  |
|  |  | Numbering Resources RIRs | PROPOSAL |  | Coordination Group |  | Numbering Resources RIRs |  | Coordination Group |  | Numbering Resources RIRs |  | Coordination Group |  | NTIA |
| ALAC |  | Domain Names Cross-Community Working Group | PROPOSAL(s) |  |  |  | Domain Names Cross-Community Working Group |  |  |  | Domain Names Cross-Community Working Group |  |  |  |  |
| ccNSO |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| GNSO |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| SSAC |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| GAC? |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| TIMELINE |  | STEP 0: 08/09/2014 – Request for Communities to produce proposals – | STEP 1: 08/09/2014 – 15/01/2015 Communities develop proposals |  | STEP 2: 15/01/2015 – 13/03/2015 ICG develops draft response |  | STEP 3: 13/03/2015 – 15/05/2015 Communities review the strawman proposal |  | STEP 5: 15/05/2015- 19/06/2015 IGC develops final response | STEP 6: 19/06/2015- 17/07/2015 Final response review |  | STEP 7: 17/07/2015 – 31/07/2015 Proposal delivery |  | STEP 8: 31/07/2015 – 30/09/2015 NTIA approval |
|  |  |  |  |  |  |  |  |  | STEP 4: 13/03/2015 – 17/07/2015 Testing |  |  |  |  |

# Text boxes

Other Interested Parties

Other Interested Parties

Other Interested Parties