## Slide 1
Implementation Oversight Task Force (IOTF) Meeting
Call #15 | 13 July 2016

## Slide 2: Agenda
Opening Remarks
Implementation Items
  RZERC Charter – Post Public Comment Analysis
AOB
  PTI Bank Account
  Open Public Comment Items
Closing Remarks
Notes: This is a simpler agenda slide, the outline for your presentation.

## Slide 3
RZERC Charter
Notes: Breakup your presentation, divide it into sections. This is especially useful if most of your presentation is text.

## Slide 4
AOB & Closing Remarks
Notes: Breakup your presentation, divide it into sections. This is especially useful if most of your presentation is text.

## Slide 5: Open Public Comment Items
Items | Open Date | Close Date
PTI Article of Incorporation | 01 July | 31 July
PTI Governance Documents Code of Conduct Conflict of Interest Policy Expected Standard of Behavior | 08 July | 07 August
PTI Bylaws | 12 July | 11 August

## Slide 6
Appendix
Notes: Breakup your presentation, divide it into sections. This is especially useful if most of your presentation is text.

## Slide 7: Discussion Items & Status
Items | IOTF Agreement | CWG Agreement | Decision | Next Step
Define selection criteria for Nom-Com PTI independent Directors |  |  |  | Fold into PTI Bylaws discussion?
PTI staffing |  |  |  | In discussion
PTI governance documents (Bylaws, AoI, CoI) |  |  |  | In discussion
ICANN-PTI Contract(s)* |  |  |  | In discussion
IANA IPR - TBD |  |  |  | 
IANA Customer Service Complaint Resolution Process |  |  | Clarification provided | Implementation
IANA Problem Resolution Process |  |  | Clarification provided | Implementation
PTI services |  |  | PTI to perform all 3 IANA functions | Implementation
Approach for selection of interim PTI independent Directors |  |  | CWG Chairs to serve as interim Directors | Implementation
CSC formation |  |  | Issue request for appointment | Implementation
RZERC charter |  |  | Post Charter for public comment | Public Comment
*Includes discussion on whether to combine the Names contract and intercompany contract

## Slide 8: Decision Log
PTI Independent Board of Directors
  Initial Selections
    Jonathan and Lise to serve as interim PTI independent directors assuming there are no issues around conflict and independence (IOTF Call #1, 21 March 2016 / CWG Meeting #78, 31 March 2016)
  Ongoing Selections
    NomCom will be the appointing body for PTI independent directors (IOTF Call #1, 21 March 2016 / CWG Meeting #78, 31 March 2016)
PTI Structure
  PTI will perform all 3 IANA functions (IOTF Call #2, 25 March 2016 / CWG Meeting #78, 31 March 2016)
Document Review Process & Timeline
  Agreement reached (IOTF Call #4, 04 April 2016)
IANA Escalation Mechanisms
  Clarification provided by Chuck Gomes and IOTF has no objections to clarification. (IOTF Call #8, 10 May 2016)
CSC
  CSC formation process and timeline shared and received no objections via IOTF call and CWG mail list. (IOTF Call #9, 20 May 2016 / CWG mail list 26 May 2016)
RZERC Charter
  RZERC Charter was shared and finalized over the IOTF and CWG mail lists. (IOTF mail list 03: June 2016 / CWG mail list: 17 May 2016)
Notes: This is a simpler agenda slide, the outline for your presentation.

## Slide 9: Document Review Process & Timeline
ICANN shares high-level descriptions with IOTF
IOTF reviews & agrees on high-level descriptions
ICANN drafts full document
OCs review & provide input on full document*
ICANN finalizes & posts draft document for public comment
ICANN analyzes comments, finalizes document & obtains Board approval
2 weeks
30 days
For discussion
1
6
3
5
4
2