## Slide 1: Neo-Brahmi Generation Panel (NBGP)
Dr. Ajay Data
अजय@डाटा.भारत
Face to Face meeting
Delhi – 23rd April 2018

## Slide 2: Agenda
Introducing NBGP: Scope: Scripts, Languages, Geo Coverage
NBGP Members
Variant Analysis Mechanism
Efforts and Progress so far - Timeline
Future Plan of Action
UASG / IDN / EAI
1
2
3
4
5
6
Notes: This is a stylized agenda slide for your presentation.
To delete a box, if there are too many boxes, click the edge of the box, ensure the entire box is highlighted, then DELETE.
To update the numbers and text, click inside the circle for the numbers or in the box for the text, revise the text.

## Slide 3: NBGP, Scope, Scripts, Coverage, Impact etc.
Introduction
Generate proposals for script specific LGRs, based on community expertise and requirements. Ensure Global Acceptability of Neo-Brahmi Script based language IDN’S and variants.
1
2
Scope
Devanagari, Gujarati, Bengali, Gurmukhi/Punjabi, Odia/Oriya, Tamil, Kannada, Telugu and Malayalam.
4
Coverage
20% of the worlds populations user the scripts, which are under the discussion under NBGP. Approx 60 languages are under scope as per EGIDS scale.
5
Impact
People using these scripts will be able to enable themselves for internet in there language using IDNs and EAI.
3
Geo Coverage
India, Sri Lanka, Nepal, Bangladesh
EGIDS: Expanded Graded Intergenerational Disruption Scale
Notes: Look for different ways to display your data or text by using alternatives to simple bullets.
To adjust the number in the arrow to text or another number, click on the text box around the number, revise.
To add an arrow, click on the arrow, ensure the arrow is highlighted, COPY and PASTE and move to the desired placement, or DELETE if there are too many arrows.

## Slide 4: Members
Co-chairs: Dr. Ajay Data, Dr. Mahesh D. Kulkarni, Prof. Udaya Narayana Singh
Members: 60+ members from India, Nepal, Sri Lanka
t\\
63%
Data Analysis
22%
NBGP
Devanagari
Akshat S. Joshi
Gujarati
Raiomond Doctor
Gurmukhi
Gurpreet Singh Lehal
Kannada
U.B. Pavanaja
Telugu
Uma Maheshwar G Rao
Bengali
Atiur Rahman Khan
Tamil
Shanmugam R
Malayalam
Veena / Prasad
Oriya
Kuldeep Patnaik
9 Script Leads
1
2
3
4
5
6
7
8
9

## Slide 5: Timeline
May
2010
Aug
2014
May
2015
Aug
2017
Dec
2017
Feb
2018
IDN ccTLD
ccTLD .bharat
NBGP Seated
IP feedback and Draft Devanagari LGR is getting prepared
F2F meeting in Colombo
Draft LGR for Devanagari is at final stages to be released for public comments. LGR for all other scripts are in the revision stage with the Integration Panel.
Summary
Draft of Gurmukhi, Gujarati, Kannada, Telugu LGR are gettering prepared
April
2018
Draft LGRs are sent to IP for first comments and revised version sent to IP again.
.भारत
Notes: To adjust the length and width of the arrow, click on the arrow, grab a corner, and lengthen or shorten, depending on your preference.
To add a bubble, click on the bubble, ensure it is fully highlighted, COPY and PASTE. Then drag the bubble to your preferred placement.
To delete a bubble, click on the bubble, ensuring it is highlighted and click DELETE. If you make a mistake, go to your top bar on PP and click EDIT, UNDO

## Slide 6: Future Timeline
April
2018
April
2018
May
2018
June
2018
June
2018
July
2018
Release of Devanagari LGR for Public Comments
Send all scripts for next round of comments to IP
Final Versions of LGR for Other Scripts
Receive feedback and update the documents
IP Feedback on LGRs Received
Release of all Neo-Brahmi LGRs for Public Comments
Face to Face meeting in Bangladesh – Small group from Bangla Script
Notes: To adjust the length and width of the arrow, click on the arrow, grab a corner, and lengthen or shorten, depending on your preference.
To add a bubble, click on the bubble, ensure it is fully highlighted, COPY and PASTE. Then drag the bubble to your preferred placement.
To delete a bubble, click on the bubble, ensuring it is highlighted and click DELETE. If you make a mistake, go to your top bar on PP and click EDIT, UNDO

## Slide 7: Status as of 1 January 2017

## Slide 8: Status as of 22nd April 2018
Script | Sufficient Resource Onboard? | Prepare the first draft of the LGR | Finalize the draft | Proposal is agreed by NBGP | Create XML | XML is agreed by NBGP | Create the test labels file | Number of revision rounds with the IP | Incorporate IP Feedback | Public Comment
Devanagari | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | 7 | Ongoing, due 27 Apr | 
Gujarati | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | 2 | Ongoing, due 27 Apr | 
Gurmukhi | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | 2 | Ongoing, due 27 Apr | 
Kannada | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | 2 | Ongoing, due 27 Apr | 
Malayalam | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | Going to submit after F2F |  | 
Tamil | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | 1 |  | 
Telugu | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | Ongoing, due 27 Apr | 2 | Ongoing, due 27 Apr | 
Bengali | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | Ongoing, due 27 Apr |  |  | 
Oriya | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | 1 | Ongoing, due 30 Apr | 
Notes: To adjust the length and width of the arrow, click on the arrow, grab a corner, and lengthen or shorten, depending on your preference.
To add a bubble, click on the bubble, ensure it is fully highlighted, COPY and PASTE. Then drag the bubble to your preferred placement.
To delete a bubble, click on the bubble, ensuring it is highlighted and click DELETE. If you make a mistake, go to your top bar on PP and click EDIT, UNDO

## Slide 9: Cross-Script Variant Analysis Mechanism
The GP identified multiple script pairs including Devanagari-Gurmukhi , Kannada-Telugu (ಅಕ್ಷರಮಾಲೆ - తెలుగు లిపి) and Tamil-Malayalam (தமிழ் - മലയാളലിപിfor the cross-script variant analysis
The panel had a detailed discussion on cross-script variant characters to determine an agreeable mechanism to identify them
The panel converged on a solution to tag each pair of candidate cross-script variant code points with one of the three colors
  Red – Identical / Indistinguishable | document as variant code points
  Yellow – Similar but distinguishable | document as reference in the appendix
  Green – Not similar

## Slide 10
Cross-Script Variants for Devanagari and Gurmukhi

## Slide 11
TLD - Variant example for Devanagari and Gurmukhi
.ਠਗ
.ठग

## Slide 12: Methodology followed to achieve goal.
Attracting members – No rejection policy
Fixed date and time for update conference all (fixed agenda)
F2F meetings
Follow-up on fixed date and time
Finalising champion for each script and internal scope
Organising cross scripts calls
Motivating members / Appreciations
Lead by example to join each call and contribute to resolve
Involve Government stakeholders
F2F meetings at every opportunity
Collaborative document update and view
Taking support from ICANN for XML and expert view from other LGR experience
Submitting document to IP for review
Phased feedback approach from IP
15. WhatsApp group for quick update / follow up and reminders
16. Personal calls to group leaders with expert connect
Division of Responsibility

## Slide 13: UASG - IDN - EAI
All Internet applications and systems must treat all TLDs in a consistent manner, including new gTLDs and internationalized TLDs.
Specifically, they must accept, validate, store, process and display all domain names.

## Slide 14: Building Blocks: Domain Names
A domain name is dotted text string used as a human-friendly technical identifier for computers and networks on the internet
example.domain.tld
Second-level
domain
Subdomain or third-
level domain
Top-Level Domain
(TLD) or suffix
Each dot represents a level in
the Domain Name System (DNS)
Notes: This may be too basic for some courses, but review of terminology is generally worth the time.

## Slide 15: Building Blocks: gTLDs
Starting in 2013, ICANN (the organization responsible for the creation and maintenance of TLD assignments) approved the creation of a large number of new TLDs. These new TLDs can represent brands, communities of interest, geographic communities (cities, regions) and more generic concepts. Collectively, all of these new TLDs are known as Generic Top Level Domains (gTLDs).
Original Seven gTLDs
.com
.org
.gov
.edu
.mil
.net
.int
Common cc TLDs
.de
.cn
.uk
.nl
.eu
.ru
.tk
New gTLDs
.top
.xyz
.loan
.club
.网址
.信息
.コム
Notes: Optional Slide:
Good review of concepts of generic top-level domains and country-code top-level domains.
Students tend to enjoy hearing how .com originated in 1985 and grew to be the dominant TLD. It can be contrasted with some of the generic TLDs that were introduced later (e.g., .aero) which have not yet gained wide-spread usage. The widespread usage of some country-code TLDs can also be discussed. If a discussion ensues, make sure to keep a limit on the discussion time so as to ensure time remains for the remainder of the lecture.

## Slide 16: Internationalized Domain Name: IDN
राजस्थान.भारत
मेल.डाटा.भारत
मेल.राहुलदेव.भारत
पत्रिका.भारत
मेल.माइक्रोसॉफ्ट.भारत
почта.рус
ડાટામેલ.ભારત
ਡਾਟਾਮੇਲ.ਭਾਰਤ
ডাটামেল্.ভারত
ڈاٹامیل.بھارت
డేటామెయిల్.భారత్
डाटामेल.भारत
داده.امارات
இந.இந்தியா
电邮.在线
датамэйл.рф
датамэйл.рус
දත්තතැපැල.ලංකා
ดาต้าเมล.ไทย
डाटाइंफोसिस.भारत
एक्सजेनप्लस.भारत

## Slide 17: Email Address Internationalization: EAI
Can you send email to this address ?
अजय.डाटा@uasg.tech
CC to
ajay@uasg.tech
Or
अजय@डाटा.भारत

## Slide 18: Join & Contribute
Please join our social media platform
@nbgp_community
Or
Visit out Wiki page for membership and current status
https://community.icann.org/display/croscomlgrprocedure/Neo-Brahmi+GP
Dr. Ajay Data
@ajaydata
Sarmad Husain
sarmad.hussain@icann.org