## RDS Workplan
Registration Directory Service (RDS) WHOIS2 Review Team (RDS-WHOIS2-RT) WORKPLAN
This document serves as a guide developed by the RDS-WHOIS2 review team. The plan is focused on key areas and milestones to be achieved during the review process and will be updated on an as-needed basis as the work progresses. For more information on the RDS-WHOIS2: see https://community.icann.org/display/WHO/RDS-WHOIS2+Review. Link to fact sheets: https://community.icann.org/display/WHO/Fact+Sheet
At Risk | Task Name | Start Date | End Date | Assigned To | Duration (days) | Completion Date | % Complete | Comments
| Assemble Review Team |  |  |  | 217 |  | 100%
| Appoint RDS-WHOIS2 Review Team | 2016-10-28 | 2017-06-02 | SO/AC Chairs | 217 | 2017-06-02 | 100% | See https://www.icann.org/news/announcement-2017-06-02-en
| Plan Review |  |  |  | 249 |  | 100%
| Administration | [5 empty] | 100%
| Determine leadership | 2017-06-05 | 2017-10-03 | RDS-WHOIS2 | 120 | 2017-10-03 | 100% | Completed in Brussels (2-3 October 2017)
| Determine role of observers | 2017-07-13 | 2017-08-13 | RDS-WHOIS2 | 31 | 2017-08-03 | 100% | Completed on plenary call #4
| Adopt legal docs (Conflict of Interest policy, Statement of Interest) | 2017-08-03 | 2017-09-14 | RDS-WHOIS2 | 42 | 2018-01-30 | 100% | See https://community.icann.org/display/WHO/Legal+Documents
| Define review team project management roles and responsibilities, incl, budget management | 2017-08-11 | 2017-10-03 | RDS-WHOIS2 | 53 | 2017-08-14 | 100% | Discussed on leadership call #3 (August 11).
| Identify need for and deliver a proposal on division of work | 2017-07-20 | 2017-10-20 | RDS-WHOIS2 | 92 | 2017-10-03 | 100% | Subgroups established in Brussels, 2-3 October 2017
| Develop and adopt template for "first pass planning questions" | 2017-10-03 | 2017-10-31 | RDS-WHOIS2 | 28 | 2018-10-19 | 100% | Template: https://tinyurl.com/ybh8sere
| Develop and adopt template for findings and recommendations | 2018-01-02 | 2018-02-09 | RDS-WHOIS2 | 38 | 2018-10-19 | 100% | Template: https://tinyurl.com/yabod7qs
| Define structure of subgroups reports | 2018-01-02 | 2018-02-09 | RDS-WHOIS2 | 38 | 2018-10-19 | 100% | Template: https://tinyurl.com/yabod7qs
| Define Terms of Reference & Work Plan | [5 empty] | 100%
| Develop methodology to prioritize issues to be addressed in scope, including validating issues against ICANN Bylaws | 2017-07-20 | 2017-09-14 | RDS-WHOIS2 | 56 | 2018-02-07 | 100%
| Adopt a framework that identifies the prioritized focus of the work (scope) | 2017-07-20 | 2017-10-03 | RDS-WHOIS2 | 75 | 2017-10-03 | 100%
| Adopt and publish terms of reference (ToR) | 2017-08-03 | 2018-02-02 | RDS-WHOIS2 | 183 | 2018-02-07 | 100%
| Adopt and publish work plan | 2017-09-07 | 2018-02-02 | RDS-WHOIS2 | 148 | 2018-02-02 | 100% | Submitted to Board
| Send adopted ToR and work plan to ICANN Board | 2017-10-20 | 2018-02-02 | RDS-WHOIS2 | 105 | 2018-02-09 | 100% | Submitted to Board
| Provide community with details on adopted ToR and work plan | 2018-01-29 | 2018-02-02 | RDS-WHOIS2 | 4 | 2018-02-27 | 100% | See https://www.icann.org/news/blog/rds-whois2-review-team-submits-terms-of-reference-and-work-plan
| Develop and adopt outreach plan | 2017-10-20 | 2018-01-22 | RDS-WHOIS2 | 94 | 2018-01-31 | 100% | Confirmed as adopted on leadership call #16
| Research & Studies |  |  |  | 249 |  | 93.33%
| Assemble repository of background materials | 2016-10-27 | 2018-01-31 | ICANN org | 461 | ongoing | 100% | Available on dedicated wiki page. ICANN org to continue populating, as requested
| Identify briefings/data sources needed | 2017-06-05 | 2018-02-09 | RDS-WHOIS2 | 249 | 2018-02-09 | 90%
| Determine requirements for independent expert(s) and - if necessary - develop statement of work | 2017-10-03 | 2018-02-09 | RDS-WHOIS2 | 129 | 2018-02-09 | 90%
| Conduct Review |  |  |  | 233 |  | 60.83%
Subgroups
| WHOIS 1 Review Team Recommendations | [5 empty] | 69.38%
| Administrative duties | [5 empty] | 100%
| Confirm members of the subgroup and determine rapporteur | 2017-10-03 | 2017-10-20 | Topic 1 Subgroups | 17 | 2017-12-08 | 100%
| Establish mandate, objectives and timeline for the work | 2017-10-03 | 2018-01-22 | Topic 1 Subgroups | 111 | 2018-03-12 | 100% | Using template referenced in row 14
| Determine topics for investigation and validate against ICANN Bylaws | 2017-10-03 | 2018-01-22 | Topic 1 Subgroups | 111 | 2018-03-12 | 100% | Using template referenced in row 19
| Identify briefings/data sources needed | 2017-10-03 | 2018-01-22 | Topic 1 Subgroups | 111 | 2018-03-12 | 100% | Using template referenced in row 19
| Determine requirements for independent expert(s) and – if necessary – develop statement of work | 2017-10-03 | 2018-01-22 | Topic 1 Subgroups | 111 | 2018-03-12 | 100% | Using template referenced in row 19
| Adopt statement of work and associated work plan | 2017-11-03 | 2018-01-22 | Topic 1 Subgroups | 80 | 2018-03-12 | 100% | Using template referenced in row 19
| Workplan execution | [5 empty] | 100%
| Review, analyze and summarize relevant documentation | 2017-10-20 | 2018-02-22 | Topic 1 Subgroups | 125 | 2018-04-10 | 100%
| Conduct investigation of identified objectives | 2017-11-03 | 2018-02-22 | Topic 1 Subgroups | 111 | 2018-04-10 | 100%
| Conduct relevant interviews as appropriate | 2017-11-03 | 2018-02-22 | Topic 1 Subgroups | 111 | 2018-04-10 | 100%
| Draft summary note of key findings | 2017-12-01 | 2018-02-22 | Topic 1 Subgroups | 83 | 2018-04-10 | 100%
| Prepare draft report section | [5 empty] | 77.5%
| Approve findings | 2018-02-22 | 2018-03-15 | Topic 1 Subgroups | 21 | 2018-04-10 | 100%
| Assemble draft recommendations using the designated review team template | 2018-02-22 | 2018-03-15 | Topic 1 Subgroups | 21 | 2018-04-10 | 100%
| Cross-check draft recommendations with scope and Bylaws | 2018-02-22 | 2018-03-15 | Topic 1 Subgroups | 21 | 2018-04-10 | 100%
| Produce subgroup report for subgroup members' approval | 2018-03-15 | 2018-03-22 | Topic 1 Subgroups | 7 |  | 90%
| Adopt & Circulate subgroup report to review team | 2018-03-22 | 2018-04-05 | Topic 1 Subgroups | 14 |  | 75%
| Present subgroup report and proposed recommendations to review team | 2018-04-05 | 2018-04-19 | Topic 1 Subgroups | 14 |  | 0% | Brussels face-to-face meeting 16-17-18 April 2018
| Refine draft report section | [5 empty] | 0%
| Incorporate edits suggested by the review team, as appropriate | 2018-04-19 | 2018-05-24 | Topic 1 Subgroups | 35 |  | 0%
| Anything New | [5 empty] | 58.54%
| Administrative duties | [5 empty] | 95.83%
| Confirm members of the subgroup and determine rapporteur | 2017-10-03 | 2017-10-20 | Subgroup 2 | 17 | 2017-12-08 | 100%
| Establish mandate, objectives and timeline for the work | 2017-10-03 | 2018-01-22 | Subgroup 2 | 111 | 2018-02-09 | 95% | Using template referenced in row 14
| Determine topics for investigation and validate against ICANN Bylaws | 2017-10-03 | 2018-01-22 | Subgroup 2 | 111 | 2018-02-09 | 95% | Using template referenced in row 14
| Identify briefings/data sources needed | 2017-10-03 | 2018-01-22 | Subgroup 2 | 111 | 2018-02-09 | 95% | Using template referenced in row 14
| Determine requirements for independent expert(s) and – if necessary – develop statement of work | 2017-10-03 | 2018-01-22 | Subgroup 2 | 111 | 2018-02-09 | 95% | Using template referenced in row 14
| Adopt statement of work and associated work plan | 2017-11-03 | 2018-01-22 | Subgroup 2 | 80 | 2018-02-09 | 95% | Using template referenced in row 14
| Workplan execution | [5 empty] | 90%
| Review, analyze and summarize relevant documentation | 2017-10-20 | 2018-02-22 | Subgroup 2 | 125 |  | 90%
| Conduct investigation of identified objectives | 2017-11-03 | 2018-02-22 | Subgroup 2 | 111 |  | 90%
| Conduct relevant interviews as appropriate | 2017-11-03 | 2018-02-22 | Subgroup 2 | 111 |  | 90%
| Draft summary note of key findings | 2017-12-01 | 2018-02-22 | Subgroup 2 | 83 |  | 90%
| Prepare draft report section | [5 empty] | 48.33%
| Approve findings | 2018-02-22 | 2018-03-15 | Subgroup 2 | 21 |  | 90%
| Assemble draft recommendations using the designated review team template | 2018-02-22 | 2018-03-15 | Subgroup 2 | 21 |  | 90%
| Cross-check draft recommendations with scope and Bylaws | 2018-02-22 | 2018-03-15 | Subgroup 2 | 21 |  | 90%
| Produce subgroup report for subgroup members' approval | 2018-03-15 | 2018-03-22 | Subgroup 2 | 7 |  | 20%
| Adopt & Circulate subgroup report to review team | 2018-03-22 | 2018-04-05 | Subgroup 2 | 14 |  | 0%
| Present subgroup report and proposed recommendations to review team | 2018-04-05 | 2018-04-19 | Subgroup 2 | 14 |  | 0% | Brussels face-to-face meeting 16-17-18 April 2018
| Refine draft report section | [5 empty] | 0%
| Incorporate edits suggested by the review team, as appropriate | 2018-05-10 | 2018-05-24 | Subgroup 2 | 14 |  | 0%
| Law Enforcement Needs | [5 empty] | 51.25%
| Administrative duties | [5 empty] | 100%
| Confirm members of the subgroup and determine rapporteur | 2017-10-03 | 2017-10-20 | Subgroup 3 | 17 | 2017-12-08 | 100%
| Establish mandate, objectives and timeline for the work | 2017-10-03 | 2018-01-22 | Subgroup 2 | 111 | 2018-02-26 | 100% | Using template referenced in row 14
| Determine topics for investigation and validate against ICANN Bylaws | 2017-10-03 | 2018-01-22 | Subgroup 3 | 111 | 2018-02-26 | 100% | Using template referenced in row 14
| Identify briefings/data sources needed | 2017-10-03 | 2018-01-22 | Subgroup 3 | 111 | 2018-02-26 | 100% | Using template referenced in row 14
| Determine requirements for independent expert(s) and – if necessary – develop statement of work | 2017-10-03 | 2018-01-22 | Subgroup 3 | 111 | 2018-02-26 | 100% | Using template referenced in row 14
| Adopt statement of work and associated work plan | 2017-11-03 | 2018-01-22 | Subgroup 3 | 80 | 2018-02-26 | 100% | Using template referenced in row 14
| Workplan execution | [5 empty] | 70%
| Review, analyze and summarize relevant documentation | 2017-10-20 | 2018-02-22 | Subgroup 3 | 125 |  | 70%
| Conduct investigation of identified objectives | 2017-11-03 | 2018-02-22 | Subgroup 3 | 111 |  | 70%
| Conduct relevant interviews as appropriate | 2017-11-03 | 2018-02-22 | Subgroup 3 | 111 |  | 70%
| Draft summary note of key findings | 2017-12-01 | 2018-02-22 | Subgroup 3 | 83 |  | 70%
| Prepare draft report section | [5 empty] | 35%
| Approve findings | 2018-02-22 | 2018-03-15 | Subgroup 3 | 21 |  | 70%
| Assemble draft recommendations using the designated review team template | 2018-02-22 | 2018-03-15 | Subgroup 3 | 21 |  | 70%
| Cross-check draft recommendations with scope and Bylaws | 2018-02-22 | 2018-03-15 | Subgroup 3 | 21 |  | 70%
| Produce subgroup report for subgroup members' approval | 2018-03-15 | 2018-03-22 | Subgroup 3 | 7 |  | 0%
| Adopt & Circulate subgroup report to review team | 2018-03-22 | 2018-04-05 | Subgroup 3 | 14 |  | 0%
| Present subgroup report and proposed recommendations to review team | 2018-04-05 | 2018-04-19 | Subgroup 3 | 14 |  | 0% | Brussels face-to-face meeting 16-17-18 April 2018
| Refine draft report section | [5 empty] | 0%
| Incorporate edits suggested by the review team, as appropriate | 2018-05-10 | 2018-05-24 | Subgroup 3 | 14 |  | 0%
| Consumer Trust | [5 empty] | 70.83%
| Administrative duties | [5 empty] | 100%
| Confirm members of the subgroup and determine rapporteur | 2017-10-03 | 2017-10-20 | Subgroup 4 | 17 | 2017-12-08 | 100%
| Establish mandate, objectives and timeline for the work | 2017-10-03 | 2018-01-22 | Subgroup 4 | 111 | 2018-03-20 | 100% | Using template referenced in row 14
| Determine topics for investigation and validate against ICANN Bylaws | 2017-10-03 | 2018-01-22 | Subgroup 4 | 111 | 2018-03-20 | 100% | Using template referenced in row 14
| Identify briefings/data sources needed | 2017-10-03 | 2018-01-22 | Subgroup 4 | 111 | 2018-03-20 | 100% | Using template referenced in row 14
| Determine requirements for independent expert(s) and – if necessary – develop statement of work | 2017-10-03 | 2018-01-22 | Subgroup 4 | 111 | 2018-03-20 | 100% | Using template referenced in row 14
| Adopt statement of work and associated work plan | 2017-11-03 | 2018-01-22 | Subgroup 4 | 80 | 2018-03-20 | 100% | Using template referenced in row 14
| Workplan execution | [5 empty] | 100%
| Review, analyze and summarize relevant documentation | 2017-10-20 | 2018-02-22 | Subgroup 4 | 125 | 2018-04-06 | 100%
| Conduct investigation of identified objectives | 2017-11-03 | 2018-02-22 | Subgroup 4 | 111 | 2018-04-06 | 100%
| Conduct relevant interviews as appropriate | 2017-11-03 | 2018-02-22 | Subgroup 4 | 111 | 2018-04-06 | 100%
| Draft summary note of key findings | 2017-12-01 | 2018-02-22 | Subgroup 4 | 83 | 2018-04-06 | 100%
| Prepare draft report section | [5 empty] | 83.33%
| Approve findings | 2018-02-22 | 2018-03-15 | Subgroup 4 | 21 | 2018-04-06 | 100%
| Assemble draft recommendations using the designated review team template | 2018-02-22 | 2018-03-15 | Subgroup 4 | 21 | 2018-04-06 | 100%
| Cross-check draft recommendations with scope and Bylaws | 2018-02-22 | 2018-03-15 | Subgroup 4 | 21 | 2018-04-06 | 100%
| Produce subgroup report for subgroup members' approval | 2018-03-15 | 2018-03-22 | Subgroup 4 | 7 | 2018-04-06 | 100%
| Adopt & Circulate subgroup report to review team | 2018-03-22 | 2018-04-05 | Subgroup 4 | 14 | 2018-04-06 | 100%
| Present subgroup report and proposed recommendations to review team | 2018-04-05 | 2018-04-19 | Subgroup 4 | 14 |  | 0% | Brussels face-to-face meeting 16-17-18 April 2018
| Refine draft report section | [5 empty] | 0%
| Incorporate edits suggested by the review team, as appropriate | 2018-05-10 | 2018-05-24 | Subgroup 4 | 14 |  | 0%
| Safeguard Registrant Data | [5 empty] | 54.17%
| Administrative duties | [5 empty] | 100%
| Confirm members of the subgroup and determine rapporteur | 2017-10-03 | 2017-10-20 | Subgroup 5 | 17 | 2017-12-08 | 100%
| Establish mandate, objectives and timeline for the work | 2017-10-03 | 2018-01-22 | Subgroup 5 | 111 | 2018-03-04 | 100% | Using template referenced in row 14
| Determine topics for investigation and validate against ICANN Bylaws | 2017-10-03 | 2018-01-22 | Subgroup 5 | 111 | 2018-03-04 | 100% | Using template referenced in row 14
| Identify briefings/data sources needed | 2017-10-03 | 2018-01-22 | Subgroup 5 | 111 | 2018-03-04 | 100% | Using template referenced in row 14
| Determine requirements for independent expert(s) and – if necessary – develop statement of work | 2017-10-03 | 2018-01-22 | Subgroup 5 | 111 | 2018-03-04 | 100% | Using template referenced in row 14
| Adopt statement of work and associated work plan | 2017-11-03 | 2018-01-22 | Subgroup 5 | 80 | 2018-03-04 | 100% | Using template referenced in row 14
| Workplan execution | [5 empty] | 70%
| Review, analyze and summarize relevant documentation | 2017-10-20 | 2018-02-22 | Subgroup 5 | 125 |  | 70%
| Conduct investigation of identified objectives | 2017-11-03 | 2018-02-22 | Subgroup 5 | 111 |  | 70%
| Conduct relevant interviews as appropriate | 2017-11-03 | 2018-02-22 | Subgroup 5 | 111 |  | 70%
| Draft summary note of key findings | 2017-12-01 | 2018-02-22 | Subgroup 5 | 83 |  | 70%
| Prepare draft report section | [5 empty] | 46.67%
| Approve findings | 2018-02-22 | 2018-03-15 | Subgroup 5 | 21 |  | 70%
| Assemble draft recommendations using the designated review team template | 2018-02-22 | 2018-03-15 | Subgroup 5 | 21 |  | 70%
| Cross-check draft recommendations with scope and Bylaws | 2018-02-22 | 2018-03-15 | Subgroup 5 | 21 |  | 70%
| Produce subgroup report for subgroup members' approval | 2018-03-15 | 2018-03-22 | Subgroup 5 | 7 |  | 70%
| Adopt & Circulate subgroup report to review team | 2018-03-22 | 2018-04-05 | Subgroup 5 | 14 |  | 0%
| Present subgroup report and proposed recommendations to review team | 2018-04-05 | 2018-04-19 | Subgroup 5 | 14 |  | 0% | Brussels face-to-face meeting 16-17-18 April 2018
| Refine draft report section | [5 empty] | 0%
| Incorporate edits suggested by the review team, as appropriate | 2018-05-10 | 2018-05-24 | Subgroup 5 | 14 |  | 0%
Review Team
| Draft Report |  |  |  | 297 |  | 0%
| Administrative duties | [5 empty] | 0%
| Adopt report format | 2018-01-02 | 2018-04-05 | RDS-WHOIS2 | 93 |  | 0% | ICANN org to provide a template
| Internal review | [5 empty] | 0%
| Provide input on subgroups' draft report | 2018-04-05 | 2018-05-10 | RDS-WHOIS2 | 35 |  | 0% | Brussels face-to-face meeting 16-17-18 April 2018
| Cross-check draft recommendations with scope and Bylaws | 2018-04-05 | 2018-05-10 | RDS-WHOIS2 | 35 |  | 0% | Incl. at Brussels face-to-face meeting 16-17-18 April 2018
| Pre-approve draft recommendations | 2018-04-05 | 2018-05-24 | RDS-WHOIS2 | 49 |  | 0% | Incl. at Brussels face-to-face meeting 16-17-18 April 2018
| Approve draft findings and recommendations | 2018-05-24 | 2018-06-28 | RDS-WHOIS2 | 35 |  | 0%
| Outreach on draft recommendations | [5 empty] | 0%
| Seek community input on draft recommendations | 2018-06-25 | 2018-06-28 | RDS-WHOIS2 | 3 |  | 0% | ICANN 62 (25-28 June 2018)
| Seek input and guidance from the Board Caucus Group and ICANN Subject Matter Experts (SMEs) on implementability of draft recommendations | 2018-06-25 | 2018-06-28 | RDS-WHOIS2 | 3 |  | 0% | ICANN 62 (25-28 June 2018)
| Assembling draft report | [5 empty] | 0%
| Produce draft report | 2018-06-28 | 2018-07-13 | RDS-WHOIS2 | 15 |  | 0%
| Publishing draft report | [5 empty] | 0%
| Approve draft report for public comment | 2018-06-28 | 2018-07-31 | RDS-WHOIS2 | 33 |  | 0%
| Send approved designated draft report sections to language services | 2018-07-31 | 2018-08-07 | ICANN org | 7 |  | 0% | Executive Summary & Recommendations
| Public comment and outreach on draft report | [5 empty] | 0%
| Publish draft report for public comment | 2018-08-07 | 2018-10-05 | ICANN org | 59 |  | 0%
| Seek Board Caucus group and ICANN organization’s input on implementability of draft recommendations | 2018-08-20 | 2018-10-05 | RDS-WHOIS2 | 46 |  | 0%
| Seek community’s input on implementability of draft recommendations | 2018-06-25 | 2018-10-05 | RDS-WHOIS2 | 102 |  | 0% | Webinars
| Produce summary of public comments | 2018-10-05 | 2018-10-19 | ICANN org | 14 |  | 0%
| Adopt public comment summary for publication | 2018-10-19 | 2018-10-26 | RDS-WHOIS2 | 7 |  | 0% | ICANN 63 (20-26 October 2018)
| Final Report |  |  |  | 77 |  | 0%
| Updating draft report | [5 empty] | 0%
| Assemble final recommendations and update draft report based on public comments received | 2018-10-05 | 2018-11-30 | RDS-WHOIS2 | 56 |  | 0% | Including during ICANN63
| Cross-check final recommendations with scope and Bylaws | 2018-10-05 | 2018-11-30 | RDS-WHOIS2 | 56 |  | 0% | Including during ICANN63
| Approval process | [5 empty] | 0%
| Approve final findings and recommendations | 2018-12-07 | 2018-12-21 | RDS-WHOIS2 | 14 |  | 0%
| Approve final report for submission to ICANN Board | 2018-12-07 | 2018-12-21 | RDS-WHOIS2 | 14 |  | 0%
| Outreach on draft final recommendations | [5 empty] | 0%
| Provide community with overview of findings and draft final recommendations | 2018-11-30 | 2018-12-21 | RDS-WHOIS2 | 21 |  | 0% | Webinar/blog post
| Send final report | [5 empty] | 0%
| Send final report to ICANN Board | 2018-12-21 | 2018-12-21 | RDS-WHOIS2 | 0 |  | 0%
| Publish final report | 2018-12-21 | 2018-12-21 | ICANN org | 0 |  | 0%
| Send final report to language services | 2018-12-21 | 2018-12-21 | ICANN org | 0 |  | 0%
| Provide community with overview of findings and final recommendations | 2019-01-07 | 2019-01-11 | RDS-WHOIS2 | 4 |  | 0% | Webinar
| Implementation Planning & Feedback |  |  |  | 93 |  | 0%
| Complete ICANN organization survey on review process | 2019-01-08 | 2019-02-08 | RDS-WHOIS2 | 31 |  | 0%
| Identify one or two review team members to remain available for clarification as may be needed during the implementation planning phase | 2018-11-07 | 2018-12-21 | RDS-WHOIS2 | 44 |  | 0%
| Face to Face Meetings | [5 empty] | 25%
| #1 Brussels | 2017-10-02 | 2017-10-03 |  |  |  | 100%
| #2 Brussels | 2018-04-16 | 2018-04-18 |  |  |  | 0%
| #3 ICANN 62 | [5 empty] | 0% | Dates TBC
| #4 ICANN 63 | [5 empty] | 0% | Dates TBD