## SSR2 Workplan 14082017
At Risk | Task Name | Start Date | End Date | Assigned To | Duration | % Complete | Predecessors | Comments
| Assemble Review Team | 2017-02-01 | 2017-02-28 |  | 20d | 100%
| Appoint SSR2 team | 2017-02-01 | 2017-02-28 | ICANN | 20d | 100%
| Plan Review | 2017-02-01 | 2018-06-29 |  | 368d | 4%
| Determine leadership | 2017-03-01 | 2017-03-31 | SSR2 Team | 23d | 100%
| Determine role of observers | 2017-03-01 | 2017-05-01 | SSR2 Team | 44d
TRUE | Adopt legal docs (Conflict of Interest policy, NDA, Statement of Interest) | 2017-08-01 | 2017-08-31 | SSR2 Team | 23d | 0%
| Develop Terms of Reference and ways of working | 2017-04-01 | 2017-05-17 | SSR2 Team | 34d | 10%
| Develop methodology to prioritize issues to be addressed in scope, including validating issues against ICANN Bylaws | 2017-05-01 | 2017-05-10 |  | 8d
| Publish Terms of Reference | 2017-05-17 | 2017-05-17 | SSR2 Team | 1d | 100%
TRUE | Define Review Team project management roles and responsibilities, including budget management | 2017-05-01
TRUE | Identify need for and deliver a proposal on division of work | 2017-04-01
| Communicate adoption of ToR and Work Plan with ICANN Board | 2017-05-17 | 2017-05-17 |  | 1d
TRUE | Develop outreach plan | 2017-08-01 | 2017-08-31 | SSR2 Team | 23d | 0%
| Determine requirements for consultant and develop statement of work | 2017-05-01 | 2017-08-31 |  | 89d
| Subgroups to Develop a Workplan | 2017-08-01 | 2017-08-31 | Subgroups | 23d | 80%
Research and Studies
| Assemble repository of background materials | 2017-03-01 | 2018-06-29 |  | 348d
| Identify briefings / data sources needed | 2017-03-01 | 2017-09-29 |  | 153d
| Identify research needs and develop requirements | 2017-03-01 | 2017-08-31 |  | 132d
| Identify expert resources for outreach and data gathering | 2017-03-01 | 2017-08-31 |  | 132d
| Determine requirements for consultant and develop Statement of Work | 2017-02-01 | 2017-08-31 |  | 152d
| Conduct Review | 2017-08-01 | 2017-12-15 |  | 99d
| Investigation and Analysis | 2017-08-01 | 2017-12-15 |  | 99d
| Subgroup 1 - SSR1 Review | 2017-08-01 | 2017-12-15 | Subgroup 1 | 99d
| Administrative Duties | 2017-08-01 | 2017-09-29 | Subgroup 1 | 44d
| Develop Subgroup Meeting Schedule | 2017-08-01 | 2017-09-15 | Subgroup 1 | 34d
| Review Workplan and Role Assignment | 2017-08-01 | 2017-09-15 | Subgroup 1 | 34d
| Decide on Group Support | 2017-08-01 | 2017-09-15 | Subgroup 1 | 34d
| Decide on Interviews (how many will be conducted; who will be interviewed; what are the standardized interview questions; set interview dates) | 2017-08-01 | 2017-09-29 | Subgroup 1 | 44d
| Decide on Site Visits (how many will be conducted; where should be visited; set travel dates) | 2017-08-01 | 2017-09-29 | Subgroup 1 | 44d
| Workplan Execution | 2017-10-01 | 2017-12-15 | Subgroup 1 | 56d
| SSR Framework | 2017-10-01 | 2017-12-15 | Subgroup 1 | 56d
| Review, Analyze and Summarize Relevant Documentation | 2017-10-01 | 2017-10-20 | Subgroup 1 | 16d
| Document initial recommendations | 2017-10-01 | 2017-10-20 | Subgroup 1 | 16d
| Conduct Relevant Interviews | 2017-10-22 | 2017-12-15 | Subgroup 1 | 41d
| Draft Interview Transcripts | 2017-10-22 | 2017-12-15 | Subgroup 1 | 41d
| Write Summary Paragraphs for Interview Findings | 2017-10-22 | 2017-12-15 | Subgroup 1 | 41d
| Conduct Relevant Site Visits | 2017-10-22 | 2017-12-15 | Subgroup 1 | 41d
| Draft Summary Note of Key Observations | 2017-10-22 | 2017-12-15 | Subgroup 1 | 41d
| ICANN's SSR Role & Remit within its limited Mission | 2017-10-01 | 2017-12-15 | Subgroup 1 | 56d
| Review, Analyze and Summarize Relevant Documentation | 2017-10-01 | 2017-10-20 | Subgroup 1 | 16d
| Document initial recommendations | 2017-10-01 | 2017-10-20 | Subgroup 1 | 16d
| Conduct Relevant Interviews | 2017-10-22 | 2017-12-15 | Subgroup 1 | 41d
| Draft Interview Transcripts | 2017-10-22 | 2017-12-15 | Subgroup 1 | 41d
| Write Summary Paragraphs for Interview Findings | 2017-10-22 | 2017-12-15 | Subgroup 1 | 41d
| Conduct Relevant Site Visits | 2017-10-22 | 2017-12-15 | Subgroup 1 | 41d
| Draft Summary Note of Key Observations | 2017-10-22 | 2017-12-15 | Subgroup 1 | 41d
| SSR Relationships to Support ICANN's Work | 2017-10-01 | 2017-12-15 | Subgroup 1 | 56d
| Review, Analyze and Summarize Relevant Documentation | 2017-10-01 | 2017-10-20 | Subgroup 1 | 16d
| Document initial recommendations | 2017-10-01 | 2017-10-20 | Subgroup 1 | 16d
| Conduct Relevant Interviews | 2017-10-22 | 2017-12-15 | Subgroup 1 | 41d
| Draft Interview Transcripts | 2017-10-22 | 2017-12-15 | Subgroup 1 | 41d
| Write Summary Paragraphs for Interview Findings | 2017-10-22 | 2017-12-15 | Subgroup 1 | 41d
| Conduct Relevant Site Visits | 2017-10-22 | 2017-12-15 | Subgroup 1 | 41d
| Draft Summary Note of Key Observations | 2017-10-22 | 2017-12-15 | Subgroup 1 | 41d
| SSR Community Outreach and Info Sharing | 2017-10-01 | 2017-12-15 | Subgroup 1 | 56d
| Review, Analyze and Summarize Relevant Documentation | 2017-10-01 | 2017-10-20 | Subgroup 1 | 16d
| Document initial recommendations | 2017-10-01 | 2017-10-20 | Subgroup 1 | 16d
| Conduct Relevant Interviews | 2017-10-22 | 2017-12-15 | Subgroup 1 | 41d
| Draft Interview Transcripts | 2017-10-22 | 2017-12-15 | Subgroup 1 | 41d
| Write Summary Paragraphs for Interview Findings | 2017-10-22 | 2017-12-15 | Subgroup 1 | 41d
| Conduct Relevant Site Visits | 2017-10-22 | 2017-12-15 | Subgroup 1 | 41d
| Draft Summary Note of Key Observations | 2017-10-22 | 2017-12-15 |  | 41d
| Compliance | 2017-10-01 | 2017-12-15 | Subgroup 1 | 56d
| Review, Analyze and Summarize Relevant Documentation | 2017-10-01 | 2017-10-20 | Subgroup 1 | 16d
| Document initial recommendations | 2017-10-01 | 2017-10-20 | Subgroup 1 | 16d
| Conduct Relevant Interviews | 2017-10-22 | 2017-12-15 | Subgroup 1 | 41d
| Draft Interview Transcripts | 2017-10-22 | 2017-12-15 | Subgroup 1 | 41d
| Write Summary Paragraphs for Interview Findings | 2017-10-22 | 2017-12-15 | Subgroup 1 | 41d
| Conduct Relevant Site Visits | 2017-10-22 | 2017-12-15 | Subgroup 1 | 41d
| Draft Summary Note of Key Observations | 2017-10-22 | 2017-12-15 | Subgroup 1 | 41d
| Subgroup 2 - ICANN SSR | 2017-08-01 | 2017-12-15 | Subgroup 2 | 99d
| Administrative Duties | 2017-08-01 | 2017-09-29 | Subgroup 2 | 44d
| Develop Subgroup Meeting Schedule | 2017-08-01 | 2017-09-15 | Subgroup 2 | 34d
| Review Workplan and Role Assignment | 2017-08-01 | 2017-09-15 | Subgroup 2 | 34d
| Decide on Group Support | 2017-08-01 | 2017-09-15 | Subgroup 2 | 34d
| Decide on Interviews (how many will be conducted; who will be interviewed; what are the standardized interview questions; set interview dates) | 2017-08-01 | 2017-09-29 | Subgroup 2 | 44d
| Decide on Site Visits (how many will be conducted; where should be visited; set travel dates) | 2017-08-01 | 2017-09-29 | Subgroup 2 | 44d
| Workplan Execution | 2017-10-01 | 2017-12-15 | Subgroup 2 | 56d
| Information Security Management System | 2017-10-01 | 2017-12-15 | Subgroup 2 | 56d
| Review, Analyze and Summarize Relevant Documentation | 2017-10-01 | 2017-10-20 | Subgroup 2 | 16d
| Document initial recommendations | 2017-10-01 | 2017-10-20 | Subgroup 2 | 16d
| Conduct Relevant Interviews | 2017-10-22 | 2017-12-15 | Subgroup 2 | 41d
| Draft Interview Transcripts | 2017-10-22 | 2017-12-15 | Subgroup 2 | 41d
| Write Summary Paragraphs for Interview Findings | 2017-10-22 | 2017-12-15 | Subgroup 2 | 41d
| Conduct Relevant Site Visits | 2017-10-22 | 2017-12-15 | Subgroup 2 | 41d
| Draft Summary Note of Key Observations | 2017-10-22 | 2017-12-15 | Subgroup 2 | 41d
| Business Continuity Management System | 2017-10-01 | 2017-12-15 | Subgroup 2 | 56d
| Review, Analyze and Summarize Relevant Documentation | 2017-10-01 | 2017-10-20 | Subgroup 2 | 16d
| Document initial recommendations | 2017-10-01 | 2017-10-20 | Subgroup 2 | 16d
| Conduct Relevant Interviews | 2017-10-22 | 2017-12-15 | Subgroup 2 | 41d
| Draft Interview Transcripts | 2017-10-22 | 2017-12-15 | Subgroup 2 | 41d
| Write Summary Paragraphs for Interview Findings | 2017-10-22 | 2017-12-15 | Subgroup 2 | 41d
| Conduct Relevant Site Visits | 2017-10-22 | 2017-12-15 | Subgroup 2 | 41d
| Draft Summary Note of Key Observations | 2017-10-22 | 2017-12-15 | Subgroup 2 | 41d
| Scope of ICANN's SSR Responsibilities | 2017-10-01 | 2017-12-15 | Subgroup 2 | 56d
| Review, Analyze and Summarize Relevant Documentation | 2017-10-01 | 2017-10-20 | Subgroup 2 | 16d
| Document initial recommendations | 2017-10-01 | 2017-10-20 | Subgroup 2 | 16d
| Conduct Relevant Interviews | 2017-10-22 | 2017-12-15 | Subgroup 2 | 41d
| Draft Interview Transcripts | 2017-10-22 | 2017-12-15 | Subgroup 2 | 41d
| Write Summary Paragraphs for Interview Findings | 2017-10-22 | 2017-12-15 | Subgroup 2 | 41d
| Conduct Relevant Site Visits | 2017-10-22 | 2017-12-15 | Subgroup 2 | 41d
| Draft Summary Note of Key Observations | 2017-10-22 | 2017-12-15 | Subgroup 2 | 41d
| ICANN Compliance | 2017-10-01 | 2017-12-15 | Subgroup 2 | 56d
| Review, Analyze and Summarize Relevant Documentation | 2017-10-01 | 2017-10-20 | Subgroup 2 | 16d
| Document initial recommendations | 2017-10-01 | 2017-10-20 | Subgroup 2 | 16d
| Conduct Relevant Interviews | 2017-10-22 | 2017-12-15 | Subgroup 2 | 41d
| Draft Interview Transcripts | 2017-10-22 | 2017-12-15 | Subgroup 2 | 41d
| Write Summary Paragraphs for Interview Findings | 2017-10-22 | 2017-12-15 | Subgroup 2 | 41d
| Conduct Relevant Site Visits | 2017-10-22 | 2017-12-15 | Subgroup 2 | 41d
| Draft Summary Note of Key Observations | 2017-10-22 | 2017-12-15 | Subgroup 2 | 41d
| Subgroup 3 - DNS SSR | 2017-08-01 | 2017-12-15 | Subgroup 3 | 99d
| Administrative Duties | 2017-08-01 | 2017-09-29 | Subgroup 3 | 44d
| Develop Subgroup Meeting Schedule | 2017-08-01 | 2017-09-15 | Subgroup 3 | 34d
| Review Workplan and Role Assignment | 2017-08-01 | 2017-09-15 | Subgroup 3 | 34d
| Decide on Group Support | 2017-08-01 | 2017-09-15 | Subgroup 3 | 34d
| Decide on Interviews (how many will be conducted; who will be interviewed; what are the standardized interview questions; set interview dates) | 2017-08-01 | 2017-09-29 | Subgroup 3 | 44d
| Decide on Site Visits (how many will be conducted; where should be visited; set travel dates) | 2017-08-01 | 2017-09-29 | Subgroup 3 | 44d
| Workplan Execution | 2017-10-01 | 2017-12-15 | Subgroup 3 | 56d
| Root Zone Management Practices | 2017-10-01 | 2017-12-15 | Subgroup 3 | 56d
| Review, Analyze and Summarize Relevant Documentation | 2017-10-01 | 2017-10-20 | Subgroup 3 | 16d
| Document initial recommendations | 2017-10-01 | 2017-10-20 | Subgroup 3 | 16d
| Conduct Relevant Interviews | 2017-10-22 | 2017-12-15 | Subgroup 3 | 41d
| Draft Interview Transcripts | 2017-10-22 | 2017-12-15 | Subgroup 3 | 41d
| Write Summary Paragraphs for Interview Findings | 2017-10-22 | 2017-12-15 | Subgroup 3 | 41d
| Conduct Relevant Site Visits | 2017-10-22 | 2017-12-15 | Subgroup 3 | 41d
| Draft Summary Note of Key Observations | 2017-10-22 | 2017-12-15 | Subgroup 3 | 41d
| Change Management | 2017-10-01 | 2017-12-15 | Subgroup 3 | 56d
| Review, Analyze and Summarize Relevant Documentation | 2017-10-01 | 2017-10-20 | Subgroup 3 | 16d
| Document initial recommendations | 2017-10-01 | 2017-10-20 | Subgroup 3 | 16d
| Conduct Relevant Interviews | 2017-10-22 | 2017-12-15 | Subgroup 3 | 41d
| Draft Interview Transcripts | 2017-10-22 | 2017-12-15 | Subgroup 3 | 41d
| Write Summary Paragraphs for Interview Findings | 2017-10-22 | 2017-12-15 | Subgroup 3 | 41d
| Conduct Relevant Site Visits | 2017-10-22 | 2017-12-15 | Subgroup 3 | 41d
| Draft Summary Note of Key Observations | 2017-10-22 | 2017-12-15 | Subgroup 3 | 41d
| Roles and Responsibilities | 2017-10-01 | 2017-12-15 | Subgroup 3 | 56d
| Review, Analyze and Summarize Relevant Documentation | 2017-10-01 | 2017-10-20 | Subgroup 3 | 16d
| Document initial recommendations | 2017-10-01 | 2017-10-20 | Subgroup 3 | 16d
| Conduct Relevant Interviews | 2017-10-22 | 2017-12-15 | Subgroup 3 | 41d
| Draft Interview Transcripts | 2017-10-22 | 2017-12-15 | Subgroup 3 | 41d
| Write Summary Paragraphs for Interview Findings | 2017-10-22 | 2017-12-15 | Subgroup 3 | 41d
| Conduct Relevant Site Visits | 2017-10-22 | 2017-12-15 | Subgroup 3 | 41d
| Draft Summary Note of Key Observations | 2017-10-22 | 2017-12-15 | Subgroup 3 | 41d
| Abuses and Threats | 2017-10-01 | 2017-12-15 | Subgroup 3 | 56d
| Review, Analyze and Summarize Relevant Documentation | 2017-10-01 | 2017-10-20 | Subgroup 3 | 16d
| Document initial recommendations | 2017-10-01 | 2017-10-20 | Subgroup 3 | 16d
| Conduct Relevant Interviews | 2017-10-22 | 2017-12-15 | Subgroup 3 | 41d
| Draft Interview Transcripts | 2017-10-22 | 2017-12-15 | Subgroup 3 | 41d
| Write Summary Paragraphs for Interview Findings | 2017-10-22 | 2017-12-15 | Subgroup 3 | 41d
| Conduct Relevant Site Visits | 2017-10-22 | 2017-12-15 | Subgroup 3 | 41d
| Draft Summary Note of Key Observations | 2017-10-22 | 2017-12-15 | Subgroup 3 | 41d
| Subgroup 4 - Future Challenges | 2017-08-01 | 2017-12-15 | Subgroup 4 | 99d
| Administrative Duties | 2017-08-01 | 2017-09-29 | Subgroup 4 | 44d
| Develop Subgroup Meeting Schedule | 2017-08-01 | 2017-09-15 | Subgroup 1 | 34d
| Review Workplan and Role Assignment | 2017-08-01 | 2017-09-15 | Subgroup 1 | 34d
| Decide on Group Support | 2017-08-01 | 2017-09-15 | Subgroup 1 | 34d
| Decide on Interviews (how many will be conducted; who will be interviewed; what are the standardized interview questions; set interview dates) | 2017-08-01 | 2017-09-29 | Subgroup 1 | 44d
| Decide on Site Visits (how many will be conducted; where should be visited; set travel dates) | 2017-08-01 | 2017-09-29 | Subgroup 1 | 44d
| Workplan Execution | 2017-08-01 | 2017-12-15 | Subgroup 4 | 99d
TRUE | TBD | 2017-08-01 | 2017-12-15 | Subgroup 4 | 99d
| Subgroup 5 - IANA Transition | 2017-08-01 | 2017-12-15 | Subgroup 5 | 99d
| Administrative Duties | 2017-08-01 | 2017-09-29 | Subgroup 5 | 44d
| Develop Subgroup Meeting Schedule | 2017-08-01 | 2017-09-15 | Subgroup 1 | 34d
| Review Workplan and Role Assignment | 2017-08-01 | 2017-09-15 | Subgroup 1 | 34d
| Decide on Group Support | 2017-08-01 | 2017-09-15 | Subgroup 1 | 34d
| Decide on Interviews (how many will be conducted; who will be interviewed; what are the standardized interview questions; set interview dates) | 2017-08-01 | 2017-09-29 | Subgroup 1 | 44d
| Decide on Site Visits (how many will be conducted; where should be visited; set travel dates) | 2017-08-01 | 2017-09-29 | Subgroup 1 | 44d
| Workplan Execution | 2017-10-01 | 2017-12-15 | Subgroup 5 | 56d
| Business Continuity Plan | 2017-10-01 | 2017-12-15 | Subgroup 5 | 56d
| Review, Analyze and Summarize Relevant Documentation | 2017-10-01 | 2017-10-20 | Subgroup 5 | 16d
| Document initial recommendations | 2017-10-01 | 2017-10-20 | Subgroup 5 | 16d
| Conduct Relevant Interviews | 2017-10-22 | 2017-12-15 | Subgroup 5 | 41d
| Draft Interview Transcripts | 2017-10-22 | 2017-12-15 | Subgroup 5 | 41d
| Write Summary Paragraphs for Interview Findings | 2017-10-22 | 2017-12-15 | Subgroup 5 | 41d
| Conduct Relevant Site Visits | 2017-10-22 | 2017-12-15 | Subgroup 5 | 41d
| Draft Summary Note of Key Observations | 2017-10-22 | 2017-12-15 | Subgroup 5 | 41d
| RZMs | 2017-10-01 | 2017-12-15 | Subgroup 5 | 56d
| Review, Analyze and Summarize Relevant Documentation | 2017-10-01 | 2017-10-20 | Subgroup 5 | 16d
| Document initial recommendations | 2017-10-01 | 2017-10-20 | Subgroup 5 | 16d
| Conduct Relevant Interviews | 2017-10-22 | 2017-12-15 | Subgroup 5 | 41d
| Draft Interview Transcripts | 2017-10-22 | 2017-12-15 | Subgroup 5 | 41d
| Write Summary Paragraphs for Interview Findings | 2017-10-22 | 2017-12-15 | Subgroup 5 | 41d
| Conduct Relevant Site Visits | 2017-10-22 | 2017-12-15 | Subgroup 5 | 41d
| Draft Summary Note of Key Observations | 2017-10-22 | 2017-12-15 | Subgroup 5 | 41d
| ICANN Relationships | 2017-10-01 | 2017-12-15 | Subgroup 5 | 56d
| Review, Analyze and Summarize Relevant Documentation | 2017-10-01 | 2017-10-20 | Subgroup 5 | 16d
| Document initial recommendations | 2017-10-01 | 2017-10-20 | Subgroup 5 | 16d
| Conduct Relevant Interviews | 2017-10-22 | 2017-12-15 | Subgroup 5 | 41d
| Draft Interview Transcripts | 2017-10-22 | 2017-12-15 | Subgroup 5 | 41d
| Write Summary Paragraphs for Interview Findings | 2017-10-22 | 2017-12-15 | Subgroup 5 | 41d
| Conduct Relevant Site Visits | 2017-10-22 | 2017-12-15 | Subgroup 5 | 41d
| Draft Summary Note of Key Observations | 2017-10-22 | 2017-12-15 | Subgroup 5 | 41d
| TZMDb Status Review | 2017-10-01 | 2017-12-15 | Subgroup 5 | 56d
| Review, Analyze and Summarize Relevant Documentation | 2017-10-01 | 2017-10-20 | Subgroup 5 | 16d
| Document initial recommendations | 2017-10-01 | 2017-10-20 | Subgroup 5 | 16d
| Conduct Relevant Interviews | 2017-10-22 | 2017-12-15 | Subgroup 5 | 41d
| Draft Interview Transcripts | 2017-10-22 | 2017-12-15 | Subgroup 5 | 41d
| Write Summary Paragraphs for Interview Findings | 2017-10-22 | 2017-12-15 | Subgroup 5 | 41d
| Conduct Relevant Site Visits | 2017-10-22 | 2017-12-15 | Subgroup 5 | 41d
| Draft Summary Note of Key Observations | 2017-10-22 | 2017-12-15 | Subgroup 5 | 41d
| Training and Staff Retention | 2017-10-01 | 2017-12-15 | Subgroup 5 | 56d
| Review, Analyze and Summarize Relevant Documentation | 2017-10-01 | 2017-10-20 | Subgroup 5 | 16d
| Document initial recommendations | 2017-10-01 | 2017-10-20 | Subgroup 5 | 16d
| Conduct Relevant Interviews | 2017-10-22 | 2017-12-15 | Subgroup 5 | 41d
| Draft Interview Transcripts | 2017-10-22 | 2017-12-15 | Subgroup 5 | 41d
| Write Summary Paragraphs for Interview Findings | 2017-10-22 | 2017-12-15 | Subgroup 5 | 41d
| Conduct Relevant Site Visits | 2017-10-22 | 2017-12-15 | Subgroup 5 | 41d
| Draft Summary Note of Key Observations | 2017-10-22 | 2017-12-15 | Subgroup 5 | 41d
| Prepare draft report | 2017-11-01 | 2018-03-16 |  | 98d
| Subgroup 1 - SSR1 Review | 2017-12-18 | 2018-01-19 | Subgroup 1 | 25d
| Review Relevant Document Summaries and Initial Recommendation Lists | 2017-12-18 | 2017-12-22 | Subgroup 1 | 5d
| Discuss Recommendations with Subgroup Members | 2017-12-18 | 2017-12-22 | Subgroup 1 | 5d
| Draft Report | 2017-12-25 | 2018-01-19 | Subgroup 1 | 20d
| Subgroup 2 - ICANN SSR | 2017-12-18 | 2018-01-19 | Subgroup 2 | 25d
| Review Relevant Document Summaries and Initial Recommendation Lists | 2017-12-18 | 2017-12-22 | Subgroup 2 | 5d
| Discuss Recommendations with Subgroup Members | 2017-12-18 | 2017-12-22 | Subgroup 2 | 5d
| Draft Report | 2017-12-25 | 2018-01-19 | Subgroup 2 | 20d
| Subgroup 3 - DNS SSR | 2017-12-18 | 2018-01-19 | Subgroup 3 | 25d
| Review Relevant Document Summaries and Initial Recommendation Lists | 2017-12-18 | 2017-12-22 | Subgroup 3 | 5d
| Discuss Recommendations with Subgroup Members | 2017-12-18 | 2017-12-22 | Subgroup 3 | 5d
| Draft Report | 2017-12-25 | 2018-01-19 | Subgroup 3 | 20d
| Subgroup 4 - Future Challenges | 2017-12-18 | 2018-01-19 | Subgroup 4 | 25d
| Review Relevant Document Summaries and Initial Recommendation Lists | 2017-12-18 | 2017-12-22 | Subgroup 4 | 5d
| Discuss Recommendations with Subgroup Members | 2017-12-18 | 2017-12-22 | Subgroup 4 | 5d
| Draft Report | 2017-12-25 | 2018-01-19 | Subgroup 4 | 20d
| Subgroup 5 - IANA Transition | 2017-12-18 | 2018-01-19 | Subgroup 5 | 25d
| Review Relevant Document Summaries and Initial Recommendation Lists | 2017-12-18 | 2017-12-22 | Subgroup 5 | 5d
| Discuss Recommendations with Subgroup Members | 2017-12-18 | 2017-12-22 | Subgroup 5 | 5d
| Draft Report | 2017-12-25 | 2018-01-19 | Subgroup 5 | 20d
| Internal Review | 2017-11-01 | 2018-03-16 |  | 98d
| Administrative Duties | 2017-11-01 | 2017-11-10 |  | 8d
| Finalize travel for Brussels Drafting Meeting | 2017-11-01 | 2017-11-10 | SSR2, Subgroups | 8d
| Internal Review Meeting | 2018-01-19 | 2018-03-16 |  | 41d
| Send final reports to SSR2 Team | 2018-01-19 | 2018-01-19 | Subgroups | 1d
| SSR2 Team Review Reports and provide feedback | 2018-01-22 | 2018-01-24 | SSR2 Team | 3d
| Subgroups present findings | 2018-01-22 | 2018-01-24 | Subgroups | 3d
| Subgroups input SSR2 Feedback into Draft Report | 2018-01-24 | 2018-03-16 | Subgroups | 38d
| Develop and adopt template for findings and recommendation | 2018-01-25 | 2018-01-31 |  | 5d
| Liaise with Board Caucus if appropriate | 2018-01-29 | 2018-02-16 |  | 15d
| Publish Draft Online | 2018-02-19 | 2018-02-19 | SSR2 Team | 1d
| Public Comment and Outreach | 2018-02-19 | 2018-03-30 |  | 30d
| Public Comment Period | 2018-02-19 | 2018-03-30 | Public | 30d
| Socialize draft recommendations with community | 2018-02-19 | 2018-03-30 | SSR2 Team | 30d
| Final Report | 2018-04-01 | 2018-06-01 |  | 46d
| Summarize Public Comments | 2018-04-01 | 2018-04-13 | ICANN Staff | 11d
| Chapter Authors Incorporate Comments | 2018-04-16 | 2018-05-14 | Subgroups | 21d
| Final Review by SSR2 Team | 2018-05-14 | 2018-05-31 | SSR2 Team | 14d
| Send Report to Board | 2018-06-01 | 2018-06-01 | SSR2 Team | 1d
| Publish Report | 2018-06-01 | 2018-06-01 | SSR2 | 1d
| Implementation planning and feedback | 2018-07-01 | 2018-07-31 |  | 23d
| Complete ICANN organization survey on review process | 2018-07-01 | 2018-07-31 |  | 23d
| Implementation - subset of review team to provide feedback on review process and implementation | 2018-08-01
| Face to Face meetings | 2017-03-10 | 2018-03-22 |  | 270d
| ICANN 58 Copenhagen | 2017-03-10 | 2017-03-16 |  | 5d
| Madrid DNS Forum and Face to Face | 2017-05-12 | 2017-05-15 |  | 2d
| ICANN 59 Johanesburg | 2017-06-25 | 2017-06-28 |  | 4d
| ICANN 60 Abu Dhabi | 2017-10-29 | 2017-11-03 |  | 6d
| Drafting meeting, Brussels | 2018-01-22 | 2018-01-24 |  | 3d
| ICANN 60 San Juan | 2018-03-18 | 2018-03-22 |  | 5d