## Slide 1: Second Security, Stability, and Resiliency of the Domain Name System Review Team (SSR2)
ICANN60
October 2017
Meeting with [ICANN Group]

## Slide 2: Overview
Mandate & Composition of the Review Team
Review Timeline & Key Milestones
Key Areas
of Review
Questions & Discussion
1
2
3
4
Notes: To delete a box, if there are too many boxes, click the edge of the box, ensure the entire box is highlighted, then DELETE.
To update the numbers and text, click inside the circle for the numbers or in the box for the text, revise the text.

## Slide 3: Mandate
The SSR2 Review Team is assessing the:
Extent to which ICANN has successfully implemented its security, stability and resiliency efforts in relation to how it manages the unique identifiers in which it coordinates.
Effectiveness of security, stability and resiliency efforts to deal with challenges/threats to the security and stability of the DNS.
Extent to which security, stability, and resiliency efforts are fully robust to meet future challenges/threats to the security, stability and resiliency of the DNS.
Extent to which SSR1 Recommendation have been implemented
The Review Team’s mandate can be found in ICANN’s Bylaws, Section 4.6(c)

## Slide 4: Composition of Review Team
Name | SO/AC Affiliation | Region
Alain Aina | ccNSO | AF
Noorul Ameen | GAC | AP
Kerry-Ann Barrett | GAC | LAC
Don Blumenthal | SSAC | NA
James Gannon | GNSO | EUR
Mohamad Amin Hasbini | GAC | AP
Geoff Huston | SSAC | AP
Žarko Kecić | ccNSO | EUR
Boban Krsic | ccNSO | EUR
Jabhera Matogoro | ALAC | AF
Denise Michel (Co-Chair) | GNSO | NA
Eric Osterweil (Co-Chair) | RSSAC | NA
Ram Krishna Pariyar | ALAC | AP
Kaveh Ranjbar | Board appointee | EUR
Norm Ritchie | GNSO | NA

## Slide 5: SSR2: Review Timeline and Progress
*Timeline is based on a current draft work plan. Estimated dates subject to change.
Feb
2017
May
2017
May –
Sept
2017
Oct –
Jan
2018
Feb
2018
June
2018
Announce Review Team selection (ICANN Org)
Deliver Terms of Reference to ICANN Board
Collect and analyze data (in progress)
Formulate
findings & recommendations
Publish Draft Report for public comment
Deliver Final Report to ICANN Board
Jan
2019
Board Action

## Slide 6: Key Milestones
Activity | Date | Status
Launched info gathering, SSR1 briefings, outreach, and Review Team agreed to leadership by three Co-Chairs : Denise Michel, GNSO; Eric Osterweil, RSSAC; Emily Taylor, GNSO (resigned July 2017) | March 2017 | 
Briefings, due diligence, info gathering, community updates ongoing; sub-groups formed and draft work topics identified in 5 key areas: SSR1 Implementation ICANN SSR DNS SSR Future Challenges Impact of IANA transition on SSR | May 2017 | 
RFP for Gap Analysis of Implementation of SSR1 Review Recommendations published | September 2017 | 
More public consultation, outreach meetings with ICANN groups | ICANN60 | Scheduled
Drafting session for first draft of report | January 2018 | Scheduled

## Slide 7: Five Key Areas of Review
1
2
3
4
5
ICANN's implementation of 28 recommendations adopted by Board in 2012 from the first SSR Review (SSR1) (adopted/implementation launched in 2012 ).
Key security, stability, and resiliency activities for which ICANN has leading/sole responsibility.
ICANN activities that impact the security, stability, and resiliency of the Domain Name System (key activities that ICANN contributes to/facilitates).
ICANN's strategy to address potential future challenges to the secure and resilient operation of the unique identifiers systems it coordinates.
The impact of the IANA stewardship transition on the security, stability, and resiliency of ICANN and the unique identifier systems it coordinates.

## Slide 8: Fact finding - briefings and documents
Extensive background materials including:
  Mitigating unique identifier abuse
  Registry and registration security and abuse
  Operation of DNS root name system
  Risk assessment and management
  Incident response
  PTI materials
  SSR1 implementation
Detailed briefings from ICANN staff, on SSR topics including:
  Domain Abuse Reporting Tool
  ITHI reporting
  PTI-ICANN relationship
  SSR1 implementation
  ICANN’s Security Framework and emerging threats
  ICANN’s Risk Management Framework
  ICANN’s Business Continuity strategies, objectives, plans and procedures
  ICANN’s operational planning and controls, and prioritized activity recovery strategy
  ICANN’s Incident Response Structure
  ICANN’s root server operations
  ICANN’s Global Domains Division activities that relate to SSR objectives

## Slide 9: Key Developments
SSR2’s progress includes:
  Terms of reference agreed in May by consensus
  Significantly greater due diligence activity than SSR1
  Working within sub-teams to increase throughput and efficiency
  Working with outside help to complete gap analysis of SSR1 implementation
  Face-to-face sessions have been effective in making substantive progress
    For instance, the recent sub-team F2F (summary here: https://community.icann.org/pages/viewpage.action?pageId=69277737 )
    Madrid ICANN DNS Symposium
    ICANN meetings, including ICANN 60

## Slide 10: Next Steps for SSR2
Engagement at ICANN 60
  SSR2 Review Team Community Engagement Session
  Governmental Advisory Committee (GAC)
  At-Large Advisory Committee (ALAC)
  Root Server System Advisory Committee (RSSAC)
  Registries Stakeholder Group (RySG)
  Security and Stability Advisory Committee (SSAC)
  Not-for-Profit Operational Concerns (NPOC)
  Commercial Stakeholder Group (CSG)
  Non-Commercial Users Constituency (NCUC)
  Board
Face-to-Face follow up meeting directly after ICANN 60
Community outreach will continue to be a cornerstone of our work
Potential further Face-to-Face meetings of sub-teams
Regular Review Team conference calls as SSR2 transitions to drafting and recommendations

## Slide 11: Opportunities to Participate
  Public consultation session - http://sched.co/CbGX
  Sunday 29th October: 13:30 – 15:00 (Capital Suite 14)
  Face-to-Face meeting day 2 at ICANN60 - http://sched.co/CbF7
  Friday 3rd November: 09:00 – 17:30 (Capital Suite 1)
SSR2 wiki contains all of Team’s work, emails, meeting records, regular newsletters: https://community.icann.org/display/SSR/SSR2+Review
Input to the review (publicly archived): input-to-ssr2rt@icann.org
Become an observer: ssr2-observers@icann.org

## Slide 12: Questions & Discussion