Cross Community Working Group on Enhacing ICANN Accountability
Workstream 2 - Human Rights Design Team
Meeting 0 – August 16 – 19:00 UTC

---
Agenda
1. 1. Administrivia
  1. Roll call, absentees, SoIs, etc
2. 2. Opening Remarks
3. 3. Scope and purpose as outlined by WS1
4. 4. Proposed Time line
5. 5. Questions to answer (in FoI)
6. 6. Meetings
7. 7. Workplan
8. 8. AOB

---
Scope and purpose of CCWG WS2 HR DT
1. Develop Framework of Interpretation of Human Rights Bylaw
2. Subgroup deliverable:
Executive summary
 Description of issue
    1. Current state of play
  2. Recommendations
    1. Requirements for recommendation (no wordsmithing)
    2. Rationale for recommendation
  3. Assessment of recommendations
    1. Meet the NTIA criteria
    2. Compliance with WS1 recommendations

---
WS2 Proposed Timeline
WS2 Proposed Timeline
Simple/Lighter topics
June 2016: sub-groups agreed, commence work on docs for public input
Aug 2016: first discussion with CCWG
Sep 2016: refining work
Oct 2016: CCWG agrees for public input
20 Oct-30 Nov: Public Input comment period
Dec 2016: Analyze public comment staff/subgroups
Jan 2017: Sub-groups refines and revises output
Feb 2017: CCWG agrees final Output for consideration by community FOR ADOPTION at Copenhagen
Complex Topics – Intermediate/Long Term
Jun 2016: sub-groups agreed
Sep-Oct 2016: first discussion with CCWG - identifies whether and how to update community at Hyderabad
Nov-Dec 2016: second discussion with CCWG (first SUBSTANTIVE)
Jan 2017: refining work
Feb 2017: CCWG agrees docs for public input
1 Mar to 10 Apr: Public Input comment period
Apr 2017: Analyze public comment staff/subgroups
May 2017: Sub-groups refines and revises output
May/Jun 2017: CCWG agrees final Output for consideration by community

---
Questions to answer (in FoI)
1. The bylaw text makes use of the following concepts that need further clarification:
3. 1. Internationally recognized human rights
4. 2. To respect human rights
5. 3. Applicable law
6. 4. Not to enforce
7. 5. Not going out of ICANN’s scope
8. 6. (anything missing?)
9. Let’s add documents we need to answer this to the background paper:
10. https://docs.google.com/document/d/1wPU-ACb-320q4K-ScAsAwVVNYiHxlOfuNgrSKb67OYw/edit?usp=sharing.

---
Meetings
1. Planned on Tuesday 19:00 UTC (weekly)
3. Based on doodle:
  1. Fixed time and date (26/30)
  2. 19:00 UTC (30/38)
  3. Tuesday (29/36) (Thursday

---
Workplan
1. How, who, what, when?
2. Suggested steps:
3. 1. Add relevant literature to background paper
4. 2. Start drafting FoI based on specific questions / concepts
5. 3. See where the easy parts are – which we can present to CCWG
6. 4. See where contentious parts are – which we can discuss and possibly get external advice

---
AOB