IGO/INGO Access to CRP – Draft Work Plan

ICANN 53

ICANN 52

|  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Analysis Phase 1 |  |  |  |  |  |  |  |  |  |  |
| Analysis Phase 2 |  |  |  |  |  |  |  |  |  |  |
| Analysis Phase 3 |  |  |  |  |  |  |  |  |  |  |
| Analysis Phase 4 |  |  |  |  |  |  |  |  |  |  |
|  | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun |

| **Action** | **Start Date** | **End Date** |
| --- | --- | --- |
| **Analysis – Phase 1** | **9 Sept 2014** | **18 Nov 2014** |
| ***Sub Group A – Current State of UDRP & URS*** | ***9 Sept 2014*** | ***7 Oct 2014*** |
| Identify differences between the UDRP and the URS | 9 Sept 2014 | 7 Oct 2014 |
| Collaborate with UDRP & URS dispute resolution service providers as well as experienced panelists for input | 9 Sept 2014 | 7 Oct 2014 |
| Obtain representative sample of IGOs and INGOs who have filed UDRP and URS claims | 9 Sept 2014 | 7 Oct 2014 |
| ***Sub Group B - Existing IGO-INGO Protections*** | ***9 Sept 2014*** | ***18 Nov 2014*** |
| Define scope of legal protection for IGOs under Article 6ter; compare with Geneva Conventions and Nairobi Treaty | 9 Sept 2014 | 18 Nov 2014 |
| Obtain representative sample of IGOs and INGOs with registered trademarks | 9 Sept 2014 | 21 Oct 2014 |
| Identify number of IGOs that have sought protection under Article 6ter | 9 Sept 2014 | 18 Nov 2014 |
| Obtain number and list of INGOs on ECOSOC list | 9 Sept 2014 | 9 Sept 2014 |
| Obtain representative sample of IGOs – scope of mission and geographic presence | 9 Sept 2014 | 21 Oct 2014 |
| ***Sub Group C - Treatment of the Protected Groups (Part I)*** | ***9 Sept 2014*** | ***21 Oct 2014*** |
| Review prior work (2003 President’s Joint Working Group on the 2001 WIPO report) as starting point for developing substantive recommendations (i.e. evaluate prior work in light of subsequent developments e.g. introduction of New gTLD Program and new RPMs) | 9 Sept 2014 | 21 Oct 2014 |
| **ICANN 52: 8-12 February 2015**  |
| **Analysis - Phase 2** | **19 Nov 2014** | **9 Feb 2015** |
| ***Treatment of the Protected Groups (Part II)*** | ***19 Nov 2014*** | ***9 Feb 2015*** |
| Obtain representative sample of IGOs – scope of mission and geographic presence (research task) | 19 Nov 2014 | 4 Dec 2014 |
| Review relevant research to date to identify possible differences between IGOs and INGOs for purposes of this PDP - Sub-Team #1 | 19 Nov 2014 | 9 Feb 2015 |
| Develop potential considerations (e.g. qualifying requirements, authentication criteria and appeal processes) for IGOs and INGOs that would be relevant to their use of dispute resolution proceedings (existing or new) - Sub-Team #2A (IGO) & #2B (INGO)  | 19 Nov 2014 | 9 Feb 2015 |
| **Analysis - Phase 3** | **10 Feb 2015** | **4 May 2015** |
| ***Exploring UDRP and/or URS Amendments*** | ***10 Feb 2015*** | ***4 May 2015*** |
| Analyze whether similar justifications and possible amendments should apply to both the UDRP and URS, or if each procedure should be treated independently and/or differently | 10 Feb 2015 | 4 May 2015 |
| Consider relevance of other existing rights protection mechanisms (RPMs) in the AGB | 10 Feb 2015 | 4 May 2015 |
| Consider the cost issue for IGOs and INGOs to use the UDRP and/or URS | 10 Feb 2015 | 4 May 2015 |
| Consider interplay of work/possible recommendations with the forthcoming GNSO review of all RPMs | 10 Feb 2015 | 4 May 2015 |
| **Analysis - Phase 4** | **5 May 2015** | **1 Jun 2015** |
| ***Consequences of Introduction of New gTLD Program*** | ***5 May 2015*** | ***1 Jun 2015*** |
| Analyze whether there is a need to distinguish between “legacy” and “new” gTLDs | 5 May 2015 | 1 Jun 2015 |
| Review whether URS should be Consensus Policy binding on ICANN Contracted Parties | 5 May 2015 | 1 Jun 2015 |
| **ICANN 53: 21-25 June 2015** |