## NCAP Study 2 Work Plan
Task Name | Start Date | End Date | Status | Duration (days) | Owner | Comments | Column10 | Column11 | Column12 | Column13 | Column14 | Column15 | Column16 | Column17 | Column18 | Column19 | Column20 | Column21 | Column22 | Column23 | Column24 | Column25 | Column26
Project Outline Task 1: Study of ICANN Collision Reports (I. Root Cause Analysis)
Perform an analysis of ICANN Collision Reports to determine the underlying cause of these collisions | 2021-05-03 | 2022-04-15 | Complete | 347 | Technical Investigator
Produce a report titled "Study of ICANN Collision Report" on the results of the analysis | 2022-02-01 | 2022-04-15 | Complete | 73 | Technical Investigator
Technical Investigator to present Root Cause Analysis to SSAC Work Party | 2022-05-02 | 2022-05-09 |  | 7 | Technical Investigator
DG Review and comment on the "Study of ICANN Collision Report" | 2022-05-11 | 2022-05-18 |  | 7 | DG
WPAD Report to be shared to the Discussion Group list | 2022-05-02 | 2022-05-18 |  | 16 | Technical Investigator
Project Outline Task 2: Impact and Data Sensitivity Analyses (III. Case Studies) (+Task 5 subpart)
Research the impact of collisions with regards to Root servers and Resolvers for .CORP, .HOME and .MAIL | 2021-02-05 | 2021-09-08 | Complete | 215 | DG and Technical Investigator
Research the impact of collisions with regards to Root servers and Resolvers for other selected strings | 2021-02-05 | 2021-11-01 | Complete | 269 | DG and Technical Investigator
Based on the above research, evaluate the effectiveness of using multiple sources of collision data with regards to the assessing the impact of collisions | 2021-09-01 | 2021-11-15 | Complete | 75 | DG and Technical Investigator
Produce a report on the results of this work titled "Impact and Data Sensitivity Analysis" (NOTE: This document was titled "A Perspective Study of DNS Queries for Non-Existent Top-Level Domains" | 2021-10-06 | 2021-12-23 | Complete | 78 | DG and Technical Investigator
DG review and comment on "A Perspective Study of DNS Queries for Non-Existent Top-Level Domains" ahead of Public Comment. NOTE: Case studies will also be included in the Public Comment. | 2022-01-03 | 2022-01-17 | Complete | 14 | DG
Undertake an official public consultation on the draft report titled "A Perspective Study of DNS Queries for Non-Existent Top-Level Domains", and case studies | 2022-01-27 | 2022-03-18 | Complete | 50 | DG
Produce a summary of the public consultation | 2022-03-19 | 2022-04-02 | Complete | 14 | ICANN org
Amend the draft report per the results of the public consultation on "A Perspective Study of DNS Queries for Non-Existent Top-Level Domains" and "Case Study of Collision Strings" | 2022-03-21 | 2022-04-29 | Complete | 39 | DG
Produce a final version of the "A Perspective Study of DNS Queries for Non-Existent Top-Level Domains" and "Case Study of Collision Strings" | 2022-01-27 | 2022-04-29 | Complete | 92 | DG, Technical Investigator
Discussion Group consensus call on the final version of the "A Perspective Study of DNS Queries for Non-Existent Top-Level Domains" and "Case Study of Collision Strings" | See action item tracker | See action item tracker |  |  | DG
Project Outline Task 3: Response to Board Questions Relating to Phase 2 (II. Answering Board Questions)
Respond to Board questions based on the results of the "Study of ICANN Collision Reports" and "Impact and Data Sensitivity Analyses" | 2021-10-06 | 2022-06-13 |  | 205 | DG | Answering the Board questions is tied to completing the final report.
Project Outline Task 4: Production of Final Report | DATES IN THE WHOLE SECTION BELOW HAVE BEEN UPDATED
DG consensus on the workflow (high-level 5 steps) | 2022-05-11 | 2022-05-25 |  | 14 | DG
SSAC WP item - Plan for Passive Collision Assessment | 2022-04-04 | 2022-05-02 | Complete | 28 | SSAC WP
DG item - review of SSAC's proposal for Passive Collision Assessment | 2022-05-04 | 2022-05-11 |  | 7 | DG
SSAC WP - Review of Root Cause Analysis findings | 2022-05-02 | 2022-05-09 |  | 7 | SSAC WP
DG item - Review of Root Cause Analysis findings | 2022-05-11 | 2022-05-18 |  | 7 | DG
SSAC WP item - Is Passive Collision Assessment really non-disruptive? | 2022-05-09 | 2022-05-16 |  | 7 | SSAC WP
SSAC WP item - What criteria can we offer that scopes high risk labels? | 2022-05-09 | 2022-05-16 |  | 7 | SSAC WP
DG item - is passive collision assessment really non-disruptive? | 2022-05-18 | 2022-05-18 |  | 0 | DG
DG item - what criteria can we offer that scopes high risk labels? | 2022-05-18 | 2022-05-18 |  | 0 | DG
SSAC WP item- How do we interpret the CDMs? (impact = volume vs diversity) | 2022-05-16 | 2022-05-23 |  | 7 | SSAC WP
SSAC WP item - What CDMs are collected? | 2022-05-16 | 2022-05-23 |  | 7 | SSAC WP
DG item - How do we interpret the CDMs? (impact = volume vs diversity) | 2022-05-25 | 2022-06-01 |  | 7 | DG
DG item - What CDMs are collected? | 2022-05-25 | 2022-06-01 |  | 7 | DG
DG item - what is the composition and what are the responsibilities of the TRT? | 2022-06-01 | 2022-06-08 |  | 7 | DG
DG item - What criteria can we offer that scopes the need for a mitigation or remediation plan? | 2022-06-01 | 2022-06-08 |  | 7 | DG
Consideration of NCAP Study 3 and mitigation strategies | 2022-07-05 | 2022-08-15 |  | 142 | DG | This can happen during the public comment period.
Produce a draft final report titled "NCAP Study 2 Report" | 2022-02-03 | 2022-06-13 |  | 85 | DG, Technical Writer
DG review and comment on draft "NCAP Study 2 Report" | 2022-06-14 | 2022-06-28 |  | 17 | DG
Undertake a public consultation on the draft final report titled "NCAP Study 2 Report". | 2022-07-05 | 2022-08-15 |  | 41 | DG
Root Cause Analysis to be included as an appendix to the draft NCAP Study 2 Report for Public Comment. | 2022-07-05 | 2022-08-15 |  | 41 | DG
Produce a summary of the public consultation | 2022-08-16 | 2022-08-30 |  | 14 | ICANN org
Amend the draft "NCAP Study 2 Report" per the results of the public consultation | 2022-08-15 | 2022-08-30 |  | 23 | DG, Technical Writer
Publish the final report titled "NCAP Study 2 Report" | 2022-09-05 | 2022-09-05 |  | 0 | DG
ICANN Meetings
ICANN73 Prep Week | 2022-02-22 | 2022-02-24 |  | 2
ICANN73 Community Forum | 2022-03-05 | 2022-03-10 |  | 5
ICANN74 Policy Forum | 2022-06-13 | 2022-06-16 |  | 3
ICANN75 AGM | 2022-09-17 | 2022-09-22 |  | 5
Formulas:
End Date = SUM([Start Date]+7)
End Date = +SUM([Start Date]+7)
Start Date = SUM([End Date]-14)
Start Date = SUM([End Date, row above]+1)